## Workflows tracker
| ORDER | ITEM | JOB NAME | EE | MD | SPECIAL PAINT | RE | CPD | WF TYPE | MECH WORKFLOW | WF START DATE | WF COMPLETION DATE | MD WF STATUS | WORKDAYS ACTIVE | WORKDAYS ELAPSED (RE) | MECH NOTES/ PENDINGS | EE WF TYPE | ELECTRICAL WORKFLOW | WF START DATE | WF COMPLETION DATE | EE WF STATUS | ACTIVE DAYS | ELECTRICAL NOTES/ PENDINGS
| 0051035283 | 10 | SWITCHGEAR UPGRADE | LGS | OAL | STD | 4570900% | [8 empty] | Finalizado | MAKE | WF1648774 |  |  | C
[16 empty] | Finalizado | MAKE | WF1645448 |  |  | C
[16 empty] | Finalizado | MAKE | WF1647369 |  |  | C
|  | 50 | [13 empty] | Finalizado | MAKE | WF1652523 |  |  | C
| 0050206201 | 000180 | AT&T GREENWOOD - GEAR ORDER | MGL | KGF | STD | 4576200% |  | MAKE | WF1669049 | 4574800% | 4575900% | C | 11 | -3 | Finalizado | MAKE | WF1650858 |  |  | C
[9 empty] | BUY | WF1668571 | 4574700% | 4575800% | C | 11 | -4 |  | MAKE | WF1650861 |  |  | C |  |  | (Mech) Proceso de orden:
[9 empty] | MAKE | WF1668543 | 4574700% | 4575900% | C | 12 | -3 |  | MAKE | WF1650856 |  |  | x
[9 empty] | MAKE | WF1668522 | 4574700% | 4575900% | C | 12 | -3 |  | MAKE | WF1650863 |  |  | C |  |  | Finalizado | Tarea cerrada en Symmetry, orden finalizada
[9 empty] | MAKE | WF1669148 | 4574800% | 4576100% | C | 13 | -1 |  | BUY | WF1651638 |  |  | C |  |  | Actualizado | BOM actualizado, pendiente cerrar tarea
[9 empty] | MAKE | WF1669064 | 4574800% | 4575100% | C | 3 | -11 |  | MAKE | WF1655340 |  |  | C |  |  | Completado | Pendiente BOM y cerrar tarea, WFs completados
[9 empty] | MAKE | WF1669179 | 4574800% | 4575400% | C | 6 | -8 |  | MAKE | WF1655339 |  |  | C |  |  | Cancelado | Orden cancelada
[9 empty] | MAKE | WF1669735 | 4574900% | 4575600% | C | 7 | -6 |  | MAKE | WF1657391 |  |  | C
[9 empty] | BUY | WF1670537 | 4575000% | 4576100% | C | 11 | -1 |  | MAKE | WF1658163 |  |  | C |  |  | Proceso de workflows:
[14 empty] | 0 |  |  | MAKE | WF1651072 |  |  | C
| 0050206201 | 000170 | AT&T GREENWOOD - GEAR ORDER | DR | OAL | STD | 4576200% |  | MAKE | WF1667259 | 4574300% | 4575900% | C | 16 | -3 | Finalizado | BUY | WF1662321 |  |  | x |  |  | C | Workflow completado
[9 empty] | MAKE | WF1674297 | 4575700% | 4577700% | C | 20 | 15 |  | BUY | WF1650836 |  |  | C |  |  | x | Workflow cancelado
[17 empty] | MAKE | WF1650838 |  |  | C |  |  | xx/xx/xxxx | Fecha de último workflow completado
| 0050206201 | 000160 | AT&T GREENWOOD - GEAR ORDER | JAM | ADL | STD | 4576900% |  | MAKE | WF1674295 | 4575700% | 4577000% | C | 13 | 1 | Finalizado | MAKE | WF1656091 |  |  | C |  |  | xx | Mayor # días activos
[9 empty] | MAKE | WF1674300 | 4575700% | 4577000% | C | 13 | 1 |  | MAKE | WF1660918 |  |  | C |  |  | xx | Día más tardío desde RM
[9 empty] | MAKE | WF1674297 | 4575700% | 4577700% | C | 20 | 8 |  | BUY | WF1658800 |  |  | x |  |  | I | En proceso
[9 empty] | BUY | WF1670537 | 4575000% | 4576100% | C | 11 | -8 |  | BUY | WF1671148
[9 empty] | BUY | WF1668571 | 4574700% | 4575800% | C | 11 | -11
[9 empty] | MAKE | WF1676370 | 4576200% | 4577600% | C | 14 | 7
[9 empty] | BUY | WF1675631 | 4576100% | 4577700% | C | 16 | 8
[9 empty] | MAKE | WF1669148 | 4574800% | 4576100% | C | -13 | -8 |  | MAKE | WF1648985 |  |  | C
| 0050535728 | 000130 | AO SMITH MCBEE SC | AOB |  |  | 4570200% | [9 empty] | MAKE | WF1593968 |  |  | C
| 0050465708 | 000270 | COLLIER COUNTY NCWRF | DEV | [12 empty] | BUY | WF1672649
[17 empty] | BUY | WF1672650
| 0050546671 | 460 | JOHN JAY COLLEGE OF CRIMINAL JUSTI | OAC | VL | STD | 17/02/2025 | [9 empty] | BUY
MAKE
MAKE
|  |  |  | DMA | ADL |  | 17/02/2025 | [9 empty] | BUY
MAKE
| 0050754152 | 90 | TOWER SEMICONDUCTOR - SAN ANTONIO - ALTE | JTV |  |  | 4570500% | [8 empty] | ON HOLD | BUY | WF1635286 |  |  | C
[17 empty] | MAKE | WF1634581 |  |  | C
[17 empty] | MAKE | WF1634544 |  |  | C
[17 empty] | BUY | WF1634504 |  |  | C
[17 empty] | MAKE | WF1634071 |  |  | C
[17 empty] | MAKE | WF1634066 |  |  | C
[17 empty] | MAKE | WF1634065 |  |  | C
| 0050529183 | 000450 | USSF ANTENNA FACILITY PROJECT | JMZ | KGF | MISAWA | 4571300%
|  | 000460 |  | AOB | DPM | [11 empty] | BUY | WF1634013 |  |  | C
| 0050959328 | 000010 | NSBSL SUBSTATION REPLACEMENT | RAS | OAL | STD | 4572600% | [9 empty] | BUY | WF1654489 |  |  | C
[17 empty] | MAKE | WF1654647 |  |  | C
| 0050780333 | 000110 | UCSF PRAB 60CD MAR 2024 LONG LEAD SWITCH | LMB | ADL | ANSI61 | 4573000% |  | MAKE | WF1654754 | 4571900% | 4574000% | C | 21 | 10 | Finalizado
[9 empty] | BUY | WF1654753 | 4571900% | 4572900% | C | 10 | -1
[9 empty] | MAKE | WF1654757 | 4571900% | 4573600% | C | 17 | 6
[9 empty] | MAKE | WF1656229 | 4572100% | 4574000% | C | 19 | 10
[9 empty] | BUY | WF1656216 | 4572100% | 4572900% | C | 8 | -1
[9 empty] | MAKE | WF1665200 | 4574000% | 4574400% | C | 4 | 14
[9 empty] | MAKE | WF1665204 | 4574000% | 4574400% | C | 4 | 14
[9 empty] | MAKE | WF1654786 | 4571900% | 4574000% | C | 21 | 10
| 0050255139 | 000780 | CHARLOTTE WATER-MT. HOLLY PS & STOWE - | KYC | VL | STD | 4573000% |  | MAKE | WF1650970 | 4571200% | 4572700% | C | 15 | -3 | Finalizado | MAKE | WF1647350
[9 empty] | MAKE | WF1654659 | 4571900% | 4572800% | C | 9 | -2
[9 empty] | MAKE | WF1652400 | 4571400% | 4572200% | C | 8 | -8
[9 empty] | MAKE | WF1654591 | 4571900% | 4572800% | C | 9 | -2
[9 empty] | MAKE | WF1655177 | 4572000% | 4573500% | C | 15 | 5
[9 empty] | BUY | WF1655377 | 4572000% | 4572900% | C | 9 | -1
| 0050746660 | 000030 | PINELLAS COUNTY DUNN WWTP _ PALM HARBOR | JTV | KGF | STD | 4573000% |  | BUY | WF1656782 | 4572200% | 4573500% | C | 13 | 5 | Finalizado | MAKE | WF1659119 |  |  | C
[9 empty] | MAKE | WF1656778 | 4572200% | 4573500% | C | 13 | 5
[9 empty] | BUY | WF1656725 | 4572200% | 4574100% | C | 19 | 11
[9 empty] | MAKE | WF1656722 | 4572200% | 4574100% | C | 19 | 11
[9 empty] | BUY | WF1657370 | 4572300% | 4573500% | C | 12 | 5
[9 empty] | MAKE | WF1663892 | 4573600% | 4574300% | C | 7 | 13
[9 empty] | MAKE | WF1657486 | 4572300% | 4572900% | C | 6 | -1
| 0051150882 | 000010 | IRON MOUNTAIN RM#6 | CFC | OAL | STD | 4574400% |  | BUY | WF1660919 | 4573000% | 4574100% | C | 11 | -3 | Finalizado
[9 empty] | MAKE | WF1660921 | 4573000% | 4574000% | C | 10 | -4
[9 empty] | MAKE | WF1660933 | 4573000% | 4574200% | C | 12 | -2
[9 empty] | MAKE | WF1661019 | 4573000% | 4574200% | C | 12 | -2
| 0051199249 | 000050 | INTEL SOW707 FEDERAL FOUNDRY OSM | ADT | LDT | STD | 4576500% |  | MAKE | WF1672871 | 4575500% | 4577600% | C | 21 | 11 | Finalizado
[9 empty] | BUY | WF1672864 | 4575500% | 4577200% | C | 17 | 7
[9 empty] | MAKE | WF1672746 | 4575500% | 4576600% | C | 11 | 1
[9 empty] | MAKE | WF1670586 | 4575000% | 4575600% | C | 6 | -9
[9 empty] | MAKE | WF1672131 | 4575400% | 4576600% | C | 12 | 1
| 0051199249 | 000040 | INTEL SOW707 FEDERAL FOUNDRY OSM | OAC | DPM | STD | 4576800% |  | MAKE | WF1670547 | 4575000% | 4575700% | C | 7 | -11 | Finalizado
[9 empty] | BUY | WF1672053 | 4575400% | 4576400% | C | 10 | -4
[9 empty] | MAKE | WF1672069 | 4575400% | 4576400% | C | 10 | -4
[9 empty] | MAKE | WF1672080 | 4575400% | 4575800% | C | 4 | -10
[9 empty] | MAKE | WF1672589 | 4575500% | 4576100% | C | 6 | -7
[9 empty] | MAKE | WF1672697 | 4575500% | 4576600% | C | 11 | -2
[9 empty] | MAKE | WF1672726 | 4575500% | 4576600% | C | 11 | -2
[9 empty] | MAKE | WF1672783 | 4575500% | 4576600% | C | 11 | -2
[9 empty] | MAKE | WF1672790 | 4575500% | 4576100% | C | 6 | -7
|  | 000030 |  |  | VL |  |  |  | BUY | WF1672805 | 4575500% | 4576300% | C | 8 | -5 | Finalizado
[9 empty] | MAKE | WF1672826 | 4575500% | 4576300% | C | 8 | -5
[9 empty] | MAKE | WF1672131 | 4575400% | 4576600% | C | 12 | -2
[9 empty] | MAKE | WF1670586 | 4575000% | 4575600% | C | 6 | -12
[9 empty] | MAKE | WF1675519 | 4576100% | 4577600% | C | 15 | 8
[9 empty] | BUY | WF1675650 | 4576100% | 4577700% | C | 16 | 9
[9 empty] | MAKE | WF1675659 | 4576100% | 4577700% | C | 16 | 9
[9 empty] | BUY | WF1676327 | 4576200% | 4577200% | C | 10 | 4
[9 empty] | MAKE | WF1676332 | 4576200% | 4577000% | C | 8 | 2
| 0051002556 | 000010 | ROYAL CARRIBEAN ES-43478 | DMA | OAL | STD | 4577900% |  | MAKE | WF1676353 | 4576200% | 4577700% | C | 15 | -2 | Finalizado
[9 empty] | BUY | WF1676356 | 4576200% | 4577700% | C | 15 | -2
| 0051117529 | 000020 | STOWERS INSTITUTE - SUBSTATION REPLACEME | RAS | ISQ | STD | 4579300% |  | MAKE | WF1680995 | 4577200% | 4577700% | C | 5 | -16 | Finalizado
| 0051229942 | 000120 | MICRON ID1 - PROJECT OPAL -WSP - BLDG B | MGL | ADL | STD | 4580000% |  | MAKE | WF1686775 | 4578500% | 4580000% | C | 15 | 0 | Finalizado
[9 empty] | MAKE | WF1689509 | 4579100% | 4579800% | C | 7 | -2
[9 empty] | MAKE | WF1688951 | 4579000% | 4579700% | C | 7 | -3
[9 empty] | MAKE | WF1686777 | 4578500% | 4579800% | C | 13 | -2
[9 empty] | MAKE | WF1686783 | 4578500% | 4580000% | C | 15 | 0
[9 empty] | MAKE | WF1686785 | 4578500% | 4580000% | C | 15 | 0
[9 empty] | BUY | WF1686787 | 4578500% | 4580000% | C | 15 | 0
| 0051004478 | 000010 | BEACON HEALTH ES-43461 (KOHLER) | DMA | OAL | STD | 4580000% |  | MAKE | WF1690270 | 4579200% | 4580000% | C | 8 | 0 | Finalizado
[9 empty] | MAKE | WF1690272 | 4579200% | 4581300% | C | 21 | 13
[9 empty] | BUY | WF1690273 | 4579200% | 4580600% | C | 14 | 6
[9 empty] | MAKE | WF1712648 | 4583900% | 4585400% | C | 15 | 54 | Finalizado
| 0050545482 | 001640 | Y12 MERCURY TREATMENT FACILITY | ASP | FRC | STD | 4580700% |  | MAKE | WF1691558 | 4579600% | 4580000% | C | 4 | -7 | Finalizado
| 0050545482 | 001630 | Y12 MERCURY TREATMENT FACILITY | ASP | HUP | STD | 4580700% |  | MAKE | WF1693128 | 4579800% | 4580600% | C | 8 | -1 | Finalizado
[9 empty] | BUY | WF1693161 | 4579800% | 4581000% | C | 12 | 3
[9 empty] | MAKE | WF1693165 | 4579800% | 4581100% | C | 13 | 4
| 0051083956 | 000040 | MAYO CLINIC ROCHESTER - HILTON BUILDING | OAC | VL | STD | 4580700% |  | MAKE | WF1692399 | 4579700% | 4581300% | C | 16 | 6 | Finalizado
[9 empty] | BUY | WF1693140 | 4579800% | 4581300% | C | 15 | 6
[9 empty] | MAKE | WF1693146 | 4579800% | 4581700% | C | 19 | 10
| 0051034440 | 000040 | LINCOLN TRANSPORTATION AND UTILITIES LIN | JRC | ISQ | ANSI61 | 4582100% |  | MAKE | WF1694419 | 4580000% | 4580700% | C | 7 | -14 | Finalizado
| 0051034443 | 000020 | LINCOLN TRANSPORTATION AND UTILITIES LIN | JRC | LDT | ANSI61 | 4582100% |  | MAKE | WF1697178 | 4580600% | 4581100% | C | 5 | -10 | Finalizado
| 0050762569 | 000090 | MCLEOD HEALTH - CAROLINA FOREST CAMPUS H | HMA | ODE | STD | 4580700% |  | MAKE | WF1695200 | 4580300% | 4581100% | C | 8 | 4 | Finalizado
[9 empty] | MAKE | WF1695202 | 4580300% | 4581100% | C | 8 | 4
[9 empty] | MAKE | WF1695208 | 4580300% | 4581100% | C | 8 | 4
| 0050762569 | 000010 | MCLEOD HEALTH - CAROLINA FOREST CAMPUS H | JTV | CML | STD | 4581400% |  | MAKE | WF1695848 | 4580400% | 4581100% | C | 7 | -3 | Finalizado
| 0050762569 | 000040 | MCLEOD HEALTH - CAROLINA FOREST CAMPUS H | JTV | HUP | STD | 4582100% |  | MAKE | WF1697184 | 4580600% | 4581100% | C | 5 | -10 | Finalizado
| 0051329560 | 000010 | STANDALONE CONNECT TO VETERANS ES-43368 | DMA | KGF | STD | 4581400% |  | BUY | WF1693768 | 4579900% | 4581000% | C | 11 | -4 | Finalizado
[9 empty] | MAKE | WF1694324 | 4580000% | 4580700% | C | 7 | -7
| 0050988425 | 000040 | DC TILLMAN | RRD | OAL | STD | 4581900% |  | MAKE | WF1695930 | 4580400% | 4581200% | C | 8 | -7 | Finalizado | MAKE | WF1656229 | 4572100% | 4574000% | C | 13
[9 empty] | MAKE | WF1695932 | 4580400% | 4581200% | C | 8 | -7 | Finalizado | BUY | WF1656216 | 4572100% | 4572900% | C | 7
| 0051198254 | 000010 | EOEM - STATES MANUFACTURING - AA - LEWIS | JAM | VL | STD | 4581700% |  | MAKE | WF1697587 | 4580700% | 4581400% | C | 7 | -3 | Finalizado
[9 empty] | BUY | WF1697176 | 4580600% | 4581900% | C | 13 | 2
[9 empty] | MAKE | WF1697130 | 4580600% | 4581900% | C | 13 | 2
| 0051138616 | 000070 | BWXT Q9 | HMA | ODE | STD | 4583500% |  | MAKE | WF1700864 | 4581400% | 4582200% | C | 8 | -13 | Finalizado
| 0051229472 | 000100 | FRESHPET PHASE 2A - ENNIS, TX | MGL | ISQ | STD | 4584000% |  | MAKE | WF1704344 | 4582100% | 4582800% | C | 7 | -12 | Finalizado
| 0051138733 | 000070 | BWXT Q10 SUB | HMA | FRC | STD | 4584200% |  | MAKE | WF1705119 | 4582400% | 4583400% | C | 10 | -8 | Finalizado
| 0051096008 | 000080 | BF GOODRICH - FORT WAYNE PLANT - SUBSTAT | DRV | CML | ANSI61 | 4584000% |  | MAKE | WF1704554 | 4582300% | 4583400% | C | 11 | -6 | Finalizado
| 0050754152 | 000090 | TOWER SEMICONDUCTOR - SAN ANTONIO - ALTE | DMA | LDT | STD | 4583300% |  | MAKE | WF1706367 | 4582600% | 4583300% | C | 7 | 0 | Finalizado | MAKE | WF1701677 | 4567700% | 4572700% | C | 36 | 45687.4157
[9 empty] | MAKE | WF1706432 | 4582600% | 4583300% | C | 7 | 0
[9 empty] | MAKE | WF1706423 | 4582600% | 4583900% | C | 13 | 6
[9 empty] | MAKE | WF1709160 | 4582600% | 4583900% | C | 13 | 6
| 0051020870 | 000840 | BUNKER HILL WTP AND RWPS DESIGN - BUNKER | JAV | ADL | ANSI61 | 4584900% |  | MAKE | WF1709320 | 4583200% | 4584600% | C | 14 | -3 | Finalizado | BUY | WF1703229
[9 empty] | MAKE | WF1709322 | 4583200% | 4585400% | C | 22 | 5
[17 empty] | MAKE | WF1655339 | 4572000% | 4574000% | C | 14
[17 empty] | MAKE | WF1703674 | 4567800% | 4568600% | C | 7 | 45688.4157
[17 empty] | MAKE | WF1704960 | 4567900% | 4569300% | C | 10 | 45691.4157
[17 empty] | MAKE | WF1704965 | 4570000% | 4572000% | C | 15 | 45711.0725
[17 empty] | MAKE | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
[17 empty] | MAKE | WF1647369 | 4570500% | 4572000% | C | 12 | 45715.0725
[17 empty] | MAKE | WF1647350 | 4570500% | 4572000% | C | 12 | 45715.0725
[17 empty] | MAKE | WF1648774 | 4570700% | 4571500% | C | 7 | 45717.0725
[17 empty] | MAKE | WF1648985 | 4570700% | 4571500% | C | 7 | 45718.0725
[17 empty] | MAKE | WF1650970 | 4571200% | 4572700% | C | 12 | 45722.0725
[17 empty] | MAKE | WF1650858 | 4571200% | 4571500% | C | 4 | 45722.0725
[17 empty] | MAKE | WF1650861 | 4571200% | 4572700% | C | 12 | 45722.0725
[17 empty] | MAKE | WF1650863 | 4571200% | 4572700% | C | 12 | 45722.0725
[17 empty] | MAKE | WF1651072 | 4571200% | 4572000% | C | 7 | 45723.0725
[17 empty] | MAKE | WF1650856 | 4571200% | 4571200% | X | 1 | 45725.0725
| 0050665738 | 000700 | REX UNC HEALTHCARE SUBSTATION REPLACEMEN | JAM | ODE | STD | 4584200% |  | MAKE | WF1706503 | 4582400% | 4583300% | C | 9 | -9 | Finalizado | BUY | WF1651638 | 4571300% | 4572200% | C | 8 | 45723.4157
[9 empty] | MAKE | WF1707018 | 4582400% | 4583900% | C | 15 | -3 |  | MAKE | WF1652523 | 4571400% | 4572200% | C | 7 | 45725.0725
[9 empty] | MAKE | WF1707006 | 4582400% | 4583300% | C | 9 | -9 |  | MAKE | WF1652400 | 4571400% | 4572200% | C | 7 | 45724.0725
| 0050665738 | 000710 | REX UNC HEALTHCARE SUBSTATION REPLACEMEN | JAM | ODE | STD | 4583500% |  | MAKE | WF1706503 | 4582400% | 4583300% | C | 9 | -2 | Finalizado | BUY | WF1654489 | 4571900% | 4572700% | C | 7 | 45719.4157
[9 empty] | MAKE | WF1707018 | 4582400% | 4583900% | C | 15 | 4 |  | MAKE | WF1654754 | 4571900% | 4574000% | C | 15 | 45731.0725
[17 empty] | MAKE | WF1654757 | 4571900% | 4573600% | C | 13 | 45731.0725
| 0051022459 | 004500 | THE ROUX INSTITUTE | JMZ | DPM | STD | 4583500% |  | MAKE | WF1708345 | 4583100% | 4584100% | C | 10 | 6 | Finalizado
| 0050665739 | 000701 | REX UNC HEALTHCARE S | JAM | [11 empty] | Finalizado | BUY | WF1703053 | 4571400% | 4572200% | C | 7
| 0050665740 | 000702 | REX UNC HEALTHCARE S | JAM | [11 empty] | Finalizado
| 0050665741 | 000703 | REX UNC HEALTHCARE S | JAM | [11 empty] | Finalizado
[16 empty] | Finalizado | MAKE | WF1703048 | 4571300% | 4572200% | C | 8
F | 0051283748 | 000120 | TOYOTA PEMC EQUIPMENT REPLACEMENT | AOB | CML | STD | 4583800% |  | MAKE | WF1710702 | 4583400% | 4584900% | C | 15 | 11 | Finalizado | MAKE | WF1705861 | 4571900% | 4574000% | C | 15 | 45731.0725
[9 empty] | MAKE | WF1709399 | 4583200% | 4584600% | C | 14 | 8
[10 empty] | WF1716071 | 4584600% | 4584900% | C | 3 | 11
| 0051383209 | 000010 | CORNING ARM FURNACE FIT-UP | RRD | HUP | STD | 4584800% |  | BUY | WF1710562 | 4583400% | 4584900% | C | 15 | 1 | Finalizado
[9 empty] | BUY | WF1706527 | 4582600% | 4583500% | C | 9 | -13
[9 empty] | MAKE | WF1709985 | 4583300% | 4585400% | C | 21 | 6
[9 empty] | MAKE | WF1710577 | 4583400% | 4586000% | C | 26 | 12
[9 empty] | MAKE | WF1710583 | 4583400% | 4584800% | C | 14 | 0
[9 empty] | BUY | WF1718673 | 4585200% | 4585900% | C | 7 | 11
[9 empty] | MAKE | WF1711802 | 4583800% | 4584800% | C | 10 | 0
[9 empty] | MAKE | WF1710566 | 4583400% | 4585200% | C | 18 | 4 |  | 1
| 0050255139 | 000280 | CYRUSONE - CYRUSONE, INC | JRC | ISQ | STD | 4584900% |  | MAKE | WF1716259 | 4584600% | 4585500% | C | 9 | 6 | Finalizado | MAKE | WF1655177 | 4572000% | 4573500% | C | 11
|  | 000290 |  |  | FRC
| 0051296915 | 000010 | EAST CAROLINA UNIVERSITY (ECU) BRODY SCH | JAM | [11 empty] | Finalizado | BUY | WF1656782 | 4572200% | 4573400% | C | 9
| 0051296915 | 000010 |  | JAM | [11 empty] | Finalizado | MAKE | WF1657486 | 4572300% | 4573300% | C | 5
| 0051020870 | 000840 | BUNKER HILL WTP | JAV | [11 empty] | Finalizado | BUY | WF1657370 | 4572300% | 4573500% | C | 8 | Línea ya registrada en filas 137-154
| 0051020870 | 000840 | [13 empty] | Finalizado | MAKE | WF1657391 | 4572300% | 4573000% | C | 10
| 0050866188 | 004690 | JHBSPH - 528 NORTH WASHINGTON ST | JTV | VL | STD | 4584900% |  | MAKE | WF1714810 | 4584400% | 4586700% | C | 23 | 18 | Finalizado
[9 empty] | BUY | WF1715221 | 4584500% | 4585900% | C | 14 | 10
[9 empty] | BUY | WF1719682 | 4585300% | 4586800% | C | 15 | 19
[9 empty] | MAKE | WF1715227 | 4584500% | 4586000% | C | 15 | 11
| 0050206201 | 000160 | AT&T GREENWOOD - GEAR ORDER | JAM |  |  | 4576900% | [8 empty] | Finalizado | BUY | WF1658800 | 4572700% | 4572700% | X | 1 | 45740.4157
[16 empty] | Finalizado | MAKE | WF1660921 | 4573000% | 4574000% | C | 6 | 45743.0725
| 0050728484 | 018570 | MDACC CSB CLINICAL S | KYC | KGF | STD | 4589600% |  | MAKE | WF1730149 | 4587500% | 4588700% | C | 12 | -9 | Finalizado
|  | 018590 |  |  | OAL |  | 4586600% |  | BUY | WF1720473 | 4585400% | 4586200% | C | 8 | -4 | Finalizado
[9 empty] | MAKE | WF1720475 | 4585400% | 4586100% | C | 7 | -5
[9 empty] | MAKE | WF1719740 | 4585300% | 4586000% | C | 7 | -6
[9 empty] | MAKE | WF1719712 | 4585300% | 4586000% | C | 7 | -6
|  | 018600 |  |  | KGF |  |  |  | MAKE | WF1719692 | 4585300% | 4586300% | C | 10 | -3 | Finalizado
[9 empty] | MAKE | WF1719693 | 4585300% | 4586300% | C | 10 | -3
[9 empty] | BUY | WF1719696 | 4585300% | 4586100% | C | 8 | -5
[9 empty] | MAKE | WF1719687 | 4585300% | 4586300% | C | 10 | -3
| 0051427096 | 000120 | MICRON ID1 - HPM/PROBE F12A | HMA | ODE | STD | 4586800% |  | MAKE | WF1721549 | 4585600% | 4586600% | C | 10 | -2 | Finalizado | MAKE | WF179976 | 4583300% | 4584700% | C | 14
[9 empty] | MAKE | WF1721556 | 4585600% | 4586700% | C | 11 | -1 | Finalizado
| 0051306085 | 000310 | CYRUSONE - CYRUSONE, INC |  | FRC | STD | 4589100% |  | MAKE | WF1729134 | 4587300% | 4588900% | C | 16 | -2 | Finalizado
[9 empty] | MAKE | WF1729833 | 4587400% | 4588200% | C | 8 | -9
/ |  | 000300 |  | HMA | ISQ |  |  |  | MAKE | WF1729076 | 4587300% | 4588300% | C | 10 | -8
[9 empty] | BUY | WF1729021 | 4587300% | 4588200% | C | 9 | -9
[9 empty] | MAKE | WF1730939 | 4587600% | 4588300% | C | 7 | -8
| 0051199020 | 000010 | EC1 (PZ4) EC2/ EC3 (CUXTAL) | ASP | ADL | RAL7035 | 4587700% |  | MAKE | WF1727836 | 4586900% | 4588200% | C | 13 | 5 | Finalizado
[9 empty] | MAKE | WF1727653 | 4586900% | 4588100% | C | 12 | 4 | Finalizado
| 0051199025 | 000010 | [6 empty] | MAKE | WF1727106 | 4586800% | 4588200% | C | 14 | 5 | Finalizado
[9 empty] | BUY | WF1727108 | 4587400% | 4588200% | C | 8 | 5 | Finalizado
| 0051199001 | 000010 | [6 empty] | MAKE | WF1727097 | 4586800% | 4588300% | C | 15 | 6 | Finalizado
| 0050442535 | 000170 | RRMC GENERATOR REPLA | JAM | CML | STD |  |  | MAKE | WF1729188 | 4587300% | 4588300% | C | 10 |  | Finalizado
| 0011048606 | 000190 |  | JAM | CML | STD
| 0050753978 | 003800 | KAISER SAN JOSE MEDICAL CENTER HOSPITAL | ADT | HUP | STD | 4589800% |  | MAKE | WF1734261 | 4588300% | 4589400% | C | 11 | -4 | Finalizado
| 0050753978 | 003790 | KAISER SAN JOSE MEDICAL CENTER HOSPITAL | RAS | ODE | STD | 4589800% |  | MAKE | WF1735821 | 4588800% | 4589500% | C | 7 | -3 | Finalizado
[9 empty] | MAKE | WF1734562 | 4588400% | 4590400% | C | 20 | 6 | Finalizado
[9 empty] | MAKE | WF1734560 | 4588400% | 4590100% | C | 17 | 3 | Finalizado
| 0050753978 | 003780 | KAISER SAN JOSE MEDICAL CENTER HOSPITAL | RAS | CML | STD | 4589800% |  | MAKE | WF1735982 | 4588800% | 4589900% | C | 212 | 202 | Finalizado
| 0051139077 | 000030 | NORTHROP B307 3000 KVA SUBSTATIONS - PAL | AOB | OAL | STD | 4589800% |  | BUY | WF1735305 | 4588700% | 4589500% | C | 8 | -3 | Finalizado
| 0051139077 | 000110 | NORTHROP B307 3000 KVA SUBSTATIONS - PAL | AOB | OAL | STD | 4589800% |  | MAKE | WF1735314 | 4588700% | 4589700% | C | 10 | -1 | Finalizado
| 0051139077 | 000190 | NORTHROP B307 3000 KVA SUBSTATIONS - PAL | AOB | OAL | STD | 4589800% |  | MAKE | WF1740256 | 4589700% | 4590900% | C | 12 | 11 | Finalizado
| 0051027340 | 000100 | PSTV CC NORMAL GEAR | MGL | FRC | STD | 4589800% |  | BUY | WF1735363 | 4588700% | 4589800% | C | 11 | 0 | Finalizado
| 0051027340 | 000100 | PSTV CC NORMAL GEAR | MGL | FRC | STD | 4589800% |  | MAKE | WF1735409 | 4588700% | 4589800% | C | 11 | 0 | Finalizado
| 0051359498 | 000080 | KSFB PROPERY IMPROVEMENTS PHASE 1 STATE | JRC | RCI | STD | 4589800% |  | MAKE | WF1735924 | 4588800% | 4589400% | C | 6 | -4 | Finalizado
| 0051072452 | 000020 | UNITED HEALTHCARE FOR PARSONS ELECTRIC - | DRV | VL | STD | 4589800% |  | MAKE | WF1737190 | 4589000% | 4590100% | C | 11 | 3 | Finalizado
| 0051072452 | 000020 | UNITED HEALTHCARE FOR PARSONS ELECTRIC - | DRV | VL | STD | 4589800% |  | MAKE | WF1737167 | 4589000% | 4591100% | C | 21 | 13 | Finalizado
| 0051072452 | 000020 | UNITED HEALTHCARE FOR PARSONS ELECTRIC - | DRV | VL | STD | 4589800% |  | BUY | WF1737145 | 4589000% | 4590300% | C | 13 | 5 | Finalizado
| 0051436816 | 000080 | SPACEX STARBASE GIGABAY UNIT SUBSTATIONS | DEV | VL | RAL9003 | 4593000% |  | MAKE | WF1743745 | 4590400% | 4591900% | C | 15 | -11 | Finalizado
| 0051436816 | 000080 | SPACEX STARBASE GIGABAY UNIT SUBSTATIONS | DEV | VL | RAL9003 | 4593000% |  | MAKE | WF1741580 | 4590100% | 4591800% | C | 17 | -12 | Finalizado
| 0051436816 | 000080 | SPACEX STARBASE GIGABAY UNIT SUBSTATIONS | DEV | VL | RAL9003 | 4593000% |  | MAKE | WF1743757 | 4590400% | 4591900% | C | 15 | -11 | Finalizado
| 0051436816 | 000080 | SPACEX STARBASE GIGABAY UNIT SUBSTATIONS | DEV | VL | RAL9003 | 4593000% |  | MAKE | WF1743774 | 4590400% | 4591700% | C | 13 | -13 | Finalizado
| 0051436816 | 000080 | SPACEX STARBASE GIGABAY UNIT SUBSTATIONS | DEV | VL | RAL9003 | 4593100% |  | MAKE | WF1743800 | 4590400% | 4591800% | C | 14 | -13 | Finalizado
| 0051436816 | 000080 | SPACEX STARBASE GIGABAY UNIT SUBSTATIONS | DEV | VL | RAL9003 | 4593000% |  | MAKE | WF1744149 | 4590500% | 4591900% | C | 14 | -11 | Finalizado
| 0051436816 | 000010 | AUS HYDRANT SYSTEM | ASP | VL | STD | 4591900% |  | MAKE | WF1744180 | 4590500% | 4591800% | C | 13 | -1 | Finalizado
| 0051536680 | 000150 | UNITED HEALTH GROUP CUL PROJECT, CHASKA | DRV | ISQ | STD | 4590500% |  | MAKE | WF1737304 | 4589100% | 4589700% | C | 6 | -8 | Finalizado
| 0051536680 | 000150 | UNITED HEALTH GROUP CUL PROJECT, CHASKA | DRV | ISQ | STD | 4590500% |  | MAKE | WF1737308 | 4589100% | 4589700% | C | 6 | -8 | Finalizado
| 0051536681 | 000150 | UNITED HEALTH GROUP CUL PROJECT, CHASKA | DRV | ISQ | STD | 4590500% |  | MAKE | WF1737633 | 4589100% | 4589700% | C | 6 | -8 | Finalizado
| 0051536682 | 000150 | UNITED HEALTH GROUP CUL PROJECT, CHASKA | DRV | ISQ | STD | 4590500% |  | MAKE | WF1738296 | 4589400% | 4590400% | C | 10 | -1 | Finalizado
| 0051536683 | 000150 | UNITED HEALTH GROUP CUL PROJECT, CHASKA | DRV | ISQ | STD | 4590500% |  | MAKE | WF1736745 | 4588900% | 4590100% | C | 12 | -4 | Finalizado
| 0051536684 | 000150 | UNITED HEALTH GROUP CUL PROJECT, CHASKA | DRV | ISQ | STD | 4590500% |  | MAKE | WF1738352 | 4589400% | 4589800% | C | 4 | -7 | Finalizado
| 0051536685 | 000150 | UNITED HEALTH GROUP CUL PROJECT, CHASKA | DRV | ISQ | STD | 4590500% |  | MAKE | WF1738333 | 4589400% | 4591000% | C | 16 | 5 | Finalizado
| 0051536686 | 000150 | UNITED HEALTH GROUP CUL PROJECT, CHASKA | DRV | ISQ | STD | 4590500% |  | MAKE | WF1741660 | 4590100% | 4591600% | C | 15 | 11 | Finalizado
| 0051536687 | 000150 | UNITED HEALTH GROUP CUL PROJECT, CHASKA | DRV | ISQ | STD | 4590500% |  | MAKE | WF1745812 | 4590900% | 4591900% | C | 10 | 14 | Finalizado
| 0051536688 | 000150 | UNITED HEALTH GROUP CUL PROJECT, CHASKA | DRV | ISQ | STD | 4590500% |  | BUY | WF1743659 | 4590400% | 4591900% | C | 15 | 14 | Finalizado
| 0051536689 | 000150 | UNITED HEALTH GROUP CUL PROJECT, CHASKA | DRV | ISQ | STD | 4590500% |  | BUY | WF1738292 | 4589400% | 4590300% | C | 9 | -2 | Finalizado
| 0051536690 | 000150 | UNITED HEALTH GROUP CUL PROJECT, CHASKA | DRV | ISQ | STD | 4590500% |  | MAKE | WF1738214 | 4589400% | 4590400% | C | 10 | -1 | Finalizado
| 0051536690 | 000150 | UNITED HEALTH GROUP CUL PROJECT, CHASKA | DRV | ISQ | STD | 4590500% |  | MAKE | WF1738376 | 4589400% | 4589800% | C | 4 | -7 | Finalizado
| 0051472151 | 000010 | SEA NEMA DOC1033717255 EQUIPOS ELECTRICO | OAC | ODE | STD | 4591100% |  | MAKE | WF1739566 | 4589600% | 4591000% | C | 14 | -1 | Finalizado
| 0051472151 | 000010 | SEA NEMA DOC1033717255 EQUIPOS ELECTRICO | OAC | ODE | STD | 4591100% |  | MAKE | WF1739573 | 4589600% | 4590400% | C | 8 | -7 | Finalizado
| 0051472151 | 000020 | SEA NEMA DOC1033717255 EQUIPOS ELECTRICO | OAC | OAL | STD | 4591100% |  | MAKE | WF1741470 | 4590100% | 4591200% | C | 11 | 1 | Finalizado
| 0051472151 | 000020 | SEA NEMA DOC1033717255 EQUIPOS ELECTRICO | OAC | OAL | STD | 4591100% |  | BUY | WF1741474 | 4590100% | 4590500% | x | 4 | -6 | Ya dado de alta
| 0051436816 | 000130 | SPACEX STARBASE GIGABAY UNIT SUBSTATIONS | DMA | HUP | RAL9003 | 4593000% |  | MAKE | WF1740823 | 4589800% | 4591100% | C | 13 | -19 | Finalizado
| 0051436816 | 000130 | SPACEX STARBASE GIGABAY UNIT SUBSTATIONS | DMA | HUP | RAL9003 | 4593000% |  | BUY | WF1741579 | 4590100% | 4591100% | C | 10 | -19 | Finalizado
| 0051436816 | 000130 | SPACEX STARBASE GIGABAY UNIT SUBSTATIONS | DMA | HUP | RAL9003 | 4593000% |  | MAKE | WF1741580 | 4590100% | 4591800% | C | 17 | -12 | Finalizado
| 0051436816 | 000030 | SPACEX STARBASE GIGABAY UNIT SUBSTATIONS | DMA | KGF | RAL9003 | 4593000% |  | MAKE | WF1743044 | 4590300% | 4591800% | C | 15 | -12 | Finalizado
| 0051424832 | 000020 | SAPPI T103B SUBSTATION REPLACEMENT | JTV | CML | STD | 4589800% |  | MAKE | WF1739717 | 4589600% | 4590200% | C | 6 | 4 | Finalizado
| 0051217009 | 000550 | HORIZONTAL HEALTH - EMERGENCY POWER UPGRADE | JAM | FRC | STD | 4591200% |  | MAKE | WF1743744 | 4590400% | 4591800% | C | 10 | 4 | Finalizado
| 0051442285 | 000110 | GIGABAY 15KV SUBSTATIONS REV3 STARBASE T | DMA | VL | RAL9003 | 4594500% |  | MAKE | WF1747718 | 4591200% | 4591900% | C | 5 | -19 | Finalizado
| 0051442285 | 000080 | GIGABAY 15KV SUBSTATIONS REV3 STARBASE T | DEV | LDT | RAL9003 | 4594500% |  | BUY | WF1751974 | 4592200% | 4594300% | C | 16 | -3 | Finalizado
| 0051442285 | 000080 | GIGABAY 15KV SUBSTATIONS REV3 STARBASE T | DEV | LDT | RAL9003 | 4594500% |  | MAKE | WF1751976 | 4592200% | 4594500% | C | 18 | 1 | Finalizado
| 0051442285 | 000080 | GIGABAY 15KV SUBSTATIONS REV3 STARBASE T | DEV | LDT | RAL9003 | 4594500% |  | MAKE | WF1751991 | 4592200% | 4593400% | C | 10 | -8 | Finalizado
| 0051442285 | 000080 | GIGABAY 15KV SUBSTATIONS REV3 STARBASE T | DEV | LDT | RAL9003 | 4594500% |  | MAKE | WF1751996 | 4592200% | 4594300% | C | 16 | -3 | Finalizado
| 0051442285 | 000070 | GIGABAY 15KV SUBSTATIONS REV3 STARBASE T | DEV | KGF | RAL9003 | 4594500% |  | MAKE | WF1751204 | 4591900% | 4594500% | C | 19 | 1 | Finalizado
| 0051442285 | 000070 | GIGABAY 15KV SUBSTATIONS REV3 STARBASE T | DEV | KGF | RAL9003 | 4594500% |  | BUY | WF1751133 | 4591800% | 4593800% | C | 15 | -6 | Finalizado
| 0051442285 | 000070 | GIGABAY 15KV SUBSTATIONS REV3 STARBASE T | DEV | KGF | RAL9003 | 4594500% |  | MAKE | WF1750555 | 4591800% | 4593300% | C | 12 | -9 | Finalizado
| 0051442285 | 000070 | GIGABAY 15KV SUBSTATIONS REV3 STARBASE T | DEV | KGF | RAL9004 | 4594500% |  | BUY | WF1750669 | 4591800% | 4593200% | C | 11 | -10 | Finalizado
| 0051442285 | 000070 | GIGABAY 15KV SUBSTATIONS REV3 STARBASE T | DEV | KGF | RAL9005 | 4594500% |  | BUY | WF1750727 | 4591800% | 4593200% | C | 11 | -10 | Finalizado
| 0051442285 | 000070 | GIGABAY 15KV SUBSTATIONS REV3 STARBASE T | DEV | KGF | RAL9006 | 4594500% |  | BUY | WF1751199 | 4591900% | 4592900% | x | 7 | -13 | Cancelado
| 0051442285 | 000070 | GIGABAY 15KV SUBSTATIONS REV3 STARBASE T | DEV | KGF | RAL9007 | 4594500% |  | MAKE | WF1750681 | 4591800% | 4594300% | C | 18 | -3 | Finalizado
| 0051442285 | 000070 | GIGABAY 15KV SUBSTATIONS REV3 STARBASE T | DEV | KGF | RAL9008 | 4594500% |  | MAKE | WF1750728 | 4591800% | 4593900% | C | 16 | -5 | Finalizado
| 0051442285 | 000070 | GIGABAY 15KV SUBSTATIONS REV3 STARBASE T | DEV | KGF | RAL9009 | 4594500% |  | MAKE | WF1750719 | 4591800% | 4594300% | C | 18 | -3 | Finalizado
| 0051442285 | 000070 | GIGABAY 15KV SUBSTATIONS REV3 STARBASE T | DEV | KGF | RAL9010 | 4594500% |  | MAKE | WF1751222 | 4591900% | 4592900% | C | 7 | -13 | Finalizado
| 0051442285 | 000070 | GIGABAY 15KV SUBSTATIONS REV3 STARBASE T | DEV | KGF | RAL9011 | 4594500% |  | MAKE | WF1751236 | 4591900% | 4594300% | C | 17 | -3 | Finalizado
| 0051442285 | 000070 | GIGABAY 15KV SUBSTATIONS REV3 STARBASE T | DEV | KGF | RAL9012 | 4594500% |  | MAKE | WF1751231 | 4591900% | 4594300% | C | 17 | -3 | Finalizado
| 0051442285 | 000070 | GIGABAY 15KV SUBSTATIONS REV3 STARBASE T | DEV | KGF | RAL9013 | 4594500% |  | MAKE | WF1751205 | 4591900% | 4594300% | C | 17 | -3 | Finalizado
| 0051442285 | 000070 | GIGABAY 15KV SUBSTATIONS REV3 STARBASE T | DEV | KGF | RAL9014 | 4594500% |  | MAKE | WF1751155 | 4591900% | 4594500% | C | 19 | 1 | Finalizado
| 0051442285 | 000070 | GIGABAY 15KV SUBSTATIONS REV3 STARBASE T | DEV | KGF | RAL9015 | 4594500% |  | MAKE | WF1751144 | 4591900% | 4594500% | C | 19 | 1 | Finalizado
| 0051442285 | 000070 | GIGABAY 15KV SUBSTATIONS REV3 STARBASE T | DEV | KGF | RAL9016 | 4594500% |  | MAKE | WF1752089 | 4592200% | 4594500% | C | 18 | 1 | Finalizado
| 0051442285 | 000070 | GIGABAY 15KV SUBSTATIONS REV3 STARBASE T | DEV | KGF | RAL9017 | 4594500% |  | MAKE | WF1750597 | 4591800% | 4593800% | C | 15 | -6 | Finalizado
| 0051442285 | 000070 | GIGABAY 15KV SUBSTATIONS REV3 STARBASE T | DEV | KGF | RAL9018 | 4594500% |  | MAKE | WF1755425 | 4592900% | 4594500% | C | 13 | 1 | Finalizado
| 0051378342 | 000010 | EOEM-CUMMINS - TEXAS DOT | DEV | VL | ANSI61 | 4594400% |  | MAKE | WF1756385 | 4593000% | 4595300% | C | 18 | 8 | Finalizado
| 0051378342 | 000010 | EOEM-CUMMINS - TEXAS DOT | DEV | VL | ANSI61 | 4594400% |  | MAKE | WF1756603 | 4593100% | 4594400% | C | 10 | 1 | Finalizado
| 0051449809 | 000010 | HYRDO BUS 480V SWGR | JAV | RCI | STD | 4594500% |  | MAKE | WF1754205 | 4592500% | 4593300% | C | 7 | -9 | Finalizado
| 0050839092 | 002030 | MD ANDERSON CANCER CENTER CONSOLIDATED S | OAC | KGF | STD | 4594000% |  | MAKE | WF1757819 | 4593300% | 4593900% | C | 5 | -2 | Finalizado
| 0050839092 | 002030 | MD ANDERSON CANCER CENTER CONSOLIDATED S | OAC | KGF | STD | 4594000% |  | BUY | WF1757818 | 4593300% | 4593900% | C | 5 | -2 | Finalizado
| 0050839092 | 002030 | MD ANDERSON CANCER CENTER CONSOLIDATED S | OAC | KGF | STD | 4594000% |  | MAKE | WF1757184 | 4593200% | 4593700% | C | 4 | -4 | Finalizado
| 0050839092 | 002030 | MD ANDERSON CANCER CENTER CONSOLIDATED S | OAC | KGF | STD | 4594000% |  | MAKE | WF1756798 | 4593100% | 4593700% | C | 5 | -4 | Finalizado
| 0050839092 | 002030 | MD ANDERSON CANCER CENTER CONSOLIDATED S | OAC | KGF | STD | 4594000% |  | BUY | WF1756800 | 4593100% | 4593900% | C | 7 | -2 | Finalizado
| 0050839092 | 002030 | MD ANDERSON CANCER CENTER CONSOLIDATED S | OAC | KGF | STD | 4594000% |  | MAKE | WF1756814 | 4593100% | 4593900% | C | 7 | -2 | Finalizado
| 0050839092 | 002030 | MD ANDERSON CANCER CENTER CONSOLIDATED S | OAC | KGF | STD | 4594000% |  | MAKE | WF1756795 | 4593100% | 4594100% | C | 8 | 1 | Finalizado
| 0050839092 | 002030 | MD ANDERSON CANCER CENTER CONSOLIDATED S | OAC | KGF | STD | 4594000% |  | MAKE | WF1765269 | 4595000% | 4595200% | C | 3 | 9 | Finalizado
| 0050839092 | 002030 | MD ANDERSON CANCER CENTER CONSOLIDATED S | OAC | KGF | STD | 4594000% |  | MAKE | WF1756796 | 4593100% | 4593700% | C | 5 | -4 | Finalizado
| 0051576246 | 000020 | AT&T 1420 BROADWAY STREET LUBBOCK TX | JAM | ODE | STD | 4594700% |  | MAKE | WF1757153 | 4593200% | 4595100% | C | 14 | 3 | Finalizado
| 0051576246 | 000020 | AT&T 1420 BROADWAY STREET LUBBOCK TX | JAM | ODE | STD | 4594700% |  | BUY | WF1757140 | 4593200% | 4594300% | C | 8 | -5 | Finalizado
| 0051576246 | 000020 | AT&T 1420 BROADWAY STREET LUBBOCK TX | JAM | ODE | STD | 4594700% |  | MAKE | WF1757167 | 4593200% | 4593900% | C | 6 | -7 | Finalizado
| 0051576246 | 000060 | AT&T 1420 BROADWAY STREET LUBBOCK TX | JAM | ISQ | STD | 4594700% |  | MAKE | WF1757806 | 4593300% | 4595300% | C | 15 | 5 | Finalizado
| 0051576246 | 000060 | AT&T 1420 BROADWAY STREET LUBBOCK TX | JAM | ISQ | STD | 4594700% |  | BUY | WF1757815 | 4593300% | 4594700% | C | 11 | 1 | Finalizado
| 0051576246 | 000060 | AT&T 1420 BROADWAY STREET LUBBOCK TX | JAM | ISQ | STD | 4594700% |  | MAKE | WF1757835 | 4593300% | 4595100% | C | 13 | 3 | Finalizado
| 0051576246 | 000050 | AT&T 1420 BROADWAY STREET LUBBOCK TX | JAM | CML | STD | 4594700% |  | MAKE | WF1759194 | 4593700% | 4595000% | C | 10 | 2 | Finalizado
| 0051576246 | Todas las líneas | AT&T 1420 BROADWAY STREET LUBBOCK TX | JAM | ODE&ISQ&CML | STD | 4594700% |  | MAKE | WF1751263 | 4591900% | 4595300% | C | 25 | 5 | Finalizado
| 0051576246 | Todas las líneas | AT&T 1420 BROADWAY STREET LUBBOCK TX | JAM | ODE&ISQ&CML | STD | 4594700% |  | MAKE | WF1757883 | 4593300% | 4595400% | C | 16 | 6 | Finalizado
| 0051576246 | Todas las líneas | AT&T 1420 BROADWAY STREET LUBBOCK TX | JAM | ODE&ISQ&CML | STD | 4594700% |  | MAKE | WF1751255 | 4591900% | 4595200% | C | 24 | 4 | Finalizado
| 0051576246 | Todas las líneas | AT&T 1420 BROADWAY STREET LUBBOCK TX | JAM | ODE&ISQ&CML | STD | 4594700% |  | MAKE | WF1751253 | 4591900% | 4595100% | C | 23 | 3 | Finalizado
| 0051576246 | Todas las líneas | AT&T 1420 BROADWAY STREET LUBBOCK TX | JAM | ODE&ISQ&CML | STD | 4594700% |  | MAKE | WF1751246 | 4591900% | 4595000% | C | 22 | 2 | Finalizado
| 0050442535 | 000170 | RRMC GENERATOR REPLA | JAM | CML | STD | 4594500% |  | MAKE | WF1757179 | 4593300% | 4594500% | C | 9 | 1 | Finalizado
| 0050442535 | 000170 | RRMC GENERATOR REPLA | JAM | CML | STD | 4594500% |  | MAKE | WF1757866 | 4593300% | 4594300% | C | 7 | -3 | Finalizado
| 0050442535 | 000170 | RRMC GENERATOR REPLA | JAM | CML | STD | 4594500% |  | BUY | WF1759943 | 4593800% | 4594500% | C | 6 | 1 | Finalizado
| 0051378345 | 000010 | EOEM-CUMMINS- USCG RBH | HMA | OAL | ANSI61 | 4594300% |  | MAKE | WF1761226 | 4594000% | 4595300% | C | 10 | 9 | Finalizado
| 0051378345 | 000010 | EOEM-CUMMINS USCG RBH | HMA | OAL | ANSI61 | 4594300% |  | BUY | WF1760617 | 4593900% | 4595100% | C | 9 | 7 | Finalizado
| 0051378345 | 000010 | EOEM-CUMMINS USCG RBH | HMA | OAL | ANSI61 | 4594300% |  | MAKE | WF1760611 | 4593900% | 4595300% | C | 11 | 9 | Finalizado
| 0051378345 | 000010 | EOEM-CUMMINS USCG RBH | HMA | OAL | ANSI61 | 4594300% |  | MAKE | WF1760609 | 4593900% | 4595400% | C | 12 | 10 | Finalizado
| 0051378345 | 000010 | EOEM-CUMMINS USCG RBH | HMA | OAL | ANSI61 | 4594300% |  | MAKE | WF1760605 | 4593900% | 4595700% | C | 13 | 11 | Finalizado
| 0051306085 | 000300&310 | CYRUSONE, INC | HMA | ISQ&FRC | STD | 4593900% |  | BUY | WF1762078 | 4594300% | 4594700% | C | 5 | 7 | Finalizado
| 0051306085 | 000300&310 | CYRUSONE, INC | HMA | ISQ&FRC | STD | 4593900% |  | BUY | WF1762133 | 4594300% | 4594700% | C | 5 | 7 | Finalizado
| 0051306085 | 000300&310 | CYRUSONE, INC | HMA | ISQ&FRC | STD | 4593900% |  | MAKE | WF1762157 | 4594300% | 4594700% | C | 5 | 7 | Finalizado
| 0051306085 | 000300&310 | CYRUSONE, INC | HMA | ISQ&FRC | STD | 4593900% |  | BUY | WF1762796 | 4594400% | 4594700% | C | 4 | 7 | Finalizado
| 0051306085 | 000300&310 | CYRUSONE, INC | HMA | ISQ&FRC | STD | 4593900% |  | MAKE | WF1764090 | 4594600% | 4595500% | C | 7 | 12 | Finalizado
| 0051306085 | 000300&310 | CYRUSONE, INC | HMA | ISQ&FRC | STD | 4593900% |  | MAKE | WF1764092 | 4594600% | 4595500% | C | 7 | 12 | Finalizado
| 0051306085 | 000300&310 | CYRUSONE, INC | HMA | ISQ&FRC | STD | 4593900% |  | MAKE | WF1764099 | 4594600% | 4595300% | C | 6 | 11 | Finalizado
| 0051608932 | 000010 | VO#XX ACTUALIZACION PZ4 TAG: 1313-SB-010 | JAV | HUP | STD | 4595900% |  | MAKE | WF1761987 | 4594300% | 4595200% | C | 8 | -6 | Finalizado
| 0051422641 | 000010 | EOEM-CUMMINS - REID | ADT | VHL | ANSI61 | 4595700% |  | MAKE | WF1764230 | 4594600% | 4595900% | C | 10 | 3 | Finalizado
| 0051422641 | 000010 | EOEM-CUMMINS - REID | ADT | VHL | ANSI61 | 4595700% |  | MAKE | WF1764231 | 4594600% | 4595900% | C | 10 | 3 | Finalizado
| 0051422641 | 000010 | EOEM-CUMMINS - REID | ADT | VHL | ANSI61 | 4595700% |  | BUY | WF1764238 | 4594600% | 4595800% | C | 9 | 2 | Finalizado
| 0051422641 | 000010 | EOEM-CUMMINS - REID | ADT | VHL | ANSI61 | 4595700% |  | BUY | WF1762945 | 4594400% | 4595300% | x | 9
| 0051422641 | 000010 | EOEM-CUMMINS - REID | ADT | VHL | ANSI61 | 4595700% |  | MAKE | WF1767157 | 4595300% | 4595800% | C |  |  | Finalizado
| 0051422641 | 000010 | EOEM-CUMMINS - REID | ADT | VHL | ANSI61 | 4595700% |  | BUY | WF1767492 | 4595400% | 4596400% | C |  |  | Finalizado
| 0051422641 | 000010 | EOEM-CUMMINS - REID | ADT | VHL | ANSI61 | 4595700% |  | MAKE | WF1764572 | 4594700% | 4595900% | C | 9 | 3 | Finalizado
| 0051378207 | 000270 | SUNY UPSTATE MEDICAL WEISKOTTEN HALL ADD | RAS | FRC | ANSI61 | 4598500% |  | MAKE | WF1766476 | 4595200% | 4595800% | C | 5 | -16 | Finalizado
| 0051378207 | 000270 | SUNY UPSTATE MEDICAL WEISKOTTEN HALL ADD | RAS | FRC | ANSI61 | 4598500% |  | BUY | WF1775890 | 4597200% | 4598100% | C | 5 | -2 | Finalizado
| 0051378207 | 000270 | SUNY UPSTATE MEDICAL WEISKOTTEN HALL ADD | RAS | FRC | ANSI61 | 4598500% |  | MAKE | WF1776319 | 4597300% | 4598200% | C | 5 | -2 | Finalizado
| 0051378207 | 000270 | SUNY UPSTATE MEDICAL WEISKOTTEN HALL ADD | RAS | FRC | ANSI61 | 4598500% |  | MAKE | WF1775913 | 4597200% | 4598200% | C | 6 | -2 | Finalizado
| 0051378207 | 000270 | SUNY UPSTATE MEDICAL WEISKOTTEN HALL ADD | RAS | FRC | ANSI61 | 4598500% |  | MAKE | WF1782344 | 4598600% | 4599200% | C | 5 | 6 | Finalizado
| 0051378207 | 000270 | SUNY UPSTATE MEDICAL WEISKOTTEN HALL ADD | RAS | FRC | ANSI61 | 4598500% |  | MAKE | WF1777521 | 4597500% | 4598200% | C | 3 | -2 | Finalizado
| 0051378207 | 000260 | SUNY UPSTATE MEDICAL WEISKOTTEN HALL ADD | RAS | RCI | ANSI61 | 4598500% |  | MAKE | WF1765340 | 4595000% | 4595700% | C | 6 | -17 | Finalizado
| 0051378207 | 000260 | SUNY UPSTATE MEDICAL WEISKOTTEN HALL ADD | RAS | RCI | ANSI61 | 4598500% |  | MAKE | WF1763020 | 4594400% | 4595900% | C | 12 | -15 | Finalizado
| 0050728484 | 018580 | MDACC CSB CLINICAL SERVICES BUILDING | KYC | OAL | STD | 4595300% |  | MAKE | WF1766612 | 4595200% | 4596000% | C | 7 | 6 | Finalizado
| 0051354978 | 000080 | ADVENT HEALTH CARROLLWOOD GARDEN TOWER E | RAS | RCI | STD | 4595700% |  | MAKE | WF1763609 | 4594500% | 4596000% | C | 12 | 4 | Finalizado
| 0051354978 | 000080 | ADVENT HEALTH CARROLLWOOD GARDEN TOWER E | RAS | RCI | STD | 4595700% |  | MAKE | WF1765333 | 4595000% | 4596500% | C | 11 | 6 | Finalizado
| 0051536680 | 000030 a 80 | UNITEDHEALTH GROUP CUL PROJECT, CHASKA, | DRV | ADL | STD | 4596400% |  | MAKE | WF1771689 | 4596400% | 4597300% | C | 8 | 8 | Finalizado
| 0051536680 | 000030 a 80 | UNITEDHEALTH GROUP CUL PROJECT, CHASKA, | DRV | ADL | STD | 4596400% |  | MAKE | WF1771711 | 4596400% | 4597300% | C | 8 | 8 | Finalizado
| 0051536680 | 000030 a 80 | UNITEDHEALTH GROUP CUL PROJECT, CHASKA, | DRV | ADL | STD | 4596400% |  | MAKE | WF1771712 | 4596400% | 4597300% | C | 8 | 8 | Finalizado
| 0051648563 | 000070 | ENCORE WIRE NEW PLANT5 MCKINNEY | JAV | ISQ | STD | 4597300% |  | MAKE | WF1776983 | 4597400% | 4598100% | C | 3 | 4 | Finalizado
| 0051659722 | 000090 | AHO EOB CHILLER NO. 7 | JRC | CML | STD | 4598200% |  | MAKE | WF1775784 | 4597200% | 4597800% | C | 4 | -2 | Finalizado
| 0051659722 | 000090 | AHO EOB CHILLER NO. 7 | JRC | CML | STD | 4598200% |  | MAKE | WF1777092 | 4597400% | 4598100% | C | 3 | -1 | Finalizado
| 0051659722 | 000090 | AHO EOB CHILLER NO. 7 | JRC | CML | STD | 4598200% |  | MAKE | WF1776893 | 4597400% | 4598500% | C | 5 | 2 | Finalizado
| 0051659711/22 | 000090 | ADVENTHEALTH ORLANDO EOB CHILLER NO. 6 | JRC | ODE | STD | 4598200% |  | MAKE | WF1775101 | 4597100% | 4598200% | C | 7 | 1 | Finalizado
| 0051659711 | 000090 | ADVENTHEALTH ORLANDO EOB CHILLER NO. 6 | JRC | ODE | STD | 4598200% |  | BUY | WF1775087 | 4597100% | 4598200% | C | 7 | 1 | Finalizado
| 0050728484/ 0051306085 | 018590/ 018600/ 000300/ 000310 | MDACC CSB CLINICAL SERVICES BUILDING/ CYRUSONE INC | OAC/ HMA | OAL/ KGF/ ISQ/ FRC | — | — |  | CHNGBOM | WF1777652 | 4597500% | 4598000% | C | 2 |  | Finalizado
| 0051041146 | 000090/100 | BETTIS LAB CTC | ASP | ADL | STD | 4598600% |  | MAKE | WF1777247 | 4597400% | 4598200% | C | 4 | -3 | Finalizado
| 0051095105 | 000400/410 | GSK MARIETTA B55 | JAM | LDT/ OAL | STD | 4598900% |  | MAKE | WF1778438 | 4597800% | 4599200% | C | 8 | 2 | Finalizado
| 0051095105 | 000400/410 | GSK MARIETTA B55 | JAM | LDT/ OAL | STD | 4598900% |  | MAKE | WF1779134 | 4597900% | 4598700% | C | 5 | -3 | Finalizado
| 0051095105 | 000400 | GSK MARIETTA B55 | JAM | LDT | STD | 4598900% |  | MAKE | WF1779672 | 4598000% | 4598700% | C | 4 | -3 | Finalizado
| 0051647770 | 000010 | SCHNEIDER ELECTRIC USA INC WAUPACA | DEV | VL | STD | 4599300% |  | MAKE | WF1780471 | 4598100% | 4598700% | C | 4 | -5 | Finalizado
| 0051647770 | 000010 | SCHNEIDER ELECTRIC USA INC WAUPACA | DEV | VL | STD | 4599300% |  | MAKE | WF1779843 | 4598000% | 4599600% | C | 11 | 4 | Finalizado
| 0051647770 | 000010 | SCHNEIDER ELECTRIC USA INC WAUPACA | DEV | VL | STD | 4599300% |  | BUY | WF1779840 | 4598000% | 4599500% | C | 10 | 3 | Finalizado
| 0051647770 | 000010 | SCHNEIDER ELECTRIC USA INC WAUPACA | DEV | VL | STD | 4599300% |  | MAKE | WF1779839 | 4598000% | 4599300% | C | 8 | 1 | Finalizado
| 0051569319 | 000030 | AMES LAB - METALS DEVELOPMENT ROOM 150 S | OAC | CML | STD | 4600600% |  | MAKE | WF1779796 | 4598000% | 4598700% | C | 4 | -13 | Finalizado
| 0051024393 | 000310 | HF CURREN AWTP MASTER PLAN IMPROVEMENTS | HMA | ISQ | STD | 4600100% |  | MAKE | WF1781142 | 4598400% | 4599600% | C | 10 | -4 | Finalizado
| 0051024393 | 000310 | HF CURREN AWTP MASTER PLAN IMPROVEMENTS | HMA | ISQ | STD | 4600200% |  | MAKE | WF1789752 | 4600100% | 4601000% | C | 7 | 6 | Finalizado
| 0051024393 | 000310 | HF CURREN AWTP MASTER PLAN IMPROVEMENTS | HMA | ISQ | STD | 4600100% |  | MAKE | WF1786894 | 4599500% | 4600800% | C | 9 | 5 | Finalizado
| 0051024393 | 000310 | HF CURREN AWTP MASTER PLAN IMPROVEMENTS | HMA | ISQ | STD | 4600100% |  | MAKE | WF1782615 | 4598600% | 4599600% | C | 9 | -4 | Finalizado
| 0051611250 | 003280 | TEMPLE UNIVERSITY LEW KLEIN COLLEGE OF M | ATA | HUP | STD | 4599300% |  | MAKE | WF1782397 | 4598600% | 4599600% | C | 9 | 4 | Finalizado
| 0051611250 | 003280 | TEMPLE UNIVERSITY LEW KLEIN COLLEGE OF M | ATA | HUP | STD | 4599300% |  | MAKE | WF1782400 | 4598600% | 4599600% | C | 9 | 4 | Finalizado
| 0051611250 | 003280 | TEMPLE UNIVERSITY LEW KLEIN COLLEGE OF M | ATA | HUP | STD | 4599300% |  | MAKE | WF1782413 | 4598600% | 4599200% | x | 5 | -2 | Cancelado
| 0051611250 | 003280 | TEMPLE UNIVERSITY LEW KLEIN COLLEGE OF M | ATA | HUP | STD | 4599300% |  | MAKE | WF1783445 | 4598700% | 4599500% | C | 7 | 3 | Finalizado
| 0051611250 | 003280 | TEMPLE UNIVERSITY LEW KLEIN COLLEGE OF M | ATA | HUP | STD | 4599300% |  | MAKE | WF1783447 | 4598700% | 4601900% | C | 20 | 16 | Finalizado
| 0051611250 | 003280 | TEMPLE UNIVERSITY LEW KLEIN COLLEGE OF M | ATA | HUP | STD | 4599300% |  | BUY | WF1782472 | 4598600% | 4599200% | C | 5 | -2 | Finalizado
| 0051611250 | 003280 | TEMPLE UNIVERSITY LEW KLEIN COLLEGE OF M | ATA | HUP | STD | 4599400% |  | MAKE | WF1790575 | 4600200% | 4601000% | C | 6 | 12 | Finalizado
| 0051611250 | 003280 | TEMPLE UNIVERSITY LEW KLEIN COLLEGE OF M | ATA | HUP | STD | 4599500% |  | MAKE | WF1789259 | 4600000% | 4601000% | C | 8 | 11 | Finalizado
| 0051611250 | 003280 | TEMPLE UNIVERSITY LEW KLEIN COLLEGE OF M | ATA | HUP | STD | 4599300% |  | MAKE | WF1781856 | 4598500% | 4599600% | C | 10 | 4 | Finalizado
| 0051611250 | 003280 | TEMPLE UNIVERSITY LEW KLEIN COLLEGE OF M | ATA | HUP | STD | 4599400% |  | MAKE | WF1790755 | 4600200% | 4601000% | C | 6 | 12 | Finalizado
| 0051611250 | 003280 | TEMPLE UNIVERSITY LEW KLEIN COLLEGE OF M | ATA | HUP | STD | 4599500% |  | MAKE | WF1789256 | 4600000% | 4601400% | C | 10 | 13 | Finalizado
| 0051611250 | 003280 | TEMPLE UNIVERSITY LEW KLEIN COLLEGE OF M | ATA | HUP | STD | 4599600% |  | MAKE | WF1793560 | 4600800% | 4601400% | C | 5 | 12 | Finalizado
| 0051611250 | 003280 | TEMPLE UNIVERSITY LEW KLEIN COLLEGE OF M | ATA | HUP | STD | 4599600% |  | MAKE | WF1790621 | 4600200% | 4601100% | C | 6 | 10 | Finalizado
| 0051611250 | 003280 | TEMPLE UNIVERSITY LEW KLEIN COLLEGE OF M | ATA | HUP | STD | 4599700% |  | MAKE | WF1790513 | 4600200% | 4601400% | C | 8 | 11 | Finalizado
| 0051611250 | 003280 | TEMPLE UNIVERSITY LEW KLEIN COLLEGE OF M | ATA | HUP | STD | 4599700% |  | MAKE | WF1789252 | 4600200% | 4601000% | C | 6 | 9 | Finalizado
| 0051611250 | 003280 | TEMPLE UNIVERSITY LEW KLEIN COLLEGE OF M | ATA | HUP | STD | 4599300% |  | MAKE | WF1782480 | 4598600% | 4599600% | C | 9 | 4 | Finalizado
| 0051436816 | 000030 | SPACEX STARBASE GIGABAY UNIT SUBSTATIONS | DMA | KGF | RAL9003 | 4593000% |  | MAKE | WF1785760 | 4599300% | 4600000% | C | 6 | 47 | Finalizado
| 0051436816 | 000030 | SPACEX STARBASE GIGABAY UNIT SUBSTATIONS | DMA | KGF | RAL9003 | 4593000% |  | MAKE | WF1783949 | 4598800% | 4600100% | C | 10 | 48 | Finalizado
| 0051436816 | 000030 | SPACEX STARBASE GIGABAY UNIT SUBSTATIONS | DMA | KGF | RAL9003 | 4593000% |  | MAKE | WF1784326 | 4598900% | 4600000% | C | 8 | 47 | Finalizado
| 0051436816 | 000130 | SPACEX STARBASE GIGABAY UNIT SUBSTATIONS | DMA | HUP | RAL9003 | 4593000% |  | MAKE | WF1786489 | 4599400% | 4601000% | C | 12 | 54 | Finalizado
| 0051436816 | 000080 | SPACEX STARBASE GIGABAY UNIT SUBSTATIONS | DEV | VHL | RAL9003 | 4593000% |  | MAKE | WF1787624 | 4599600% | 4600300% | C | 5 | 49 | Finalizado
| 0051549615 | 000430/440/450/460/470/480/490 | GENENTECH - APOLLO 11 - EQUIPMENT | KYC | ODE | STD | 4602800% |  | MAKE | WF1787873 | 4599800% | 4600800% | C | 7 | -12 | Finalizado
| 0051549615 | 000430/440/450/460/470/480/490 | GENENTECH - APOLLO 11 - EQUIPMENT | KYC | ODE | STD | 4602800% |  | MAKE | WF1787874 | 4599800% | 4600100% | C | 3 | -16 | Finalizado
| 0051549615 | 000430/440/450/460/470/480/490 | GENENTECH - APOLLO 11 - EQUIPMENT | KYC | ODE | STD | 4602800% |  | MAKE | WF1787889 | 4599800% | 4600100% | C | 3 | -16 | Finalizado
| 0051549615 | 000430/440/450/460/470/480/490 | GENENTECH - APOLLO 11 - EQUIPMENT | KYC | ODE | STD | 4602800% |  | MAKE | WF1788202 | 4599900% | 4601000% | C | 9 | -10 | Finalizado
| 0051549615 | 000430/440/450/460/470/480/490 | GENENTECH - APOLLO 11 - EQUIPMENT | KYC | ODE | STD | 4602800% |  | MAKE | WF1788225 | 4599900% | 4601000% | C | 9 | -10 | Finalizado
| 0051129914 | 000760/750 | LOUISA COUNTY TECH CAMPUS | UFA | ADL | STD | 4600900% |  | BUY | WF1788499 | 4599900% | 4601400% | C | 11 | 4 | Finalizado
| 0051129914 | 000760/750 | LOUISA COUNTY TECH CAMPUS | UFA | ADL | STD | 4600900% |  | MAKE | WF1788501 | 4599900% | 4601500% | C | 11 | 4 | Finalizado
| 0051129914 | 000760/750 | LOUISA COUNTY TECH CAMPUS | UFA | ADL | STD | 4600900% |  | MAKE | WF1790024 | 4600100% | 4602800% | C | 16 | 11 | Finalizado
| 0051129914 | 000760/750 | LOUISA COUNTY TECH CAMPUS | UFA | ADL | STD | 4600900% |  | BUY | WF1790023 | 4600100% | 4601400% | C | 9 | 4 | Finalizado
| 0050927776 | 000950/960/970 | REPLACE NETWORK SUBSTATIONS 9A,9B,9C,9D | ASP | CML | STD | 4600900% |  | MAKE | WF1789875 | 4600100% | 4603500% | C | 21 | 16 | Finalizado
| 0050927776 | 000950/960/970 | REPLACE NETWORK SUBSTATIONS 9A,9B,9C,9D | ASP | CML | STD | 4600900% |  | MAKE | WF1789889 | 4600100% | 4603200% | C | 19 | 14 | Finalizado
| 0050927776 | 000950/960/970 | REPLACE NETWORK SUBSTATIONS 9A,9B,9C,9D | ASP | CML | STD | 4600900% |  | BUY | WF1790595 | 4600200% | 4602000% | x | 10 | 6 | Cancelado
| 0050927776 | 000950/960/970 | REPLACE NETWORK SUBSTATIONS 9A,9B,9C,9D | ASP | CML | STD | 4600900% |  | MAKE | WF1791343 | 4600300% | 4603100% | C | 17 | 14 | Finalizado
| 0050927776 | 000950/960/970 | REPLACE NETWORK SUBSTATIONS 9A,9B,9C,9D | ASP | CML | STD | 4600900% |  | MAKE | WF1791372 | 4600300% | 4602100% | C | 10 | 7 | Finalizado
| 0050927777 | 000950/960/90 | REPLACE NETWORK SUBSTATIONS 9A,9B,9C,9D | ASP | CML | STD | 4601000% |  | MAKE | WF1792636 | 4600700% | 4602500% | C | 11 | 8 | Finalizado
| 0050927778 | 000950/960/970 | REPLACE NETWORK SUBSTATIONS 9A,9B,9C,9D | ASP | CML | STD | 4601100% |  | MAKE | WF1792667 | 4600700% | 4603200% | C | 16 | 12 | Finalizado
| 0050927778 | 000950/960/970 | REPLACE NETWORK SUBSTATIONS 9A,9B,9C,9D | ASP | CML | STD | 4601100% |  | BUY | WF1797033 | 4602000% | 4603400% | C | 10 | 13 | Finalizado
| 0050927778 | 000950/960/970 | REPLACE NETWORK SUBSTATIONS 9A,9B,9C,9D | ASP | CML | STD | 4601100% |  | BUY | WF1797106 | 4602000% | 4603000% | C | 8 | 11 | Finalizado
| 0050927776 | 000950/960/970 | REPLACE NETWORK SUBSTATIONS 9A,9B,9C,9D | ASP | CML | STD | 4600900% |  | MAKE | WF1792125 | 4600600% | 4602000% | C | 9 | 6 | Finalizado
| 0051620541 | 000010 | RAYTHEON - MARLBOROUGH | JRC | GHT | STD |  |  | BUY | WF1792804 | 4600700% | 4603500% | C | 18 |  | Finalizado
| 0051461793 | 000010 | BURLINGTON NEW DOUBLE-END SUBSTATION | HMA | FRC | STD | 4603100% |  | MAKE | WF1794690 | 4601000% | 4602700% | C | 9 | -5 | Finalizado
| 0051106129 | 000320/ 580 | AT&T SWITCHGEAR UPGRADE | MGL | ISQ | STD | 4602000% |  | MAKE | WF1793584 | 4600800% | 4601400% | C | 5 | -3 | Finalizado
| 0051106129 | 000320/ 580 | AT&T SWITCHGEAR UPGRADE | MGL | ISQ | STD | 4602000% |  | MAKE | WF1793591 | 4600800% | 4601400% | C | 5 | -3 | Finalizado
| 0051615853 | 000100/ 110 | SPACEX CAPE GIGABAY M1/M2 UNIT SUBSTATIO | DEV | KGF | RAL9001 | 4602000% |  | MAKE | WF1790543 | 4600200% | 4601400% | C | 8 | -3 | Finalizado
| 0051615853 | 000100/ 110 | SPACEX CAPE GIGABAY M1/M2 UNIT SUBSTATIO | DEV | KGF | RAL9001 | 4602000% |  | MAKE | WF1791930 | 4600600% | 4601400% | C | 7 | -3 | Finalizado
| 0051615853 | 000100/ 110 | SPACEX CAPE GIGABAY M1/M2 UNIT SUBSTATIO | DEV | KGF | RAL9001 | 4602000% |  | MAKE | WF1791221 | 4600300% | 4601400% | C | 7 | -3 | Finalizado
| 0051106129 | 000310/ 490 | AT&T SWITCHGEAR UPGRADE | MGL | VL | STD | 4602000% |  | MAKE | WF1795986 | 4601400% | 4603500% | C | 13 | 11 | Finalizado
| 0051106129 | 000310/ 490 | AT&T SWITCHGEAR UPGRADE | MGL | VL | STD | 4602000% |  | MAKE | WF1795898 | 4601400% | 4602100% | C | 4 | 2 | Finalizado
| 0051106129 | 000510 | AT&T SWITCHGEAR UPGRADE | MGL | ADL | STD | 4598200% |  | MAKE | WF1795911 | 4601400% | 4603200% | C | 11 | 32 | Finalizado
| 0050829646 | 001060/ 80 | AT&T : 51 PEACHTREE CENTER AVE SE ATL | DRV | HUP/ CML | STD | 4604400% |  | MAKE | WF1797108 | 4602000% | 4603100% | C | 9 | -10 | Finalizado
| 0050829646 | 001060/ 80 | AT&T : 51 PEACHTREE CENTER AVE SE ATL | DRV | HUP/ CML | STD | 4604400% |  | MAKE | WF1796617 | 4601700% | 4603000% | C | 9 | -11 | Finalizado
| 0050829646 | 001080 | AT&T : 51 PEACHTREE CENTER AVE SE ATL | DRV | HUP | STD | 4604400% |  | BUY | WF1796616 | 4601700% | 4603600% | C | 13 | -7 | Finalizado
| 0050829646 | 001080 | AT&T : 51 PEACHTREE CENTER AVE SE ATL | DRV | HUP | STD | 4604400% |  | MAKE | WF1796605 | 4601700% | 4603200% | C | 10 | -9 | Finalizado
| 0050829646 | 001060/ 80 | AT&T : 51 PEACHTREE CENTER AVE SE ATL | DRV | HUP/ CML | STD | 4604400% |  | MAKE | WF1797190 | 4602000% | 4603500% | C | 11 | -8 | Finalizado
| 0050829646 | 001060/ 80 | AT&T : 51 PEACHTREE CENTER AVE SE ATL | DRV | HUP/ CML | STD | 4604400% |  | MAKE | WF1796648 | 4601700% | 4603700% | C | 14 | -6 | Finalizado
| 0050829646 | 001060 | AT&T : 51 PEACHTREE CENTER AVE SE ATL | DRV | CML | STD | 4604400% |  | MAKE | WF1803903 | 4603700% | 4604300% | C | 5 | -2 | Finalizado
| 0050829646 | 001060 | AT&T : 51 PEACHTREE CENTER AVE SE ATL | DRV | CML | STD | 4604400% |  | MAKE | WF1803920 | 4603700% | 4604400% | C | 6 | 1 | Finalizado
| 0050829646 | 001060/ 80 | AT&T : 51 PEACHTREE CENTER AVE SE ATL | DRV | HUP/ CML | STD | 4604400% |  | BUY | WF1796649 | 4601700% | 4603600% | C | 13 | -7 | Finalizado
| 0051732952 | 000010 | NOVO NORDISK - BLDG QC CHEM-RM LAB - CLA | DEV | ISQ | STD | 4604500% |  | MAKE | WF1796023 | 4601400% | 4603200% | C | 11 | -10 | Finalizado
| 0051732952 | 000010 | NOVO NORDISK - BLDG QC CHEM-RM LAB - CLA | DEV | ISQ | STD | 4604500% |  | MAKE | WF1799816 | 4602900% | 4603500% | C | 5 | -9 | Finalizado
| 0051218461 | 001970 | HARD LABOR CREEK WTP - WALTON COUNTY, GA | JRC | OAL |  | 4604800% |  | MAKE | WF1802551 | 4603500% | 4605100% | C | 13 | 4 | Finalizado
| 0051218461 | 001970 | HARD LABOR CREEK WTP - WALTON COUNTY, GA | JRC | OAL |  | 4604800% |  | BUY | WF1802550 | 4603500% | 4604900% | C | 11 | 2 | Finalizado
| 0051193435 | 000290 | NORTHROP B410 CHILLER UPGRADE | ASP | HUP |  | 4604500% |  | MAKE | WF1802521 | 4603500% | 4605100% | C | 13 | 5 | Finalizado
| 0051193435 | 000290 | NORTHROP B410 CHILLER UPGRADE | ASP | HUP |  | 4604500% |  | BUY | WF1802512 | 4603500% | 4604900% | C | 11 | 3 | Finalizado
| 0051008484 | 000500 | NORTH FORK PEACHTREE CREEK STORAGE TANK | DMA | RCI |  | 4605900% |  | MAKE | WF1805186 | 4604100% | 4605900% | C | 15 | 1 | Finalizado
| 0051008484 | 000500 | NORTH FORK PEACHTREE CREEK STORAGE TANK | DMA | RCI |  | 4605900% |  | BUY | WF1805185 | 4604100% | 4604100% | x | 1 | -15
| 0051008484 | 000500 | NORTH FORK PEACHTREE CREEK STORAGE TANK | DMA | RCI |  | 4605900% |  | BUY | WF1805305 | 4604100% | 4605800% | C | 14 | -2 | Finalizado
| 0051008484 | 000500 | NORTH FORK PEACHTREE CREEK STORAGE TANK | DMA | RCI |  | 4605900% |  | BUY | WF1806568 | 4604300% | 4606300% | C | 15 | 3 | Finalizado
| 0050927776 | 000980 | REPLACE NETWORK SUBSTATIONS 9A,9B,9C,9D | ASP | ODE |  | 4604800% |  | MAKE | WF1805700 | 4604200% | 4605000% | C | 7 | 3 | Finalizado
| 0051656319 | 000010 | NESTLÉ SILAO | OAC | ADL |  | 4604500% |  | MAKE | WF1803401 | 4603600% | 4604500% | C | 8 | 1 | Finalizado
| 0051656319 | 000010 | NESTLÉ SILAO | OAC | ADL |  | 4604500% |  | MAKE | WF1803393 | 4603600% | 4604400% | C | 7 | -2 | Finalizado
| 0051656319 | 000010 | NESTLÉ SILAO | OAC | ADL |  | 4604500% |  | MAKE | WF1803392 | 4603600% | 4604400% | C | 7 | -2 | Finalizado
| 0051656319 | 000010 | NESTLÉ SILAO | OAC | ADL |  | 4604500% |  | BUY | WF1803400 | 4603600% | 4605000% | C | 11 | 4 | Finalizado
| 0051656319 | 000010 | NESTLÉ SILAO | OAC | ADL |  | 4604500% |  | BUY | WF1803394 | 4603600% | 4604900% | C | 10 | 3 | Finalizado
| 0051618201 | 000040 | EOEM - REHLKO - PANAMA CITY - MILLVILLE | DMA | KGF |  | 4605200% |  | MAKE | WF1804434 | 4603800% | 4605000% | C | 9 | -3 | Finalizado
| 0051618201 | 000040 | EOEM - REHLKO - PANAMA CITY - MILLVILLE | DMA | KGF |  | 4605200% |  | MAKE | WF1807077 | 4604400% | 4605000% | C | 5 | -3 | Finalizado
| 0051618201 | 000040 | EOEM - REHLKO - PANAMA CITY - MILLVILLE | DMA | KGF |  | 4605200% |  | MAKE | WF1804277 | 4603800% | 4604800% | C | 7 | -5 | Finalizado
| 0051787649 | 000010/ 000050 | MICRON ID1 PHASE 2 - F12A UNIT SUBSTATIO | SMA | CML/ VHL |  | 4606200% |  | BUY | WF1805687 | 4604200% | 4604900% | C | 6 | -10 | Finalizado
| 0051787649 | 000010 | MICRON ID1 PHASE 2 - F12A UNIT SUBSTATIO | SMA | CML |  | 4606900% |  | MAKE | WF1805037 | 4604100% | 4604800% | C | 6 | -16 | Finalizado
| 0051343281 | 000010 | EAST BANK REGIONAL PUMP STATION - NASHVI | EGM | GHT |  | 4605900% |  | MAKE | WF1806642 | 4604300% | 4605100% | c | 7 | -7 | Finalizado
| 0051024393 | 000310 | HF CURREN AWTP MASTER PLAN IMPROVEMENTS | HMA | ISQ | STD | 4600100% |  | MAKE | WF1809205 | 4604900% | 4605800% | C | 8 | 38 | Finalizado
| 0051129914 | 000750/ 760 | LOUISA COUNTY TECH CAMPUS | UFA | ADL |  | 4603200% |  | BUY | WF1810046 | 4605000% | 4606300% | C | 10 | 22 | Finalizado
| 0051129914 | 000750/ 760 | LOUISA COUNTY TECH CAMPUS | UFA | ADL |  | 4603200% |  | MAKE | WF1810047 | 4605000% | 4605700% | C | 6 | 18 | Finalizado
| 0051523070 | 000010 | NSWC RAM LAB | JAV | RCI |  | 4612500% |  | MAKE | WF1810695 | 4605100% | 4606300% | C | 9 | -45 | Finalizado
| 0050941348 | 000150 | FC23-011 | JAM | OAL |  | 4605200% |  | BUY | WF1812731 | 4605600% | 4607000% | C | 11 | 13 | Finalizado
| 0050941348 | 000150 | FC23-011 | JAM | OAL |  | 4605200% |  | MAKE | WF1812732 | 4605600% | 4606600% | C | 9 | 11 | Finalizado
| 0050384250 | 001270 | NEW PARNASSUS | HMA | HUP |  | 4608000% |  | MAKE | WF1814275 | 4605800% | 4607100% | C | 10 | -8 | Finalizado
| 0051827227 | 000010 | NEW CASTLE | JAV | ODE |  | 4608000% |  | MAKE | WF1814058 | 4605800% | 4606500% | C | 6 | -12 | Finalizado
| 0051827227 | 000010 | NEW CASTLE | JAV | ODE |  | 4608000% |  | MAKE | WF1814064 | 4605800% | 4606600% | C | 7 | -11 | Finalizado
| 0050384250 | 001260 | NEW PARNASSUS | HMA | CML |  | 4608000% |  | BUY | WF1815038 | 4606000% | 4607300% | C | 10 | -6 | Finalizado
| 0050384250 | 001260 | NEW PARNASSUS | HMA | CML |  | 4608000% |  | MAKE | WF1815037 | 4606000% | 4607000% | C | 7 | -9 | Finalizado
| 0050384250 | 001260 | NEW PARNASSUS | HMA | CML |  | 4608000% |  | MAKE | WF1814275 | 4605800% | 4607100% | C | 10 | -8 | Finalizado
| 0051791572 | 000010 | ADVENT HEALTH CELEBRATION PATIENT TOWER | ATA | ISQ |  | 4607100% |  | MAKE | WF1815036 | 4606000% | 4607100% | C | 8 | 1 | Finalizado
| 0051008484 | 000500 | NORTH FORK PEACHTREE CREEK STORAGE TANK | DMA | RCI |  | 4605900% |  | MAKE | WF1815825 | 4606200% | 4606900% | C | 6 | 7 | Finalizado
| 0050384250 | 001240 | NEW PARNASSUS | ASP | KGF |  | 4608000% |  | MAKE | WF1815649 | 4606200% | 4606900% | C | 6 | -10 | Finalizado
| 0051212323 | 010200 | GEISINGER MEDICAL | OHO | OAL |  | 4607600% |  | MAKE | WF1815539 | 4606200% | 4606900% | C | 6 | -6 | Finalizado
| 0051212323 | 010200 | GEISINGER MEDICAL | OHO | OAL |  | 4607600% |  | BUY | WF1816621 | 4606300% | 4607800% | c | 12 | 3 | Finalizado
| 0051212323 | 010170 | GEISINGER MEDICAL | OHO | CML |  | 4607600% |  | MAKE | WF1815776 | 4606200% | 4607100% | C | 8 | -4 | Finalizado
| 0050384250 | 001250 | NEW PARNASSUS | ASP | VHL |  | 4608000% |  | BUY | WF1817261 | 4606400% | 4607700% | C | 10 | -4 | Completado
| 0050384250 | 001250 | NEW PARNASSUS | ASP | VHL |  | 4608000% |  | MAKE | WF1817258 | 4606400% | 4607800% | C | 11 | -3 | Completado
| 0050384250 | 001250 | NEW PARNASSUS | ASP | VHL |  | 4608000% |  | MAKE | WF1817252 | 4606400% | 4607100% | C | 6 | -8 | Completado
| 0050384250 | 001250 | NEW PARNASSUS | ASP | VHL |  | 4608000% |  | MAKE | WF1817227 | 4606400% | 4607300% | C | 8 | -6 | Completado
| 0051842216 | 000030 | FREIGHTLINER | JRC | ISQ |  | 4608000% |  | MAKE | WF1817340 | 4606400% | 4607100% | C | 6 | -8 | Finalizado
| 0051212323 | 010180 | GEISINGER MEDICAL | OHO | CML |  | 4607600% |  | MAKE | WF1819309 | 4606900% | 4607300% | C | 5 | -2 | Finalizado
| 0051212323 | 010180 | GEISINGER MEDICAL | OHO | CML |  | 4607600% |  | BUY | WF1819270 | 4606900% | 4607900% | C | 9 | 4 | Finalizado
| 0051272041 | 002870 | UC BERKELEY HEATHCOCK HALL | UFA | GHT |  | 4608000% |  | MAKE | WF1820647 | 4607100% | 4607900% | C | 7 | -2 | Finalizado
| 0051733188 | 000410 | PROJECT ICY HOT CORE | DEV | HUP |  | 4608500% |  | MAKE | WF1821083 | 4607200% | 4608000% | C | 7 | -4 | Completado
| 0051212323 | 010190 | GEISINGER MEDICAL | OHO | OAL |  | 4607600% |  | MAKE | WF1820616 | 4607100% | 4607900% | C | 7 | 4 | Finalizado
| 0051212323 | 010190 | GEISINGER MEDICAL | OHO | OAL |  | 4607600% |  | MAKE | WF1820617 | 4607100% | 4607900% | C | 7 | 4 | Finalizado
| 0051212323 | 010190 | GEISINGER MEDICAL | OHO | OAL |  | 4607600% |  | MAKE | WF1820618 | 4607100% | 4607900% | C | 7 | 4 | Finalizado
| 0051733188 | 000490 | PROJECT ICY HOT CORE | DEV | KGF |  | 4609100% |  | MAKE | WF1821822 | 4607300% | 4608400% | C | 8 | -6 | Completado
| 0051733188 | 000490 | PROJECT ICY HOT CORE | DEV | KGF |  | 4609100% |  | MAKE | WF1821773 | 4607300% | 4609300% | C | 15 | 3 | Completado
| 0051733188 | 000490 | PROJECT ICY HOT CORE | DEV | KGF |  | 4609100% |  | BUY | WF1821739 | 4607300% | 4608300% | C | 7 | -7 | Completado
| 0051733188 | 000490 | PROJECT ICY HOT CORE | DEV | KGF |  | 4609100% |  | MAKE | WF1821729 | 4607300% | 4608500% | C | 9 | -5 | Completado
| 0051733188 | 000490 | PROJECT ICY HOT CORE | DEV | KGF |  | 4609100% |  | MAKE | WF1821726 | 4607300% | 4605600% | C | -14 | -26 | Completado
| 0051733188 | 000430 | PROJECT ICY HOT CORE | DEV | HUP |  | 4609700% |  | MAKE | WF1822560 | 4607600% | 4609000% | C | 11 | -6 | Completado
| 0050384250 | 001230 | NEW PARNASSUS | ASP | VHL |  | 4608700% |  | MAKE | WF1824197 | 4607800% |  |  | 17 | 10
| 0051735870 | 000010 | PROJECT OPAL LLE3 | JAM | RCI |  | 4609800% |  | MAKE | WF1824746 | 4607900% | 4609200% | C | 10 | -5 | Completado
| 0051829783 | 000010 | OP-250808-15689594 | JAM | IJF |  | 4608700% |  | MAKE | WF1821248 | 4607200% | 4608400% | C | 9 | -4 | Completado
| 0051829783 | 000010 | OP-250808-15689594 | JAM | IJF |  | 4608700% |  | MAKE | WF1821837 | 4607300% | 4609100% | C | 13 | 3 | Completado
| 0051829783 | 000010 | OP-250808-15689594 | JAM | IJF |  | 4608700% |  | MAKE | WF1821845 | 4607300% | 4608700% | C | 11 | 1 | Completado
| 0051829783 | 000010 | OP-250808-15689594 | JAM | IJF |  | 4608700% |  | MAKE | WF1821779 | 4607300% |  |  | 20 | 10
| 0051829783 | 000010 | OP-250808-15689594 | JAM | IJF |  | 4608700% |  | BUY | WF1821894 | 4607300% | 4608600% | C | 10 | -2 | Completado
| 0051829783 | 000010 | OP-250808-15689594 | JAM | IJF |  | 4608700% |  | BUY | WF1821913 | 4607300% | 4608800% | C | 11 | 1 | Completado
| 0051829783 | 000010 | OP-250808-15689594 | JAM | IJF |  | 4608700% |  | MAKE | WF1822717 | 4607600% |  |  | 19 | 10
| 0051829783 | 000010 | OP-250808-15689594 | JAM | IJF |  | 4608700% |  | MAKE | WF1822807 | 4607600% | 4609000% | C | 11 | 2 | Completado
| 0051829783 | 000010 | OP-250808-15689594 | JAM | IJF |  | 4608700% |  | MAKE | WF1822810 | 4607600% | 4608400% | C | 7 | -4 | Completado
| 0051829783 | 000010 | OP-250808-15689594 | JAM | IJF |  | 4608700% |  | MAKE | WF1824061 | 4607800% |  |  | 17 | 10
| 0051829783 | 000010 | OP-250808-15689594 | JAM | IJF |  | 4608700% |  | MAKE | WF1824795 | 4607900% | 4608400% | C | 4 | -4 | Completado
| 0051733188 | 000450 | PROJECT ICY HOT CORE | DEV | KGF |  | 4609700% |  | MAKE | WF1825447 | 4608000% | 4608600% | C | 5 | -8 | Completado
| 0051674363 | 000010 | W912EF25QA023-ARMY US | HMA | ISQ |  | 4609400% |  | MAKE | WF1824946 | 4607900% |  | x | 16 | 5
| 0051631924 | 000020 | 1319-V/056. M3-SPCC | DMA | GHT |  | 4609000% |  | MAKE | WF1826405 | 4608300% | 4609000% | C | 6 | 1 | Completado
| 0051536680 | 000120 | UNITEDHEALTH GROUP | MGL | CML |  | 4609400% |  | MAKE | WF1824999 | 4607900% | 4608500% | C | 5 | -8 | Completado
| 0051536680 | 000120 | UNITEDHEALTH GROUP | MGL | CML |  | 4609400% |  | MAKE | WF1825519 | 4608000% | 4609200% | C | 9 | -3 | Completado
| 0051536680 | 000120 | UNITEDHEALTH GROUP | MGL | CML |  | 4609400% |  | MAKE | WF1826241 | 4608300% | 4608600% | C | 4 | -7 | Completado
| 0051271091 | 000890 | POLK REGIONAL WC | ATA | OAL |  | 4609400% |  | MAKE | WF1827053 | 4608400% |  |  | 13 | 5
| 0051271091 | 000890 | POLK REGIONAL WC | ATA | OAL |  | 4609400% |  | MAKE | WF1827055 | 4608400% |  |  | 13 | 5
| 0051271091 | 000890 | POLK REGIONAL WC | ATA | OAL |  | 4609400% |  | BUY | WF1827056 | 4608400% |  |  | 13 | 5
| 0051519925 | 000010 | DUNEDIN | DMA | ODE |  | 4610100% |  | MAKE | WF1826982 | 4608400% |  |  | 13 | -2
| 0051519925 | 000010 | DUNEDIN | DMA | ODE |  | 4610100% |  | MAKE | WF1827051 | 4608400% |  |  | 13 | -2
| 0051519925 | 000010 | DUNEDIN | DMA | ODE |  | 4610100% |  | MAKE | WF1827086 | 4608400% |  |  | 13 | -2
| 0051519925 | 000010 | DUNEDIN | DMA | ODE |  | 4610100% |  | MAKE | WF1827854 | 4608500% | 4609400% | C | 8 | -6 | Completado
| 0051733188 | 000590 | PROJECT ICY HOT CORE | DEV | HUP |  | 4610500% |  | BUY | WF1825521 | 4608000% |  |  | 15 | -4
| 0051733188 | 000590 | PROJECT ICY HOT CORE | DEV | HUP |  | 4610500% |  | MAKE | WF1825523 | 4608000% |  |  | 15 | -4
| 0051442285 | 000110 | GIGABAY 15KV SUBSTATIONS REV3 STARBASE T | DMA | VHL |  | 4608700% |  | MAKE | WF1827869 | 4608500% | 4609100% | C | 5 | 3 | Completado
| 0051733188 | 000390 | PROJECT ICY HOT CORE | DEV | LDT |  | 4610000% |  | MAKE | WF1828484 | 4608600% |  |  | 11 | 1
| 0051733188 | 000530 | PROJECT ICY HOT CORE | DEV | KGF |  | 4610000% |  | MAKE | WF1829111 | 4608700% |  |  | 10 | 1
| 0051436677 | 000010 | HAINES WWTP EXPANSION | KYC | GHT |  | 4611100% |  | MAKE | WF1830735 | 4609100% |  |  | 8 | -8
| 0051872300 | 000010 | WHOLESTONE FOODS FREEZER | JRC | CML |  | 4610100% |  | MAKE | WF1828567 | 4608600% | 4609200% | C | 5 | -8 | Completado
| 0051434217 | 000320 | SMUD FAOB | JAM | ADL |  | 4610700% |  | BUY | WF1830776 | 4609100% |  |  | 8 | -6
| 0051434217 | 000320 | SMUD FAOB | JAM | ADL |  | 4610700% |  | MAKE | WF1830775 | 4609100% |  |  | 8 | -6
| 0051434217 | 000320 | SMUD FAOB | JAM | ADL |  | 4610700% |  | MAKE | WF1831181 | 4609200% |  |  | 7 | -6
| 0051035589 | 000210 | CPS EMC UPGRADE | ALT | VHL |  | 4608700% |  | MAKE | WF1832012 | 4609300% |  |  | 6 | 10
| 0051700206 | 000010 | EOEM-CUMMINS-HCA S | ALT | OAL |  | 4611500% |  | MAKE | WF1832094 |  |  |  |  | -12
| 0051700206 | 000010 | EOEM-CUMMINS-HCA S | ALT | OAL |  | 4611500% |  | MAKE | WF1832636 |  |  |  |  | -12
Formulas:
WORKDAYS ACTIVE = DAYS([WF COMPLETION DATE],[WF START DATE])
WORKDAYS ACTIVE = DAYS([WF START DATE],[WF COMPLETION DATE])
WORKDAYS ELAPSED (RE) = DAYS([WF COMPLETION DATE],[RE])
WORKDAYS ELAPSED (RE) = DAYS([WF COMPLETION DATE],[RE, row above])

## Cierre de WFs
JOB NAME | TYPE | WF | START DATE | DAYS ELAPSED | NOTES | RM

## Holidays
|  |  | Holidays 2025 | Holidays 2026
4565800%
4569100%
4573300%
4576400%
4576500%
4577800%
4578600%
4591600%
4596100%
4597800%
4598000%
4598100%
4600300%
4601500%
4601600%
4602200%
WF INFORMATION
| MAKE |  |  |  | BUY |  |  | CHNG BOM
| Tasks | Phase | Total |  | Tasks | Phase | Total | Tasks | Phase | Total
| 7 | 1 | 8 |  | 3 | 1 | 3 | 7 | 1 | 7
| 3 | 2 | 10 |  | 1 | 2 | 4 | 1 | 2 | 8
| 4 | 3 | 14 |  | 4 | 3 | 8 | 3 | 3 | 11
| 2 | 4 | 16 |  | 3 | 4 | 11
| 2 | 5 | 18 |  | 3 | 5 | 14
| 2 | 6 | 20 |  | 3 | 6 | 17
TASK RESPONSIBLES
| Name | Department
JUAN CARLOS MIRANDA
CARLOS CAVASOS
DANIELA PAOLA GONZALEZ
GRECIA JUAREZ
ALEJANDRO OSUNA BALDERAS
JUAN ANTONIO CABELLO
ALBERTO MARTINEZ
VICTOR HUGO RODRIGEZ TORRALBA
ALONDRA AGUILERA
REGINA LOPEZ
JOSE PABLO AGUILAR
ABIGAIL ESTRELLO ORTIZ
REBECA CISNEROS
FERNANDO CASAS
NA
AILIA TERESA CHUCUAN

## Mech Statistics
AVG WORKDAYS PER WF MAKE | AVG WORKDAYS PER WF BUY | AVG WORKDAYS PER WF
10.7118 | 10.7 | 10.6814
ACTIVE WFS | ACTIVE WFs > 10 WORKDAYS ELAPSED | LATE ACTIVE WFs (regarding RE) | TO-BE-LATE WFs (<5 workdays pre RE)
19 | 13 | 10 | 15

## Filters (hidden)
[12 empty] | Job name | (All)
Job name | (All) | [10 empty] | Type | (All)
Type | (All) | [10 empty] | Status | (All)
Status | (All) | [10 empty] | Class | (All)
Class | (All) | [10 empty] | Product | (All)
Product | (All) | [10 empty] | Start Date [Month and Year] | (Multiple Items)
Average of Overdue Time [Expected-Completion] | Average of Active Time | Average of Pre RM Opening Time | Count of WF | [8 empty] | Average of Overdue Time [Expected-Completion] | Average of Active Time | Average of Pre RM Opening Time | Count of WF
2.243 | 9.6624 | 13.1893 | 856 | [8 empty] | 1.3933 | 8.76 | 11.2533 | 150
Job Name | (All) | [10 empty] | Job Name | (All)
Type | (All) | [10 empty] | Type | (All) |  |  | Product | (All)
Status | (All) |  |  |  |  | Product | (All) |  |  |  |  | Status | (All) |  |  | Status | (All)
Class | (All) |  |  |  |  | Status | (All) |  |  |  |  | Class | (All) |  |  | Classification [Completion-Due Date] | (Multiple Items)
Start Date [Month and Year] | (All) |  |  |  |  | Classification [Completion-Due Date] | (Multiple Items) |  |  |  |  | Start Date [Month and Year] | Mar-2026 |  |  | Start Date [Month and Year] | Mar-2026
Classification [Completion-Due Date] | Count of Classification [Completion-Due Date] |  |  |  |  | Average of Overdue Time [Expected-Completion] | [5 empty] | Classification [Completion-Due Date] | Count of Classification [Completion-Due Date] |  |  | Average of Overdue Time [Expected-Completion]
LATE | 52.22% |  |  |  |  | 5.8822 | [5 empty] | LATE | 22.41% |  |  | 5.5385
ON TIME | 45.44% | [10 empty] | ON TIME | 77.59% |  |  | Status | X
SUPER LATE | 2.336% |  |  |  |  | Status | X |  |  |  |  | Grand Total | 100% |  |  | Start Date [Month and Year] | Mar-2026
Grand Total | 100%
[6 empty] | Count of WF | Average of Pre RM Opening Time | Average of Active Time | Average of Overdue Time [Expected-Completion] | Average of Impact Time Post RM | Average of % Of completion |  |  |  |  | Count of WF | Average of Pre RM Opening Time | Average of Active Time | Average of Overdue Time [Expected-Completion] | Average of Impact Time Post RM | Average of % Of completion
[6 empty] | 44 | 11.4091 | 10.5682 | 1.9545 | -1.2727 | #N/A |  |  |  |  | 2 | 24 | 3.5 | -5 | -21.5 | 16.67%
[16 empty] | Status | C
[6 empty] | Status | C | [8 empty] | Start Date [Month and Year] | Mar-2026
[12 empty] | Type | (All)
Type | (All) |  |  |  |  | Count of WF | Average of Pre RM Opening Time | Average of Active Time | Average of Overdue Time [Expected-Completion] | Average of Impact Time Post RM |  | Status | X |  |  | Count of WF | Average of Pre RM Opening Time | Average of Active Time | Average of Overdue Time [Expected-Completion] | Average of Impact Time Post RM
Status | X |  |  |  |  | 764 | 13.1034 | 9.6034 | 2.2893 | -3.2435 |  | Class | (All) |  |  | 17 | 6.4118 | 4.5882 | -1.3529 | -2.1176
Class | (All) | [10 empty] | Classification [Completion-Due Date] | LATE |  |  | Status | I
Classification [Completion-Due Date] | LATE |  |  |  |  | Status | I |  |  |  |  | Start Date [Month and Year] | Mar-2026 |  |  | Start Date [Month and Year] | Mar-2026
Job Name | Count of WF | 2 |  |  |  | Count of WF | Average of Pre RM Opening Time | Average of Active Time | Average of Overdue Time [Expected-Completion] | Average of Impact Time Post RM |  | Job Name | Count of WF | 0 |  | Count of WF | Average of Pre RM Opening Time | Average of Active Time | Average of Overdue Time [Expected-Completion] | Average of Impact Time Post RM
KAISER SAN JOSE MEDICAL CENTER HOSPITAL | 1 |  |  |  |  | 48 | 16.1875 | 9.7708 | 1.7708 | -7.1042 |  | Grand Total |  |  |  | 39 | 15.2308 | 7.9487 | -0.38462 | -8.1026
SEA NEMA DOC1033717255 EQUIPOS ELECTRICO | 1 | [14 empty] | Status | (All)
Grand Total | 2 |  |  |  |  | Status | (All) | [8 empty] | Start Date [Month and Year] | Mar-2026
[6 empty] | Count of WF | Average of Pre RM Opening Time | Average of Active Time | Average of Overdue Time [Expected-Completion] | Average of Impact Time Post RM | [5 empty] | Count of WF | Average of Pre RM Opening Time | Average of Active Time | Average of Overdue Time [Expected-Completion] | Average of Impact Time Post RM
[6 empty] | 856 | 13.1893 | 9.6624 | 2.243 | -3.3586 | [5 empty] | 58 | 12.9483 | 6.8103 | -0.82759 | -6.8103
[16 empty] | Status | X
[6 empty] | Status | X | [8 empty] | Class | Mech
[6 empty] | Class | Mech | [8 empty] | Start Date [Month and Year] | Mar-2026
[6 empty] | Count of WF | Average of Pre RM Opening Time | Average of Active Time | Average of Overdue Time [Expected-Completion] | Average of Impact Time Post RM | Average of % Of completion |  |  |  |  | Count of WF | Average of Pre RM Opening Time | Average of Active Time | Average of Overdue Time [Expected-Completion] | Average of Impact Time Post RM | Average of % Of completion
[6 empty] | 17 | 9.2941 | 11.8235 | 3.7059 | 2.5882 | 13.71% |  |  |  |  | 1 | 22 | 6 | -3 | -17 | 33.33%
[16 empty] | Status | C
[6 empty] | Status | C | [8 empty] | Class | Mech
[6 empty] | Class | Mech | [8 empty] | Start Date [Month and Year] | Mar-2026
[12 empty] | Type | (All)
Type | (All) |  |  |  |  | Count of WF | Average of Pre RM Opening Time | Average of Active Time | Average of Overdue Time [Expected-Completion] | Average of Impact Time Post RM |  | Status | X |  |  | Count of WF | Average of Pre RM Opening Time | Average of Active Time | Average of Overdue Time [Expected-Completion] | Average of Impact Time Post RM
Status | X |  |  |  |  | 419 | 9.5179 | 8.7804 | 1.8115 | -0.58711 |  | Class | (All) |  |  | 9 | 4.3333 | 2.5556 | -1.3333 | -2.5556
Class | (All) | [10 empty] | Classification [Completion-Due Date] | (Multiple Items) |  |  | Status | I
Classification [Completion-Due Date] | (Multiple Items) |  |  |  |  | Status | I |  |  |  |  | Start Date [Month and Year] | Mar-2026 |  |  | Class | Mech
[6 empty] | Class | Mech | [8 empty] | Start Date [Month and Year] | Mar-2026
Job Name | Count of WF | 26 | [9 empty] | Job Name | Count of WF | 2
AT&T 1420 BROADWAY STREET LUBBOCK TX | 5 |  |  |  |  | Count of WF | Average of Pre RM Opening Time | Average of Active Time | Average of Overdue Time [Expected-Completion] | Average of Impact Time Post RM |  | SQD EXPANSION DE SISITEMAS DE ENERGIA | 1 |  |  | Count of WF | Average of Pre RM Opening Time | Average of Active Time | Average of Overdue Time [Expected-Completion] | Average of Impact Time Post RM
AT&T GREENWOOD - GEAR ORDER | 2 |  |  |  |  | 27 | 14.2593 | 10 | 2.5185 | -4.7407 |  | EOEM-CUMMINS- HCA ST DAVID'S S AUSTIN | 1 |  |  | 22 | 13.9545 | 8.4091 | 0.81818 | -6.2727
BUNKER HILL WTP | 1 | [10 empty] | Grand Total | 2 |  |  | Status | (All)
EC1&EC2&EC3 | 1 |  |  |  |  | Status | (All) | [8 empty] | Class | Mech
MDACC CSB CLINICAL SERVICES BUILDING | 1 |  |  |  |  | Class | Mech | [8 empty] | Start Date [Month and Year] | Mar-2026
NORTHROP B307 3000 KVA SUBSTATIONS - PAL | 2
TOWER SEMICONDUCTOR - SAN ANTONIO - ALTE | 1 |  |  |  |  | Count of WF | Average of Pre RM Opening Time | Average of Active Time | Average of Overdue Time [Expected-Completion] | Average of Impact Time Post RM | [5 empty] | Count of WF | Average of Pre RM Opening Time | Average of Active Time | Average of Overdue Time [Expected-Completion] | Average of Impact Time Post RM
UNITEDHEALTHCARE FOR PARSONS ELECTRIC | 2 |  |  |  |  | 463 | 9.7862 | 8.9633 | 1.9222 | -0.71274 | [5 empty] | 32 | 11.5 | 6.6875 | 0.09375 | -5.5625
GSK MARIETTA B55 | 1 | [14 empty] | Status | X
EOEM-CUMMINS - REIDSVILLE WTP | 1 |  |  |  |  | Status | X | [8 empty] | Class | Elec
VO#XX ACTUALIZACION PZ4 TAG: 1313-SB-010 | 1 |  |  |  |  | Class | Elec | [8 empty] | Start Date [Month and Year] | Mar-2026
SUNY UPSTATE MEDICAL WEISKOTTEN HALL ADD | 2
ADVENTHEALTH ORLANDO EOB CHILLER NO. 6 | 1 |  |  |  |  | Count of WF | Average of Pre RM Opening Time | Average of Active Time | Average of Overdue Time [Expected-Completion] | Average of Impact Time Post RM | Average of % Of completion |  |  |  |  | Count of WF | Average of Pre RM Opening Time | Average of Active Time | Average of Overdue Time [Expected-Completion] | Average of Impact Time Post RM | Average of % Of completion
AHO EOB CHILLER NO. 7 | 1 |  |  |  |  | 26 | 13.5385 | 10 | 1.0769 | -4.2692 | #N/A |  |  |  |  | 1 | 26 | 1 | -7 | -26 | 0%
AT&T 105 AUD – 9TH FLOOR SOUTH AON CLOUD | 2 | [14 empty] | Status | C
HF CURREN AWTP MASTER PLAN IMPROVEMENTS | 2 |  |  |  |  | Status | C | [8 empty] | Class | Elec
REPLACE NETWORK SUBSTATIONS 9A,9B,9C,9D | 2 |  |  |  |  | Class | Elec | [8 empty] | Start Date [Month and Year] | Mar-2026
TEMPLE UNIVERSITY LEW KLEIN COLLEGE OF M | 2
RAYTHEON - MARLBOROUGH - BUILDING 2 - PH | 1 |  |  |  |  | Count of WF | Average of Pre RM Opening Time | Average of Active Time | Average of Overdue Time [Expected-Completion] | Average of Impact Time Post RM | [5 empty] | Count of WF | Average of Pre RM Opening Time | Average of Active Time | Average of Overdue Time [Expected-Completion] | Average of Impact Time Post RM
W912EF25QA023-ARMY US | 1 |  |  |  |  | 345 | 17.458 | 10.6029 | 2.8696 | -6.4696 | [5 empty] | 8 | 8.75 | 6.875 | -1.375 | -1.625
NSWC RAM LAB | 1 | [14 empty] | Status | I
ABB BLACKLIST | 1 |  |  |  |  | Status | I | [8 empty] | Class | Elec
OP-250808-15689594 | 1 |  |  |  |  | Class | Elec | [8 empty] | Start Date [Month and Year] | Mar-2026
PROJECT OPAL LLE3 | 1
SQD EXPANSION DE SISITEMAS DE ENERGIA | 1 |  |  |  |  | Count of WF | Average of Pre RM Opening Time | Average of Active Time | Average of Overdue Time [Expected-Completion] | Average of Impact Time Post RM | [5 empty] | Count of WF | Average of Pre RM Opening Time | Average of Active Time | Average of Overdue Time [Expected-Completion] | Average of Impact Time Post RM
EOEM-CUMMINS- HCA ST DAVID'S S AUSTIN | 1 |  |  |  |  | 21 | 18.6667 | 9.4762 | 0.80952 | -10.1429 | [5 empty] | 17 | 16.8824 | 7.3529 | -1.9412 | -10.4706
Grand Total | 38 | [14 empty] | Status | (All)
[6 empty] | Status | (All) | [8 empty] | Class | Elec
[6 empty] | Class | Elec |  |  |  |  | Type | (All) |  |  | Start Date [Month and Year] | Mar-2026
Type | (All) | [10 empty] | Status | (Multiple Items)
Status | (Multiple Items) |  |  |  |  | Count of WF | Average of Pre RM Opening Time | Average of Active Time | Average of Overdue Time [Expected-Completion] | Average of Impact Time Post RM |  | Class | (All) |  |  | Count of WF | Average of Pre RM Opening Time | Average of Active Time | Average of Overdue Time [Expected-Completion] | Average of Impact Time Post RM
Class | (All) |  |  |  |  | 392 | 17.2628 | 10.5026 | 2.6403 | -6.5204 |  | Classification [Completion-Due Date] | (Multiple Items) |  |  | 26 | 14.7308 | 6.9615 | -1.9615 | -8.3462
Classification [Completion-Due Date] | (Multiple Items) | [10 empty] | Start Date [Month and Year] | Mar-2026 |  |  | Type | MAKE
[6 empty] | Type | MAKE | [8 empty] | Status | X
Job Name | Count of WF | 103 |  |  |  | Status | X |  |  |  |  | Job Name | Count of WF | 7 |  | Start Date [Month and Year] | Mar-2026
AO SMITH MCBEE SC | 1 | [10 empty] | NEW PARNASSUS HEIGHTS HOSPITAL - UCSF - | 1
AT&T 1420 BROADWAY STREET LUBBOCK TX | 19 |  |  |  |  | Count of WF | Average of Pre RM Opening Time | Average of Active Time | Average of Overdue Time [Expected-Completion] | Average of Impact Time Post RM | Average of % Of completion | AT&T 105 AUD – 9TH FLOOR SOUTH AON CLOUD | 1 |  |  | Count of WF | Average of Pre RM Opening Time | Average of Active Time | Average of Overdue Time [Expected-Completion] | Average of Impact Time Post RM | Average of % Of completion
AT&T GREENWOOD - GEAR ORDER | 13 |  |  |  |  | 18 | 18.6667 | 13.1667 | 5 | -5.4444 | 2.469% | PROJECT ICY HOT CORE AND SHELL | 1 |  |  | 2 | 24 | 3.5 | -5 | -21.5 | 16.67%
AUS HYDRANT SYSTEM | 1 | [10 empty] | CPS EMC UPGRADE - SAN ANTONIO - ALTERMAN | 1 |  |  | Type | MAKE
BEACON HEALTH ES-43461 | 4 |  |  |  |  | Type | MAKE |  |  |  |  | DUNEDIN WWTP ELECTRICAL SYSTEM UPGRADES | 4 |  |  | Status | C
BF GOODRICH - FORT WAYNE PLANT - SUBSTAT | 1 |  |  |  |  | Status | C |  |  |  |  | POLK REGIONAL WC SE WELLFIELD AND WATER | 3 |  |  | Start Date [Month and Year] | Mar-2026
BUNKER HILL WTP | 17 | [10 empty] | UT RED MCCOMBS UNDERGRADUATE SCHOOL OF B | 2
BURLINGTON NEW DOUBLE-END SUBSTATION | 2 |  |  |  |  | Count of WF | Average of Pre RM Opening Time | Average of Active Time | Average of Overdue Time [Expected-Completion] | Average of Impact Time Post RM |  | Grand Total | 13 |  |  | Count of WF | Average of Pre RM Opening Time | Average of Active Time | Average of Overdue Time [Expected-Completion] | Average of Impact Time Post RM
BWXT Q10 SUB | 1 |  |  |  |  | 540 | 14.9926 | 9.7185 | 2.9981 | -4.9741 | [5 empty] | 14 | 9.2143 | 4.4286 | -1.0714 | -5.2143
CHARLOTTE WATER-MT. HOLLY PS & STOWE - | 6 | [14 empty] | Type | MAKE
CORNING ARM FURNACE FIT-UP | 5 |  |  |  |  | Type | MAKE | [8 empty] | Status | I
CUMMINS POWER GENERATION DOCK DOORS | 1 |  |  |  |  | Status | I | [8 empty] | Start Date [Month and Year] | Mar-2026
CYRUSONE - CYRUSONE, INC | 5
DC TILLMAN | 6 |  |  |  |  | Count of WF | Average of Pre RM Opening Time | Average of Active Time | Average of Overdue Time [Expected-Completion] | Average of Impact Time Post RM | [5 empty] | Count of WF | Average of Pre RM Opening Time | Average of Active Time | Average of Overdue Time [Expected-Completion] | Average of Impact Time Post RM
EAST CAROLINA UNIVERSITY (ECU) BRODY SCH | 1 |  |  |  |  | 35 | 17 | 10.3429 | 3.2286 | -7.3143 | [5 empty] | 26 | 15.8462 | 7.8077 | 0.5 | -8.8846
EC1&EC2&EC3 | 7 | [14 empty] | Type | MAKE
EOEM - STATES MANUFACTURING - AA - LEWIS | 2 |  |  |  |  | Type | MAKE | [8 empty] | Status | (All)
EOEM-CUMMINS - USCG RIO BAYAMON | 4 |  |  |  |  | Status | (All) | [8 empty] | Start Date [Month and Year] | Mar-2026
GIGABAY 15KV SUBSTATIONS REV3 STARBASE T | 17
HORIZON HEALTH - EMERGENCY POWER UPGRADE | 1 |  |  |  |  | Count of WF | Average of Pre RM Opening Time | Average of Active Time | Average of Overdue Time [Expected-Completion] | Average of Impact Time Post RM | Average of Completion Days Template |  |  |  |  | Count of WF | Average of Pre RM Opening Time | Average of Active Time | Average of Overdue Time [Expected-Completion] | Average of Impact Time Post RM | Average of Completion Days Template
INTEL SOW707 FEDERAL FOUNDRY OSM | 7 |  |  |  |  | 593 | 15.2226 | 9.86 | 3.0725 | -5.1265 | 6.7875 |  |  |  |  | 42 | 14.0238 | 6.4762 | -0.28571 | -8.2619 | 6.7619
IRON MOUNTAIN RM#6 | 1 | [14 empty] | Type | BUY
JHBSPH - 528 NORTH WASHINGTON ST | 4 |  |  |  |  | Type | BUY | [8 empty] | Status | X
KAISER SAN JOSE MEDICAL CENTER HOSPITAL | 6 |  |  |  |  | Status | X | [8 empty] | Start Date [Month and Year] | Mar-2026
MDACC CSB CLINICAL SERVICES BUILDING | 7
MICRON ID1 - HPM/PROBE F12A | 6 |  |  |  |  | Count of WF | Average of Pre RM Opening Time | Average of Active Time | Average of Overdue Time [Expected-Completion] | Average of Impact Time Post RM | Average of % Of completion |  |  |  |  | Count of WF | Average of Pre RM Opening Time | Average of Active Time | Average of Overdue Time [Expected-Completion] | Average of Impact Time Post RM | Average of % Of completion
MICRON ID1 - PROJECT OPAL - WSP - BLDG B | 1 |  |  |  |  | 25 | 6.4 | 9 | -0.04 | 1.84 | 8.941%
MICRON ID1 - PROJECT OPAL -WSP - BLDG B | 5 | [14 empty] | Type | BUY
NORTHROP B307 3000 KVA SUBSTATIONS - PAL | 2 |  |  |  |  | Type | BUY | [8 empty] | Status | C
NSBSL SUBSTATION REPLACEMENT | 2 |  |  |  |  | Status | C | [8 empty] | Start Date [Month and Year] | Mar-2026
PINELLAS COUNTY DUNN WWTP _ PALM HARBOR | 4
PSTV CC NORMAL GEAR | 2 |  |  |  |  | Count of WF | Average of Pre RM Opening Time | Average of Active Time | Average of Overdue Time [Expected-Completion] | Average of Impact Time Post RM | [5 empty] | Count of WF | Average of Pre RM Opening Time | Average of Active Time | Average of Overdue Time [Expected-Completion] | Average of Impact Time Post RM
REX UNC HEALTHCARE S | 7 |  |  |  |  | 217 | 9.6498 | 9.5069 | 0.62212 | 0.11982 | [5 empty] | 2 | 4 | 6.5 | -3.5 | 3.5
ROYAL CARRIBEAN ES-43478 | 1 | [14 empty] | Type | BUY
RRMC GENERATOR REPLACEMENT PROJECT | 3 |  |  |  |  | Type | BUY | [8 empty] | Status | I
SEA NEMA DOC1033717255 EQUIPOS ELECTRICO | 4 |  |  |  |  | Status | I | [8 empty] | Start Date [Month and Year] | Mar-2026
SPACEX STARBASE GIGABAY UNIT SUBSTATIONS | 12
SWITCHGEAR UPGRADE | 3 |  |  |  |  | Count of WF | Average of Pre RM Opening Time | Average of Active Time | Average of Overdue Time [Expected-Completion] | Average of Impact Time Post RM | [5 empty] | Count of WF | Average of Pre RM Opening Time | Average of Active Time | Average of Overdue Time [Expected-Completion] | Average of Impact Time Post RM
TALLAHASSEE POLICE DEPARTMENT HEADQUARTE | 5 |  |  |  |  | 13 | 14 | 8.2308 | -2.1538 | -6.5385 | [5 empty] | 13 | 14 | 8.2308 | -2.1538 | -6.5385
THE ROUX INSTITUTE | 2 | [14 empty] | Type | BUY
TOWER SEMICONDUCTOR - SAN ANTONIO - ALTE | 8 |  |  |  |  | Type | BUY | [8 empty] | Status | (All)
TOYOTA PEMC | 1 |  |  |  |  | Status | (All) | [8 empty] | Start Date [Month and Year] | Mar-2026
UCSF PRAB 60CD MAR 2024 LONG LEAD SWITCH | 4
UNITEDHEALTH GROUP CUL PROJECT, CHASKA, | 8 |  |  |  |  | Count of WF | Average of Pre RM Opening Time | Average of Active Time | Average of Overdue Time [Expected-Completion] | Average of Impact Time Post RM | Average of Completion Days Template |  |  |  |  | Count of WF | Average of Pre RM Opening Time | Average of Active Time | Average of Overdue Time [Expected-Completion] | Average of Impact Time Post RM | Average of Completion Days Template
UNITEDHEALTHCARE FOR PARSONS ELECTRIC | 9 |  |  |  |  | 255 | 9.5529 | 9.3922 | 0.41569 | -0.05098 | 8.9765 |  |  |  |  | 15 | 12.6667 | 8 | -2.3333 | -5.2 | 10.3333
USSF ANTENNA FACILITY PROJECT | 1
Y12 MERCURY TREATMENT FACILITY | 4 | [14 empty] | WF SUBMITTAL [RM<5/10 DAYS] | LATE BY ENG
EOEM-CUMMINS - TEXAS DOT | 20 |  |  |  |  | WF SUBMITTAL [RM<5/10 DAYS] | LATE BY ENG | [8 empty] | Start Date [Month and Year] | Mar-2026
MD ANDERSON CANCER CENTER CONSOLIDATED S | 3
NEW PARNASSUS HEIGHTS HOSPITAL - UCSF - | 19 |  |  |  |  | Count of WF | Average of Pre RM Opening Time | Average of Active Time | Average of Overdue Time [Expected-Completion] | Average of Impact Time Post RM | Average of Completion Days Template |  |  |  |  | Count of WF | Average of Pre RM Opening Time | Average of Active Time | Average of Overdue Time [Expected-Completion] | Average of Impact Time Post RM | Average of Completion Days Template
GSK MARIETTA B55 | 4 |  |  |  |  | 174 | -9.1552 | 7.7529 | 0.48276 | 16.2701 | 7.2701 |  |  |  |  | 19 | -0.47368 | 5.1579 | -1.4211 | 5.6316 | 6.5789
EOEM-CUMMINS - REIDSVILLE WTP | 4 | [14 empty] | WF SUBMITTAL [RM<5/10 DAYS] | ON TIME BY ENG
ADVENT HEALTH CARROLLWOOD GARDEN TOWER E | 2 |  |  |  |  | WF SUBMITTAL [RM<5/10 DAYS] | ON TIME BY ENG | [8 empty] | Start Date [Month and Year] | Mar-2026
NEMA 3R LIGHNING ASSY UPDATE | 1
VO#XX ACTUALIZACION PZ4 TAG: 1313-SB-010 | 1 |  |  |  |  | Count of WF | Average of Pre RM Opening Time | Average of Active Time | Average of Overdue Time [Expected-Completion] | Average of Impact Time Post RM | Average of Completion Days Template |  |  |  |  | Count of WF | Average of Pre RM Opening Time | Average of Active Time | Average of Overdue Time [Expected-Completion] | Average of Impact Time Post RM | Average of Completion Days Template
TME27242 | 1 |  |  |  |  | 682 | 18.89 | 10.1496 | 2.6921 | -8.3666 | 7.4575 |  |  |  |  | 39 | 19.4872 | 7.6154 | -0.53846 | -12.8718 | 8.1538
SCHNEIDER ELECTRIC USA INC | 7
ADVENTHEALTH ORLANDO EOB CHILLER NO. 6 | 1
BETTIS LAB CTC | 1
AHO EOB CHILLER NO. 7 | 1
AT&T 105 AUD – 9TH FLOOR SOUTH AON CLOUD | 1
meta f2.0 | 2
TAYLOR DAIRY ROAD WTP | 1
LOUISA COUNTY TECH CAMPUS | 1
meta rsb #80 | 6
switchboard f2.0 | 13
meta rsb Proyecto META SWB | 2
META 2.0 | 2
HF CURREN AWTP MASTER PLAN IMPROVEMENTS | 5
GENENTECH - APOLLO 11 - EQUIPMENT | 5
META - DC FV2.0 - LEB - NW BUILDING (LV) | 1
REPLACE NETWORK SUBSTATIONS 9A,9B,9C,9D | 12
TEMPLE UNIVERSITY LEW KLEIN COLLEGE OF M | 6
BUNDLE FOR KOMAX PZ4 | 1
RAYTHEON - MARLBOROUGH - BUILDING 2 - PH | 1
SPACEX CAPE GIGABAY M1/M2 UNIT SUBSTATIO | 1
AT&T : 51 PEACHTREE CENTER AVE SE ATL | 6
RADY CHILDRENS HOSPITAL - ICU AND CONNEC | 1
AT&T SWITCHGEAR UPGRADE | 4
NESTLÉ SILAO | 6
HARD LABOR CREEK WTP - WALTON COUNTY, GA | 3
NOVO NORDISK - BLDG QC CHEM-RM LAB - CLA | 3
LOUISA COUNTY TECH CAMHUPS | 8
UC BERKELEY HEATHCOCK HALL | 1
W912EF25QA023-ARMY US | 6
NSWC RAM LAB | 1
NORTHROP B410 CHILLER UPGRADE | 5
BUNDLE FOR KOMAX | 1
EOEM - REHLKO - PANAMA CITY - MILLVILLE | 2
NORTH FORK PEACHTREE CREEK STORAGE TANK | 3
FC23-011 3000 KVA SUBSTATION U | 3
GUNDERSEN HEALTH SYSTEM HERITAGE EMERGEN | 1
ADVENT HEALTH CELEBRATION PATIENT TOWER | 2
GEISINGER MEDICAL CENTER SOUTH TOWER | 2
FREIGHTLINER - CLEVELAND, NC. | 1
AMEREN CASTLE BLUFF ENERGY CENTER | 1
OP-250808-15689594 | 13
PROJECT OPAL LLE3 | 4
PROJECT ICY HOT CORE AND SHELL | 10
BF GOODRICH - FORT WAYNE, IN - OUTDOOR | 1
SMUD FAOB | 5
CPS EMC UPGRADE - SAN ANTONIO - ALTERMAN | 1
DUNEDIN WWTP ELECTRICAL SYSTEM UPGRADES | 4
POLK REGIONAL WC SE WELLFIELD AND WATER | 3
UT RED MCCOMBS UNDERGRADUATE SCHOOL OF B | 2 | [10 empty] | Type | (All)
Grand Total | 461 | [10 empty] | Status | X
[12 empty] | Class | (All)
[12 empty] | Start Date [Month and Year] | Mar-2026
Type | (All) | [10 empty] | Job Name | Count of WF | 2
Status | X | [10 empty] | SQD EXPANSION DE SISITEMAS DE ENERGIA | 1
Class | (All) | [10 empty] | EOEM-CUMMINS- HCA ST DAVID'S S AUSTIN | 1
[12 empty] | Grand Total | 2
Job Name | Count of WF | 28
AT&T 1420 BROADWAY STREET LUBBOCK TX | 5
AT&T GREENWOOD - GEAR ORDER | 2
BUNKER HILL WTP | 1
EC1&EC2&EC3 | 1
KAISER SAN JOSE MEDICAL CENTER HOSPITAL | 1
MDACC CSB CLINICAL SERVICES BUILDING | 1
NORTHROP B307 3000 KVA SUBSTATIONS - PAL | 2
SEA NEMA DOC1033717255 EQUIPOS ELECTRICO | 1
TOWER SEMICONDUCTOR - SAN ANTONIO - ALTE | 1
UNITEDHEALTHCARE FOR PARSONS ELECTRIC | 2
GSK MARIETTA B55 | 2
EOEM-CUMMINS - REIDSVILLE WTP | 1
VO#XX ACTUALIZACION PZ4 TAG: 1313-SB-010 | 1
SUNY UPSTATE MEDICAL WEISKOTTEN HALL ADD | 3
ADVENTHEALTH ORLANDO EOB CHILLER NO. 6 | 1
AHO EOB CHILLER NO. 7 | 1
AT&T 105 AUD – 9TH FLOOR SOUTH AON CLOUD | 2
HF CURREN AWTP MASTER PLAN IMPROVEMENTS | 2
REPLACE NETWORK SUBSTATIONS 9A,9B,9C,9D | 2
TEMPLE UNIVERSITY LEW KLEIN COLLEGE OF M | 3
RAYTHEON - MARLBOROUGH - BUILDING 2 - PH | 2
W912EF25QA023-ARMY US | 1
NSWC RAM LAB | 1
ABB BLACKLIST | 1
OP-250808-15689594 | 1
PROJECT OPAL LLE3 | 1
SQD EXPANSION DE SISITEMAS DE ENERGIA | 1
EOEM-CUMMINS- HCA ST DAVID'S S AUSTIN | 1
Grand Total | 44
[12 empty] | Type | (All)
[12 empty] | Status | (Multiple Items)
[12 empty] | Class | (All)
[12 empty] | Start Date [Month and Year] | Mar-2026
[12 empty] | Impacted Post RM | IMPACTED
[12 empty] | WF SUBMITTAL [RM<5/10 DAYS] | ON TIME BY ENG
[12 empty] | Job Name | Count of WF | 0
Job Name | (All) | Job Name | (All)
Type | (All) | Type | (All)
Status | (All) | Status | (All)
Class | (All) | Class | (All)
Start Date [Month and Year] | Count of WF | Start Date [Month and Year] | Average of Overdue Time [Expected-Completion] | Average of Impact Time Post RM | Average of Pre RM Opening Time
Apr-2025 | 38 | Apr-2025 | -0.10526 | -0.76316 | 10.2105
Aug-2025 | 61 | Aug-2025 | 1.7541 | -7.1311 | 16.7213
Dec-2025 | 78 | Dec-2025 | 3.1154 | 1.3846 | 10
Feb-2026 | 92 | Feb-2026 | 2.7935 | -1.163 | 10.1848
Jan-2026 | 54 | Jan-2026 | 2.0185 | -2.7778 | 9.9815
Jul-2025 | 50 | Jul-2025 | 2.26 | -9.86 | 19.6
Jun-2025 | 49 | Jun-2025 | 4.5102 | -2.7551 | 13.5306
Mar-2026 | 58 | Mar-2026 | -0.82759 | -6.8103 | 12.9483
May-2025 | 31 | May-2025 | 1.2258 | -0.6129 | 9.3871
Nov-2025 | 77 | Nov-2025 | 2.2468 | -1.8701 | 14.5714
Oct-2025 | 109 | Oct-2025 | 1.4954 | -2.3761 | 11.5413
Sep-2025 | 99 | Sep-2025 | 4.0909 | -3.9192 | 15.5556
Grand Total | 796

## GSC (hidden)
GLOBAL STATS CALCULATIONS [PZ4/QED2/QED6]
AVG Active Time | AVG Overdue Time post template | AVG Opening Time Pre RM | %OnTime WF | %Late WF | %+15DAYS LATE | %WF Closure by Eng Errors | # Overdue Projects impacted by correct WF submittal | #Projects Impacted by incorrect WF | #Projects impacted by cancelation on time | Top Cancellation offender | Active WF
9.6624 | 5.8822 | 13.1893 | 45.44% | 52.22% | 2.336% | 5.14% | 103 | 28 | 26 | ACTIVE US23 | 45
AVG Active Time | AVG Overdue Time post template | AVG Opening Time Pre RM | %OnTime WF | %Late WF | %+15DAYS LATE | %WF Closure by Eng Errors | # Overdue Projects impacted by correct WF submittal | #Projects Impacted by incorrect WF | #Projects impacted by cancelation on time | RM Date impacted by late WFs (NOT ENG) | Top Cancellation offender | Active WF
8.76 | 5.5385 | 11.2533 | 77.59% | 22.41% | 0% | 1.333% | 7 | 2 | 2 | 0 | ACTIVE US23 | 45

## Database PZ4 + SWBD
Product | Order Number | Item | Sales Number | Job Name | RM | RE | AE | MD | WF | Class | Type | Special Paint | CPD | Pre RM Opening Time | Start date | Due date | Completion Date | Competion Date Content | Start Date [Month and Year] | Old vs New Order Lead Time WF dead line | Completion Days Template | Active Time | Overdue Time [Expected-Completion] | Classification not considering 15+ days | Classification [Completion-Due Date] | WF SUBMITTAL [RM<5/10 DAYS] | Reason For Late WF Submital by Eng | Status | Impact Time Post RM | Impacted Post RM | Re-Worked WF Active Time | Cancelation Cause | Urgent Closure | Classification [Completion-RM] | Task responsible | Task Number | Completion Forecast | % Of completion | Comments
PZ4 | 0050535728 | 000130 | 0050535728-000130 | AO SMITH MCBEE SC | 4570200% |  | AOB | OAL | WF1593968 | Elec | MAKE | ANSI 49 | 4582400% | 90 | 4557900% | 4558600% | 4560000% | FALSE | Oct-2024 | 5 | 6 | 16 | 10 | LATE | LATE | ON TIME BY ENG |  | C | -73 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4558907% | 100%
PZ4 | 0050754152 | 000090 | 0050754152-000090 | TOWER SEMICONDUCTOR - SAN ANTONIO - ALTE | 4570500% |  | JTV | LDT | WF1634065 | Mech | MAKE | ANSI 49 | 4592200% | 21 | 4567700% | 4568600% | 4569300% | FALSE | Jan-2025 | 5 | 8 | 12 | 4 | LATE | LATE | ON TIME BY ENG |  | C | -9 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4568907% | 100%
PZ4 | 0050754152 | 000090 | 0050754152-000090 | TOWER SEMICONDUCTOR - SAN ANTONIO - ALTE | 4570500% |  | JTV | LDT | WF1634066 | Mech | MAKE | ANSI 49 | 4592200% | 21 | 4567700% | 4568600% | 4569300% | FALSE | Jan-2025 | 5 | 8 | 12 | 4 | LATE | LATE | ON TIME BY ENG |  | C | -9 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4568907% | 100%
PZ4 | 0050754152 | 000090 | 0050754152-000090 | TOWER SEMICONDUCTOR - SAN ANTONIO - ALTE | 4570500% |  | JTV | LDT | WF1634071 | Mech | MAKE | ANSI 49 | 4592200% | 21 | 4567700% | 4568600% | 4569300% | FALSE | Jan-2025 | 5 | 8 | 12 | 4 | LATE | LATE | ON TIME BY ENG |  | C | -9 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4568907% | 100%
PZ4 | 0050529183 | 000460 | 0050529183-000460 | USSF ANTENNA FACILITY PROJECT | 4571300% |  | AOB | DPM | WF1634013 | Elec | BUY | MISAWA | 4591500% | 27 | 4567700% | 4568700% | 4572700% | FALSE | Jan-2025 | 5 | 9 | 36 | 27 | LATE | SUPER LATE | ON TIME BY ENG |  | C | 11 | IMPACTED |  |  | Closed | LATE | NA | 17 | 4568742% | 100%
PZ4 | 0050754152 | 000090 | 0050754152-000090 | TOWER SEMICONDUCTOR - SAN ANTONIO - ALTE | 4570500% |  | JTV | LDT | WF1634544 | Mech | MAKE | ANSI 49 | 4592200% | 20 | 4567800% | 4568500% | 4569300% | FALSE | Jan-2025 | 5 | 6 | 11 | 5 | LATE | LATE | ON TIME BY ENG |  | C | -9 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4568807% | 100%
PZ4 | 0050754152 | 000090 | 0050754152-000090 | TOWER SEMICONDUCTOR - SAN ANTONIO - ALTE | 4570500% |  | JTV | LDT | WF1634581 | Mech | MAKE | ANSI 49 | 4592200% | 20 | 4567800% | 4568500% | 4568800% | FALSE | Jan-2025 | 5 | 6 | 9 | 3 | LATE | LATE | ON TIME BY ENG |  | C | -11 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4568807% | 100%
PZ4 | 0050754152 | 000090 | 0050754152-000090 | TOWER SEMICONDUCTOR - SAN ANTONIO - ALTE | 4570500% |  | JTV | LDT | WF1634504 | Mech | BUY | ANSI 49 | 4592200% | 20 | 4567800% | 4568800% | 4568600% | FALSE | Jan-2025 | 5 | 9 | 7 | -2 | ON TIME | ON TIME | ON TIME BY ENG |  | C | -13 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 17 | 4568842% | 100%
PZ4 | 0050754152 | 000090 | 0050754152-000090 | TOWER SEMICONDUCTOR - SAN ANTONIO - ALTE | 4570500% |  | JTV | LDT | WF1635286 | Elec | BUY | ANSI 49 | 4592200% | 19 | 4567900% | 4569100% | 4569300% | FALSE | Jan-2025 | 5 | 9 | 10 | 1 | LATE | LATE | ON TIME BY ENG |  | C | -9 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 17 | 4569142% | 100%
PZ4 | 0051035283 | 0000010&0000050 | 0051035283-0000010&0000050 | SWITCHGEAR UPGRADE | 4570900% |  | LGS | OAL | WF1645448 | Elec | MAKE | ANSI 49 | 4583500% | 8 | 4570000% | 4570800% | 4572000% | FALSE | Feb-2025 | 5 | 7 | 15 | 8 | LATE | LATE | ON TIME BY ENG |  | C | 8 | IMPACTED |  |  | Closed | LATE | NA | 18 | 4571107% | 100%
PZ4 | 0051035283 | 0000010&0000050 | 0051035283-0000010&0000050 | SWITCHGEAR UPGRADE | 4570900% |  | LGS | OAL | WF1647369 | Elec | MAKE | ANSI 49 | 4583500% | 5 | 4570500% | 4571200% | 4572000% | FALSE | Feb-2025 | 5 | 6 | 12 | 6 | LATE | LATE | ON TIME BY ENG |  | C | 8 | IMPACTED |  |  | Closed | LATE | NA | 18 | 4571507% | 100%
PZ4 | 0050255139 | 000780 | 0050255139-000780 | CHARLOTTE WATER-MT. HOLLY PS & STOWE - | 4573000% |  | KYC | VL | WF1647350 | Elec | MAKE | ANSI 49 | 4596000% | 20 | 4570500% | 4571200% | 4572000% | FALSE | Feb-2025 | 5 | 6 | 12 | 6 | LATE | LATE | ON TIME BY ENG |  | C | -9 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4571507% | 100%
PZ4 | 0051035283 | 0000010&0000050 | 0051035283-0000010&0000050 | SWITCHGEAR UPGRADE | 4570900% |  | LGS | OAL | WF1648774 | Elec | MAKE | ANSI 49 | 4583500% | 3 | 4570700% | 4571400% | 4571500% | FALSE | Feb-2025 | 5 | 6 | 7 | 1 | LATE | LATE | LATE BY ENG |  | C | 5 | IMPACTED |  |  | Closed | LATE | NA | 18 | 4571707% | 100%
PZ4 | 0050206201 | 000160 | 0050206201-000160 | AT&T GREENWOOD - GEAR ORDER | 4576900% |  | JAM | ADL | WF1648985 | Elec | MAKE | ANSI 49 | 4586800% | 45 | 4570700% | 4571500% | 4571500% | FALSE | Feb-2025 | 5 | 7 | 7 | 0 | ON TIME | ON TIME | ON TIME BY ENG |  | C | -36 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4571807% | 100%
PZ4 | 0050255139 | 000780 | 0050255139-000780 | CHARLOTTE WATER-MT. HOLLY PS & STOWE - | 4573000% |  | KYC | VL | WF1650970 | Mech | MAKE | ANSI 49 | 4596000% | 15 | 4571200% | 4571900% | 4572700% | FALSE | Feb-2025 | 5 | 6 | 12 | 6 | LATE | LATE | ON TIME BY ENG |  | C | -4 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4572207% | 100%
PZ4 | 0050206201 | 000180 | 0050206201-000180 | AT&T GREENWOOD - GEAR ORDER | 4576200% |  | MGL | KGF | WF1650858 | Elec | MAKE | ANSI 49 | 4588800% | 37 | 4571200% | 4571900% | 4571500% | FALSE | Feb-2025 | 5 | 6 | 4 | -2 | ON TIME | ON TIME | ON TIME BY ENG |  | C | -33 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4572207% | 100%
PZ4 | 0050206201 | 000180 | 0050206201-000180 | AT&T GREENWOOD - GEAR ORDER | 4576200% |  | MGL | KGF | WF1650861 | Elec | MAKE | ANSI 49 | 4588800% | 37 | 4571200% | 4571900% | 4572700% | FALSE | Feb-2025 | 5 | 6 | 12 | 6 | LATE | LATE | ON TIME BY ENG |  | C | -25 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4572207% | 100%
PZ4 | 0050206201 | 000180 | 0050206201-000180 | AT&T GREENWOOD - GEAR ORDER | 4576200% |  | MGL | KGF | WF1650863 | Elec | MAKE | ANSI 49 | 4588800% | 37 | 4571200% | 4571900% | 4572700% | FALSE | Feb-2025 | 5 | 6 | 12 | 6 | LATE | LATE | ON TIME BY ENG |  | C | -25 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4572207% | 100%
PZ4 | 0050206201 | 000180 | 0050206201-000180 | AT&T GREENWOOD - GEAR ORDER | 4576200% |  | MGL | KGF | WF1651072 | Elec | MAKE | ANSI 49 | 4588800% | 37 | 4571200% | 4572000% | 4572000% | FALSE | Feb-2025 | 5 | 7 | 7 | 0 | ON TIME | ON TIME | ON TIME BY ENG |  | C | -30 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4572307% | 100%
PZ4 | 0050206201 | 000180 | 0050206201-000180 | AT&T GREENWOOD - GEAR ORDER | 4576200% |  | MGL | KGF | WF1650856 | Elec | MAKE | ANSI 49 | 4588800% | 37 | 4571200% | 4572200% | 4571200% | FALSE | Feb-2025 | 5 | 9 | 1 | -8 | ON TIME | ON TIME | ON TIME BY ENG |  | X | -36 | NOT IMPACTED |  |  | Cancelled | ON TIME | NA | 0 | 4572507% | 0%
PZ4 | 0050206201 | 000180 | 0050206201-000180 | AT&T GREENWOOD - GEAR ORDER | 4576200% |  | MGL | KGF | WF1651638 | Elec | BUY | ANSI 49 | 4588800% | 36 | 4571300% | 4572300% | 4572200% | FALSE | Feb-2025 | 5 | 9 | 8 | -1 | ON TIME | ON TIME | ON TIME BY ENG |  | C | -28 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 17 | 4572342% | 100%
PZ4 | 0051035283 | 0000010&0000050 | 0051035283-0000010&0000050 | SWITCHGEAR UPGRADE | 4570900% |  | LGS | OAL | WF1652523 | Elec | MAKE | ANSI 49 | 4583500% | -4 | 4571400% | 4572200% | 4572200% | FALSE | Feb-2025 | 5 | 7 | 7 | 0 | ON TIME | ON TIME | LATE BY ENG |  | C | 10 | IMPACTED |  |  | Closed | LATE | NA | 18 | 4572507% | 100%
PZ4 | 0050255139 | 000780 | 0050255139-000780 | CHARLOTTE WATER-MT. HOLLY PS & STOWE - | 4573000% |  | KYC | VL | WF1652400 | Mech | MAKE | ANSI 49 | 4596000% | 13 | 4571400% | 4572100% | 4572200% | FALSE | Feb-2025 | 5 | 6 | 7 | 1 | LATE | LATE | ON TIME BY ENG |  | C | -7 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4572407% | 100%
PZ4 | 0050959328 | 000010 | 0050959328-000010 | NSBSL SUBSTATION REPLACEMENT | 4572600% |  | RAS | OAL | WF1654489 | Elec | BUY | ANSI 49 | 4583500% | 6 | 4571900% | 4571900% | 4572700% | FALSE | Mar-2025 | 5 | 1 | 7 | 6 | LATE | LATE | ON TIME BY ENG |  | C | 2 | IMPACTED |  |  | Closed | LATE | NA | 17 | 4571942% | 100%
PZ4 | 0050959328 | 000010 | 0050959328-000010 | NSBSL SUBSTATION REPLACEMENT | 4572600% |  | RAS | OAL | WF1654647 | Elec | MAKE | ANSI 49 | 4583500% | 6 | 4571900% | 4572700% | 4573500% | FALSE | Mar-2025 | 5 | 7 | 12 | 5 | LATE | LATE | ON TIME BY ENG |  | C | 7 | IMPACTED |  |  | Closed | LATE | NA | 18 | 4573007% | 100%
PZ4 | 0050255139 | 000780 | 0050255139-000780 | CHARLOTTE WATER-MT. HOLLY PS & STOWE - | 4573000% |  | KYC | VL | WF1654591 | Mech | MAKE | ANSI 49 | 4596000% | 10 | 4571900% | 4572600% | 4572800% | FALSE | Mar-2025 | 5 | 6 | 8 | 2 | LATE | LATE | ON TIME BY ENG |  | C | -3 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4572907% | 100%
PZ4 | 0050255139 | 000780 | 0050255139-000780 | CHARLOTTE WATER-MT. HOLLY PS & STOWE - | 4573000% |  | KYC | VL | WF1654659 | Mech | MAKE | ANSI 49 | 4596000% | 10 | 4571900% | 4572700% | 4572800% | FALSE | Mar-2025 | 5 | 7 | 8 | 1 | LATE | LATE | ON TIME BY ENG |  | C | -3 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4573007% | 100%
PZ4 | 0050780333 | 000110 | 0050780333-000110 | UCSF PRAB 60CD MAR 2024 LONG LEAD SWITCH | 4573000% |  | LMB | ADL | WF1654754 | Mech | MAKE | ANSI 61 | 4589600% | 10 | 4571900% | 4572800% | 4574000% | FALSE | Mar-2025 | 5 | 8 | 15 | 7 | LATE | LATE | ON TIME BY ENG |  | C | 6 | IMPACTED |  |  | Closed | LATE | NA | 18 | 4573107% | 100%
PZ4 | 0050780333 | 000110 | 0050780333-000110 | UCSF PRAB 60CD MAR 2024 LONG LEAD SWITCH | 4573000% |  | LMB | ADL | WF1654757 | Mech | MAKE | ANSI 61 | 4589600% | 10 | 4571900% | 4572800% | 4573600% | FALSE | Mar-2025 | 5 | 8 | 13 | 5 | LATE | LATE | ON TIME BY ENG |  | C | 4 | IMPACTED |  |  | Closed | LATE | NA | 18 | 4573107% | 100%
PZ4 | 0050780333 | 000110 | 0050780333-000110 | UCSF PRAB 60CD MAR 2024 LONG LEAD SWITCH | 4573000% |  | LMB | ADL | WF1654786 | Mech | MAKE | ANSI 61 | 4589600% | 10 | 4571900% | 4572800% | 4574000% | FALSE | Mar-2025 | 5 | 8 | 15 | 7 | LATE | LATE | ON TIME BY ENG |  | C | 6 | IMPACTED |  |  | Closed | LATE | NA | 18 | 4573107% | 100%
PZ4 | 0050780333 | 000110 | 0050780333-000110 | UCSF PRAB 60CD MAR 2024 LONG LEAD SWITCH | 4573000% |  | LMB | ADL | WF1654753 | Mech | BUY | ANSI 61 | 4589600% | 10 | 4571900% | 4573300% | 4572900% | FALSE | Mar-2025 | 5 | 11 | 9 | -2 | ON TIME | ON TIME | ON TIME BY ENG |  | C | -2 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 17 | 4573342% | 100%
PZ4 | 0050255139 | 000780 | 0050255139-000780 | CHARLOTTE WATER-MT. HOLLY PS & STOWE - | 4573000% |  | KYC | VL | WF1655177 | Mech | MAKE | ANSI 49 | 4596000% | 9 | 4572000% | 4572700% | 4573500% | FALSE | Mar-2025 | 5 | 6 | 11 | 5 | LATE | LATE | ON TIME BY ENG |  | C | 3 | IMPACTED |  |  | Closed | LATE | NA | 18 | 4573007% | 100%
PZ4 | 0050255139 | 000780 | 0050255139-000780 | CHARLOTTE WATER-MT. HOLLY PS & STOWE - | 4573000% |  | KYC | VL | WF1655377 | Mech | BUY | ANSI 49 | 4596000% | 9 | 4572000% | 4573000% | 4572900% | FALSE | Mar-2025 | 5 | 9 | 8 | -1 | ON TIME | ON TIME | ON TIME BY ENG |  | C | -2 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 17 | 4573042% | 100%
PZ4 | 0050206201 | 000180 | 0050206201-000180 | AT&T GREENWOOD - GEAR ORDER | 4576200% |  | MGL | KGF | WF1655339 | Elec | MAKE | ANSI 49 | 4588800% | 31 | 4572000% | 4572800% | 4574000% | FALSE | Mar-2025 | 5 | 7 | 14 | 7 | LATE | LATE | ON TIME BY ENG |  | C | -17 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4573107% | 100%
PZ4 | 0050206201 | 000180 | 0050206201-000180 | AT&T GREENWOOD - GEAR ORDER | 4576200% |  | MGL | KGF | WF1655340 | Elec | MAKE | ANSI 49 | 4588800% | 31 | 4572000% | 4572800% | 4572800% | FALSE | Mar-2025 | 5 | 7 | 7 | 0 | ON TIME | ON TIME | ON TIME BY ENG |  | C | -24 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4573107% | 100%
PZ4 | 0050780333 | 000110 | 0050780333-000110 | UCSF PRAB 60CD MAR 2024 LONG LEAD SWITCH | 4573000% |  | LMB | ADL | WF1656229 | Mech | MAKE | ANSI 61 | 4589600% | 8 | 4572100% | 4573000% | 4574000% | FALSE | Mar-2025 | 5 | 8 | 13 | 5 | LATE | LATE | ON TIME BY ENG |  | C | 6 | IMPACTED |  |  | Closed | LATE | NA | 18 | 4573307% | 100%
PZ4 | 0050780333 | 000110 | 0050780333-000110 | UCSF PRAB 60CD MAR 2024 LONG LEAD SWITCH | 4573000% |  | LMB | ADL | WF1656216 | Mech | BUY | ANSI 61 | 4589600% | 8 | 4572100% | 4573500% | 4572900% | FALSE | Mar-2025 | 5 | 11 | 7 | -4 | ON TIME | ON TIME | ON TIME BY ENG |  | C | -2 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 17 | 4573542% | 100%
PZ4 | 0050206201 | 000160 | 0050206201-000160 | AT&T GREENWOOD - GEAR ORDER | 4576900% |  | JAM | ADL | WF1656091 | Elec | MAKE | ANSI 49 | 4586800% | 35 | 4572100% | 4572900% | 4573500% | FALSE | Mar-2025 | 5 | 7 | 10 | 3 | LATE | LATE | ON TIME BY ENG |  | C | -23 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4573207% | 100%
PZ4 | 0050746660 | 000030 | 0050746660-000030 | PINELLAS COUNTY DUNN WWTP _ PALM HARBOR | 4573000% |  | JTV | KGF | WF1656722 | Mech | MAKE | ANSI 49 | 4586900% | 7 | 4572200% | 4572900% | 4574100% | FALSE | Mar-2025 | 5 | 6 | 13 | 7 | LATE | LATE | ON TIME BY ENG |  | C | 7 | IMPACTED |  |  | Closed | LATE | NA | 18 | 4573207% | 100%
PZ4 | 0050746660 | 000030 | 0050746660-000030 | PINELLAS COUNTY DUNN WWTP _ PALM HARBOR | 4573000% |  | JTV | KGF | WF1656778 | Mech | MAKE | ANSI 49 | 4586900% | 7 | 4572200% | 4572900% | 4573500% | FALSE | Mar-2025 | 5 | 6 | 9 | 3 | LATE | LATE | ON TIME BY ENG |  | C | 3 | IMPACTED |  |  | Closed | LATE | NA | 18 | 4573207% | 100%
PZ4 | 0050746660 | 000030 | 0050746660-000030 | PINELLAS COUNTY DUNN WWTP _ PALM HARBOR | 4573000% |  | JTV | KGF | WF1656725 | Mech | BUY | ANSI 49 | 4586900% | 7 | 4572200% | 4573400% | 4574100% | FALSE | Mar-2025 | 5 | 9 | 13 | 4 | LATE | LATE | ON TIME BY ENG |  | C | 7 | IMPACTED |  |  | Closed | LATE | NA | 17 | 4573442% | 100%
PZ4 | 0050746660 | 000030 | 0050746660-000030 | PINELLAS COUNTY DUNN WWTP _ PALM HARBOR | 4573000% |  | JTV | KGF | WF1656782 | Mech | BUY | ANSI 49 | 4586900% | 7 | 4572200% | 4573400% | 4573500% | FALSE | Mar-2025 | 5 | 9 | 9 | 0 | ON TIME | ON TIME | ON TIME BY ENG |  | C | 3 | IMPACTED |  |  | Closed | LATE | NA | 17 | 4573442% | 100%
PZ4 | 0050746660 | 000030 | 0050746660-000030 | PINELLAS COUNTY DUNN WWTP _ PALM HARBOR | 4573000% |  | JTV | KGF | WF1657486 | Mech | MAKE | ANSI 49 | 4586900% | 6 | 4572300% | 4573300% | 4572900% | FALSE | Mar-2025 | 5 | 7 | 5 | -2 | ON TIME | ON TIME | ON TIME BY ENG |  | C | -2 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4573607% | 100%
PZ4 | 0050746660 | 000030 | 0050746660-000030 | PINELLAS COUNTY DUNN WWTP _ PALM HARBOR | 4573000% |  | JTV | KGF | WF1657370 | Mech | BUY | ANSI 49 | 4586900% | 6 | 4572300% | 4573500% | 4573500% | FALSE | Mar-2025 | 5 | 9 | 8 | -1 | ON TIME | ON TIME | ON TIME BY ENG |  | C | 3 | IMPACTED |  |  | Closed | LATE | NA | 17 | 4573542% | 100%
PZ4 | 0050206201 | 000180 | 0050206201-000180 | AT&T GREENWOOD - GEAR ORDER | 4576200% |  | MGL | KGF | WF1657391 | Elec | MAKE | ANSI 49 | 4588800% | 28 | 4572300% | 4573000% | 4573700% | FALSE | Mar-2025 | 5 | 6 | 10 | 4 | LATE | LATE | ON TIME BY ENG |  | C | -18 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4573307% | 100%
PZ4 | 0050206201 | 000180 | 0050206201-000180 | AT&T GREENWOOD - GEAR ORDER | 4576200% |  | MGL | KGF | WF1658163 | Elec | MAKE | ANSI 49 | 4588800% | 27 | 4572600% | 4573600% | 4573500% | FALSE | Mar-2025 | 5 | 9 | 7 | -2 | ON TIME | ON TIME | ON TIME BY ENG |  | C | -20 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4573907% | 100%
PZ4 | 0050746660 | 000030 | 0050746660-000030 | PINELLAS COUNTY DUNN WWTP _ PALM HARBOR | 4573000% |  | JTV | KGF | WF1659119 | Elec | MAKE | ANSI 49 | 4586900% | 4 | 4572700% | 4573600% | 4574000% | FALSE | Mar-2025 | 5 | 8 | 9 | 1 | LATE | LATE | LATE BY ENG |  | C | 6 | IMPACTED |  |  | Closed | LATE | NA | 18 | 4573907% | 100%
PZ4 | 0050206201 | 000160 | 0050206201-000160 | AT&T GREENWOOD - GEAR ORDER | 4576900% |  | JAM | ADL | WF1658800 | Elec | BUY | ANSI 49 | 4586800% | 31 | 4572700% | 4574000% | 4572700% | FALSE | Mar-2025 | 5 | 10 | 1 | -9 | ON TIME | ON TIME | ON TIME BY ENG |  | X | -28 | NOT IMPACTED |  |  | Cancelled | ON TIME | NA | 0 | 4574042% | 0%
PZ4 | 0051150882 | 000010 | 0051150882-000010 | IRON MOUNTAIN RM#6 | 4574400% |  | CFC | OAL | WF1660921 | Mech | MAKE | ANSI 49 | 4586900% | 11 | 4573000% | 4574000% | 4574000% | FALSE | Mar-2025 | 5 | 7 | 6 | -1 | ON TIME | ON TIME | ON TIME BY ENG |  | C | -5 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4574307% | 100%
PZ4 | 0051150882 | 000010 | 0051150882-000010 | IRON MOUNTAIN RM#6 | 4574400% |  | CFC | OAL | WF1660933 | Mech | MAKE | ANSI 49 | 4586900% | 11 | 4573000% | 4574000% | 4574200% | FALSE | Mar-2025 | 5 | 7 | 8 | 1 | LATE | LATE | ON TIME BY ENG |  | C | -3 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4574307% | 100%
PZ4 | 0051150882 | 000010 | 0051150882-000010 | IRON MOUNTAIN RM#6 | 4574400% |  | CFC | OAL | WF1661019 | Mech | MAKE | ANSI 49 | 4586900% | 11 | 4573000% | 4574100% | 4574200% | FALSE | Mar-2025 | 5 | 8 | 8 | 0 | ON TIME | ON TIME | ON TIME BY ENG |  | C | -3 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4574407% | 100%
PZ4 | 0051150882 | 000010 | 0051150882-000010 | IRON MOUNTAIN RM#6 | 4574400% |  | CFC | OAL | WF1660919 | Mech | BUY | ANSI 49 | 4586900% | 11 | 4573000% | 4574300% | 4574100% | FALSE | Mar-2025 | 5 | 10 | 7 | -3 | ON TIME | ON TIME | ON TIME BY ENG |  | C | -4 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 17 | 4574342% | 100%
PZ4 | 0050206201 | 000160 | 0050206201-000160 | AT&T GREENWOOD - GEAR ORDER | 4576900% |  | JAM | ADL | WF1660918 | Elec | MAKE | ANSI 49 | 4586800% | 28 | 4573000% | 4574000% | 4574000% | FALSE | Mar-2025 | 5 | 7 | 6 | -1 | ON TIME | ON TIME | ON TIME BY ENG |  | C | -20 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4574307% | 100%
PZ4 | 0050746660 | 000030 | 0050746660-000030 | PINELLAS COUNTY DUNN WWTP _ PALM HARBOR | 4573000% |  | JTV | KGF | WF1663892 | Mech | MAKE | ANSI 49 | 4586900% | -5 | 4573600% | 4574300% | 4574300% | FALSE | Mar-2025 | 5 | 6 | 6 | 0 | ON TIME | ON TIME | LATE BY ENG |  | C | 9 | IMPACTED |  |  | Closed | LATE | NA | 18 | 4574607% | 100%
PZ4 | 0050780333 | 000110 | 0050780333-000110 | UCSF PRAB 60CD MAR 2024 LONG LEAD SWITCH | 4573000% |  | LMB | ADL | WF1665200 | Mech | MAKE | ANSI 61 | 4589600% | -7 | 4574000% | 4574700% | 4574400% | FALSE | Mar-2025 | 5 | 6 | 5 | -1 | ON TIME | ON TIME | LATE BY ENG |  | C | 10 | IMPACTED |  |  | Closed | LATE | NA | 18 | 4575007% | 100%
PZ4 | 0050780333 | 000110 | 0050780333-000110 | UCSF PRAB 60CD MAR 2024 LONG LEAD SWITCH | 4573000% |  | LMB | ADL | WF1665204 | Mech | MAKE | ANSI 61 | 4589600% | -7 | 4574000% | 4574700% | 4574400% | FALSE | Mar-2025 | 5 | 6 | 5 | -1 | ON TIME | ON TIME | LATE BY ENG |  | C | 10 | IMPACTED |  |  | Closed | LATE | NA | 18 | 4575007% | 100%
PZ4 | 0050206201 | 000170 | 0050206201-000170 | AT&T GREENWOOD - GEAR ORDER | 4576200% |  | DR | OAL | WF1667259 | Mech | MAKE | ANSI 49 | 4588800% | 14 | 4574300% | 4575000% | 4575900% | FALSE | Mar-2025 | 5 | 6 | 12 | 6 | LATE | LATE | ON TIME BY ENG |  | C | -2 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4575307% | 100%
PZ4 | 0050206201 | 000180 | 0050206201-000180 | AT&T GREENWOOD - GEAR ORDER | 4576200% |  | MGL | KGF | WF1668522 | Mech | MAKE | ANSI 49 | 4588800% | 12 | 4574700% | 4575500% | 4575900% | FALSE | Mar-2025 | 5 | 7 | 10 | 3 | LATE | LATE | ON TIME BY ENG |  | C | -2 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4575807% | 100%
PZ4 | 0050206201 | 000180 | 0050206201-000180 | AT&T GREENWOOD - GEAR ORDER | 4576200% |  | MGL | KGF | WF1668543 | Mech | MAKE | ANSI 49 | 4588800% | 12 | 4574700% | 4575500% | 4575900% | FALSE | Mar-2025 | 5 | 7 | 10 | 3 | LATE | LATE | ON TIME BY ENG |  | C | -2 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4575807% | 100%
PZ4 | 0050206201 | 000180 | 0050206201-000180 | AT&T GREENWOOD - GEAR ORDER | 4576200% |  | MGL | KGF | WF1668571 | Mech | BUY | ANSI 49 | 4588800% | 12 | 4574700% | 4575700% | 4575800% | FALSE | Mar-2025 | 5 | 9 | 10 | 1 | LATE | LATE | ON TIME BY ENG |  | C | -3 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 17 | 4575742% | 100%
PZ4 | 0050206201 | 000180 | 0050206201-000180 | AT&T GREENWOOD - GEAR ORDER | 4576200% |  | MGL | KGF | WF1669049 | Mech | MAKE | ANSI 49 | 4588800% | 11 | 4574800% | 4575500% | 4575900% | FALSE | Apr-2025 | 5 | 6 | 9 | 3 | LATE | LATE | ON TIME BY ENG |  | C | -2 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4575807% | 100%
PZ4 | 0050206201 | 000180 | 0050206201-000180 | AT&T GREENWOOD - GEAR ORDER | 4576200% |  | MGL | KGF | WF1669064 | Mech | MAKE | ANSI 49 | 4588800% | 11 | 4574800% | 4575500% | 4575100% | FALSE | Apr-2025 | 5 | 6 | 4 | -2 | ON TIME | ON TIME | ON TIME BY ENG |  | C | -8 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4575807% | 100%
PZ4 | 0050206201 | 000180 | 0050206201-000180 | AT&T GREENWOOD - GEAR ORDER | 4576200% |  | MGL | KGF | WF1669148 | Mech | MAKE | ANSI 49 | 4588800% | 11 | 4574800% | 4575600% | 4576100% | FALSE | Apr-2025 | 5 | 7 | 10 | 3 | LATE | LATE | ON TIME BY ENG |  | C | -2 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4575907% | 100%
PZ4 | 0050206201 | 000180 | 0050206201-000180 | AT&T GREENWOOD - GEAR ORDER | 4576200% |  | MGL | KGF | WF1669179 | Mech | MAKE | ANSI 49 | 4588800% | 11 | 4574800% | 4575700% | 4575400% | FALSE | Apr-2025 | 5 | 8 | 5 | -3 | ON TIME | ON TIME | ON TIME BY ENG |  | C | -7 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4576007% | 100%
PZ4 | 0050206201 | 000180 | 0050206201-000180 | AT&T GREENWOOD - GEAR ORDER | 4576200% |  | MGL | KGF | WF1669735 | Mech | MAKE | ANSI 49 | 4588800% | 10 | 4574900% | 4575600% | 4575600% | FALSE | Apr-2025 | 5 | 6 | 6 | 0 | ON TIME | ON TIME | ON TIME BY ENG |  | C | -5 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4575907% | 100%
PZ4 | 0050206201 | 000180 | 0050206201-000180 | AT&T GREENWOOD - GEAR ORDER | 4576200% |  | MGL | KGF | WF1670537 | Mech | BUY | ANSI 49 | 4588800% | 9 | 4575000% | 4576200% | 4576100% | FALSE | Apr-2025 | 5 | 9 | 8 | -1 | ON TIME | ON TIME | ON TIME BY ENG |  | C | -2 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 17 | 4576242% | 100%
PZ4 | 0051199249 | 000050 | 0051199249-000050 | INTEL SOW707 FEDERAL FOUNDRY OSM | 4576500% |  | ADT | LDT | WF1670586 | Mech | MAKE | ANSI 49 | 4586800% | 12 | 4575000% | 4575800% | 4575600% | FALSE | Apr-2025 | 5 | 7 | 5 | -2 | ON TIME | ON TIME | ON TIME BY ENG |  | C | -6 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4576107% | 100%
PZ4 | 0051199249 | 000040 | 0051199249-000040 | INTEL SOW707 FEDERAL FOUNDRY OSM | 4576800% |  | OAC | DPM | WF1670547 | Mech | MAKE | ANSI 49 | 4586900% | 13 | 4575000% | 4575800% | 4575700% | FALSE | Apr-2025 | 5 | 7 | 6 | -1 | ON TIME | ON TIME | ON TIME BY ENG |  | C | -6 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4576107% | 100%
PZ4 | 0050206201 | 000160 | 0050206201-000160 | AT&T GREENWOOD - GEAR ORDER | 4576900% |  | JAM | ADL | WF1671148 | Elec | BUY | ANSI 49 | 4586800% | 13 | 4575100% | 4576300% | 4576300% | FALSE | Apr-2025 | 5 | 9 | 9 | 0 | ON TIME | ON TIME | ON TIME BY ENG |  | C | -3 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 17 | 4576342% | 100%
PZ4 | 0051199249 | 000050 | 0051199249-000050 | INTEL SOW707 FEDERAL FOUNDRY OSM | 4576500% |  | ADT | LDT | WF1672131 | Mech | MAKE | ANSI 49 | 4586800% | 10 | 4575400% | 4576300% | 4576600% | FALSE | Apr-2025 | 5 | 8 | 8 | 0 | ON TIME | ON TIME | ON TIME BY ENG |  | C | 0 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4576607% | 100%
PZ4 | 0051199249 | 000040 | 0051199249-000040 | INTEL SOW707 FEDERAL FOUNDRY OSM | 4576800% |  | OAC | DPM | WF1672069 | Mech | MAKE | ANSI 49 | 4586900% | 11 | 4575400% | 4576200% | 4576400% | FALSE | Apr-2025 | 5 | 7 | 8 | 1 | LATE | LATE | ON TIME BY ENG |  | C | -1 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4576507% | 100%
PZ4 | 0051199249 | 000040 | 0051199249-000040 | INTEL SOW707 FEDERAL FOUNDRY OSM | 4576800% |  | OAC | DPM | WF1672080 | Mech | MAKE | ANSI 49 | 4586900% | 11 | 4575400% | 4576200% | 4575800% | FALSE | Apr-2025 | 5 | 7 | 5 | -2 | ON TIME | ON TIME | ON TIME BY ENG |  | C | -5 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4576507% | 100%
PZ4 | 0051199249 | 000040 | 0051199249-000040 | INTEL SOW707 FEDERAL FOUNDRY OSM | 4576800% |  | OAC | DPM | WF1672053 | Mech | BUY | ANSI 49 | 4586900% | 11 | 4575400% | 4576400% | 4576400% | FALSE | Apr-2025 | 5 | 9 | 8 | -1 | ON TIME | ON TIME | ON TIME BY ENG |  | C | -1 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 17 | 4576442% | 100%
PZ4 | 0051199249 | 000050 | 0051199249-000050 | INTEL SOW707 FEDERAL FOUNDRY OSM | 4576500% |  | ADT | LDT | WF1672746 | Mech | MAKE | ANSI 49 | 4586800% | 9 | 4575500% | 4576300% | 4576600% | FALSE | Apr-2025 | 5 | 7 | 7 | 0 | ON TIME | ON TIME | ON TIME BY ENG |  | C | 0 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4576607% | 100%
PZ4 | 0051199249 | 000050 | 0051199249-000050 | INTEL SOW707 FEDERAL FOUNDRY OSM | 4576500% |  | ADT | LDT | WF1672871 | Mech | MAKE | ANSI 49 | 4586800% | 9 | 4575500% | 4576400% | 4577600% | FALSE | Apr-2025 | 5 | 8 | 14 | 6 | LATE | LATE | ON TIME BY ENG |  | C | 7 | IMPACTED |  |  | Closed | LATE | NA | 18 | 4576707% | 100%
PZ4 | 0051199249 | 000050 | 0051199249-000050 | INTEL SOW707 FEDERAL FOUNDRY OSM | 4576500% |  | ADT | LDT | WF1672864 | Mech | BUY | ANSI 49 | 4586800% | 9 | 4575500% | 4576900% | 4577200% | FALSE | Apr-2025 | 5 | 11 | 12 | 1 | LATE | LATE | ON TIME BY ENG |  | C | 5 | IMPACTED |  |  | Closed | LATE | NA | 17 | 4576942% | 100%
PZ4 | 0051199249 | 000040 | 0051199249-000040 | INTEL SOW707 FEDERAL FOUNDRY OSM | 4576800% |  | OAC | DPM | WF1672589 | Mech | MAKE | ANSI 49 | 4586900% | 10 | 4575500% | 4576200% | 4576100% | FALSE | Apr-2025 | 5 | 6 | 5 | -1 | ON TIME | ON TIME | ON TIME BY ENG |  | C | -4 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4576507% | 100%
PZ4 | 0051199249 | 000040 | 0051199249-000040 | INTEL SOW707 FEDERAL FOUNDRY OSM | 4576800% |  | OAC | DPM | WF1672697 | Mech | MAKE | ANSI 49 | 4586900% | 10 | 4575500% | 4576200% | 4576600% | FALSE | Apr-2025 | 5 | 6 | 7 | 1 | LATE | LATE | ON TIME BY ENG |  | C | -1 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4576507% | 100%
PZ4 | 0051199249 | 000040 | 0051199249-000040 | INTEL SOW707 FEDERAL FOUNDRY OSM | 4576800% |  | OAC | DPM | WF1672726 | Mech | MAKE | ANSI 49 | 4586900% | 10 | 4575500% | 4576200% | 4576600% | FALSE | Apr-2025 | 5 | 6 | 7 | 1 | LATE | LATE | ON TIME BY ENG |  | C | -1 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4576507% | 100%
PZ4 | 0051199249 | 000040 | 0051199249-000040 | INTEL SOW707 FEDERAL FOUNDRY OSM | 4576800% |  | OAC | DPM | WF1672783 | Mech | MAKE | ANSI 49 | 4586900% | 10 | 4575500% | 4576300% | 4576600% | FALSE | Apr-2025 | 5 | 7 | 7 | 0 | ON TIME | ON TIME | ON TIME BY ENG |  | C | -1 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4576607% | 100%
PZ4 | 0051199249 | 000040 | 0051199249-000040 | INTEL SOW707 FEDERAL FOUNDRY OSM | 4576800% |  | OAC | DPM | WF1672790 | Mech | MAKE | ANSI 49 | 4586900% | 10 | 4575500% | 4576300% | 4576100% | FALSE | Apr-2025 | 5 | 7 | 5 | -2 | ON TIME | ON TIME | ON TIME BY ENG |  | C | -4 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4576607% | 100%
PZ4 | 0051199249 | 000040 | 0051199249-000040 | INTEL SOW707 FEDERAL FOUNDRY OSM | 4576800% |  | OAC | VL | WF1672826 | Mech | MAKE | ANSI 49 | 4586900% | 10 | 4575500% | 4576300% | 4576300% | FALSE | Apr-2025 | 5 | 7 | 7 | 0 | ON TIME | ON TIME | ON TIME BY ENG |  | C | -2 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4576607% | 100%
PZ4 | 0051199249 | 000040 | 0051199249-000040 | INTEL SOW707 FEDERAL FOUNDRY OSM | 4576800% |  | OAC | VL | WF1672805 | Mech | BUY | ANSI 49 | 4586900% | 10 | 4575500% | 4576500% | 4576300% | FALSE | Apr-2025 | 5 | 9 | 7 | -2 | ON TIME | ON TIME | ON TIME BY ENG |  | C | -2 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 17 | 4576542% | 100%
PZ4 | 0050465708 | 000270 | 0050465708-000270 | COLLIER COUNTY NCWRF ELECTRICAL SERVICE | 4578200% |  | DEV | LDT | WF1672650 | Elec | BUY | ANSI 49 | 4589700% | 20 | 4575500% | 4576500% | 4576300% | FALSE | Apr-2025 | 5 | 9 | 7 | -2 | ON TIME | ON TIME | ON TIME BY ENG |  | C | -11 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 17 | 4576542% | 100%
PZ4 | 0050465708 | 000270 | 0050465708-000270 | COLLIER COUNTY NCWRF ELECTRICAL SERVICE | 4578200% |  | DEV | LDT | WF1672649 | Elec | BUY | ANSI 49 | 4589700% | 20 | 4575500% | 4576500% | 4576400% | FALSE | Apr-2025 | 5 | 9 | 7 | -2 | ON TIME | ON TIME | ON TIME BY ENG |  | C | -10 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 17 | 4576542% | 100%
PZ4 | 0050206201 | 000170 | 0050206201-000170 | AT&T GREENWOOD - GEAR ORDER | 4576200% |  | DR | OAL | WF1674297 | Mech | MAKE | ANSI 49 | 4588800% | 4 | 4575700% | 4576800% | 4577700% | FALSE | Apr-2025 | 5 | 8 | 13 | 5 | LATE | LATE | LATE BY ENG |  | C | 10 | IMPACTED |  |  | Closed | LATE | NA | 18 | 4577107% | 100%
PZ4 | 0050206201 | 000160 | 0050206201-000160 | AT&T GREENWOOD - GEAR ORDER | 4576900% |  | JAM | ADL | WF1674295 | Mech | MAKE | ANSI 49 | 4586800% | 9 | 4575700% | 4576800% | 4577000% | FALSE | Apr-2025 | 5 | 8 | 8 | 0 | ON TIME | ON TIME | ON TIME BY ENG |  | C | 2 | IMPACTED |  |  | Closed | LATE | NA | 18 | 4577107% | 100%
PZ4 | 0050206201 | 000160 | 0050206201-000160 | AT&T GREENWOOD - GEAR ORDER | 4576900% |  | JAM | ADL | WF1674300 | Mech | MAKE | ANSI 49 | 4586800% | 9 | 4575700% | 4576800% | 4577000% | FALSE | Apr-2025 | 5 | 8 | 8 | 0 | ON TIME | ON TIME | ON TIME BY ENG |  | C | 2 | IMPACTED |  |  | Closed | LATE | NA | 18 | 4577107% | 100%
PZ4 | 0051199249 | 000040 | 0051199249-000040 | INTEL SOW707 FEDERAL FOUNDRY OSM | 4576800% |  | OAC | VL | WF1675519 | Mech | MAKE | ANSI 49 | 4586900% | 6 | 4576100% | 4577000% | 4577600% | FALSE | Apr-2025 | 5 | 8 | 10 | 2 | LATE | LATE | ON TIME BY ENG |  | C | 7 | IMPACTED |  |  | Closed | LATE | NA | 18 | 4577307% | 100%
PZ4 | 0051199249 | 000040 | 0051199249-000040 | INTEL SOW707 FEDERAL FOUNDRY OSM | 4576800% |  | OAC | VL | WF1675659 | Mech | MAKE | ANSI 49 | 4586900% | 6 | 4576100% | 4577100% | 4577700% | FALSE | Apr-2025 | 5 | 9 | 11 | 2 | LATE | LATE | ON TIME BY ENG |  | C | 8 | IMPACTED |  |  | Closed | LATE | NA | 18 | 4577407% | 100%
PZ4 | 0051199249 | 000040 | 0051199249-000040 | INTEL SOW707 FEDERAL FOUNDRY OSM | 4576800% |  | OAC | VL | WF1675650 | Mech | BUY | ANSI 49 | 4586900% | 6 | 4576100% | 4577500% | 4577700% | FALSE | Apr-2025 | 5 | 11 | 11 | 0 | ON TIME | ON TIME | ON TIME BY ENG |  | C | 8 | IMPACTED |  |  | Closed | LATE | NA | 17 | 4577542% | 100%
PZ4 | 0050206201 | 000160 | 0050206201-000160 | AT&T GREENWOOD - GEAR ORDER | 4576900% |  | JAM | ADL | WF1675631 | Mech | BUY | ANSI 49 | 4586800% | 7 | 4576100% | 4577500% | 4577700% | FALSE | Apr-2025 | 5 | 11 | 11 | 0 | ON TIME | ON TIME | ON TIME BY ENG |  | C | 7 | IMPACTED |  |  | Closed | LATE | NA | 17 | 4577542% | 100%
PZ4 | 0051199249 | 000040 | 0051199249-000040 | INTEL SOW707 FEDERAL FOUNDRY OSM | 4576800% |  | OAC | VL | WF1676332 | Mech | MAKE | ANSI 49 | 4586900% | 5 | 4576200% | 4577100% | 4577000% | FALSE | Apr-2025 | 5 | 8 | 5 | -3 | ON TIME | ON TIME | ON TIME BY ENG |  | C | 3 | IMPACTED |  |  | Closed | LATE | NA | 18 | 4577407% | 100%
PZ4 | 0051199249 | 000040 | 0051199249-000040 | INTEL SOW707 FEDERAL FOUNDRY OSM | 4576800% |  | OAC | VL | WF1676327 | Mech | BUY | ANSI 49 | 4586900% | 5 | 4576200% | 4577600% | 4577200% | FALSE | Apr-2025 | 5 | 11 | 7 | -4 | ON TIME | ON TIME | ON TIME BY ENG |  | C | 5 | IMPACTED |  |  | Closed | LATE | NA | 17 | 4577642% | 100%
PZ4 | 0050206201 | 000160 | 0050206201-000160 | AT&T GREENWOOD - GEAR ORDER | 4576900% |  | JAM | ADL | WF1676370 | Mech | MAKE | ANSI 49 | 4586800% | 6 | 4576200% | 4577100% | 4577600% | FALSE | Apr-2025 | 5 | 8 | 9 | 1 | LATE | LATE | ON TIME BY ENG |  | C | 6 | IMPACTED |  |  | Closed | LATE | NA | 18 | 4577407% | 100%
PZ4 | 0051002556 | 000010 | 0051002556-000010 | ROYAL CARRIBEAN ES-43478 | 4577900% |  | DMA | OAL | WF1676353 | Mech | MAKE | ANSI 49 | 4589600% | 14 | 4576200% | 4577100% | 4577700% | FALSE | Apr-2025 | 5 | 8 | 10 | 2 | LATE | LATE | ON TIME BY ENG |  | C | -2 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4577407% | 100%
PZ4 | 0051002556 | 000010 | 0051002556-000010 | ROYAL CARRIBEAN ES-43478 | 4577900% |  | DMA | OAL | WF1676356 | Mech | BUY | ANSI 49 | 4589600% | 14 | 4576200% | 4577600% | 4577700% | FALSE | Apr-2025 | 5 | 11 | 10 | -1 | ON TIME | ON TIME | ON TIME BY ENG |  | C | -2 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 17 | 4577642% | 100%
PZ4 | 0051117529 | 000020 | 0051117529-000020 | STOWERS INSTITUTE - SUBSTATION REPLACEME | 4579300% |  | RAS | ISQ | WF1680995 | Mech | MAKE | ANSI 49 | 4589800% | 16 | 4577200% | 4578200% | 4577700% | FALSE | Apr-2025 | 5 | 7 | 4 | -3 | ON TIME | ON TIME | ON TIME BY ENG |  | C | -11 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4578507% | 100%
PZ4 | 0051229942 | 000120 | 0051229942-000120 | MICRON ID1 - PROJECT OPAL -WSP - BLDG B | 4580000% |  | MGL | ADL | WF1686775 | Mech | MAKE | ANSI 49 | 4588800% | 12 | 4578500% | 4579300% | 4580000% | FALSE | May-2025 | 5 | 7 | 11 | 4 | LATE | LATE | ON TIME BY ENG |  | C | 1 | IMPACTED |  |  | Closed | LATE | NA | 18 | 4579607% | 100%
PZ4 | 0051229942 | 000120 | 0051229942-000120 | MICRON ID1 - PROJECT OPAL -WSP - BLDG B | 4580000% |  | MGL | ADL | WF1686777 | Mech | MAKE | ANSI 49 | 4588800% | 12 | 4578500% | 4579300% | 4579800% | FALSE | May-2025 | 5 | 7 | 9 | 2 | LATE | LATE | ON TIME BY ENG |  | C | -3 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4579607% | 100%
PZ4 | 0051229942 | 000120 | 0051229942-000120 | MICRON ID1 - PROJECT OPAL -WSP - BLDG B | 4580000% |  | MGL | ADL | WF1686783 | Mech | MAKE | ANSI 49 | 4588800% | 12 | 4578500% | 4579300% | 4580000% | FALSE | May-2025 | 5 | 7 | 11 | 4 | LATE | LATE | ON TIME BY ENG |  | C | 1 | IMPACTED |  |  | Closed | LATE | NA | 18 | 4579607% | 100%
PZ4 | 0051229942 | 000120 | 0051229942-000120 | MICRON ID1 - PROJECT OPAL -WSP - BLDG B | 4580000% |  | MGL | ADL | WF1686785 | Mech | MAKE | ANSI 49 | 4588800% | 12 | 4578500% | 4579300% | 4580000% | FALSE | May-2025 | 5 | 7 | 11 | 4 | LATE | LATE | ON TIME BY ENG |  | C | 1 | IMPACTED |  |  | Closed | LATE | NA | 18 | 4579607% | 100%
PZ4 | 0051229942 | 000120 | 0051229942-000120 | MICRON ID1 - PROJECT OPAL -WSP - BLDG B | 4580000% |  | MGL | ADL | WF1686787 | Mech | BUY | ANSI 49 | 4588800% | 12 | 4578500% | 4579800% | 4580000% | FALSE | May-2025 | 5 | 10 | 11 | 1 | LATE | LATE | ON TIME BY ENG |  | C | 1 | IMPACTED |  |  | Closed | LATE | NA | 17 | 4579842% | 100%
PZ4 | 0051229942 | 000120 | 0051229942-000120 | MICRON ID1 - PROJECT OPAL -WSP - BLDG B | 4580000% |  | MGL | ADL | WF1688951 | Mech | MAKE | ANSI 49 | 4588800% | 9 | 4579000% | 4579800% | 4579700% | FALSE | May-2025 | 5 | 7 | 6 | -1 | ON TIME | ON TIME | ON TIME BY ENG |  | C | -4 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4580107% | 100%
PZ4 | 0051229942 | 000120 | 0051229942-000120 | MICRON ID1 - PROJECT OPAL -WSP - BLDG B | 4580000% |  | MGL | ADL | WF1689509 | Mech | MAKE | ANSI 49 | 4588800% | 8 | 4579100% | 4579800% | 4579800% | FALSE | May-2025 | 5 | 6 | 6 | 0 | ON TIME | ON TIME | ON TIME BY ENG |  | C | -3 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4580107% | 100%
PZ4 | 0051004478 | 000010 | 0051004478-000010 | BEACON HEALTH ES-43461 | 4580000% |  | DMA | OAL | WF1690270 | Mech | MAKE | ANSI 49 | 4593900% | 7 | 4579200% | 4580000% | 4580000% | FALSE | May-2025 | 5 | 7 | 7 | 0 | ON TIME | ON TIME | ON TIME BY ENG |  | C | 1 | IMPACTED |  |  | Closed | LATE | NA | 18 | 4580307% | 100%
PZ4 | 0051004478 | 000010 | 0051004478-000010 | BEACON HEALTH ES-43461 | 4580000% |  | DMA | OAL | WF1690272 | Mech | MAKE | ANSI 49 | 4593900% | 7 | 4579200% | 4580000% | 4581300% | FALSE | May-2025 | 5 | 7 | 16 | 9 | LATE | LATE | ON TIME BY ENG |  | C | 10 | IMPACTED |  |  | Closed | LATE | NA | 18 | 4580307% | 100%
PZ4 | 0051004478 | 000010 | 0051004478-000010 | BEACON HEALTH ES-43461 | 4580000% |  | DMA | OAL | WF1690273 | Mech | BUY | ANSI 49 | 4593900% | 7 | 4579200% | 4580400% | 4580600% | FALSE | May-2025 | 5 | 9 | 11 | 2 | LATE | LATE | ON TIME BY ENG |  | C | 5 | IMPACTED |  |  | Closed | LATE | NA | 17 | 4580442% | 100%
PZ4 | 0050545482 | 001640 | 0050545482-001640 | Y12 MERCURY TREATMENT FACILITY | 4580700% |  | ASP | FRC | WF1691558 | Mech | MAKE | ANSI 49 | 4600000% | 10 | 4579600% | 4580300% | 4580000% | FALSE | May-2025 | 5 | 6 | 5 | -1 | ON TIME | ON TIME | ON TIME BY ENG |  | C | -6 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4580607% | 100%
PZ4 | 0050545482 | 001640 | 0050545482-001640 | Y12 MERCURY TREATMENT FACILITY | 4580700% |  | ASP | FRC | WF1692399 | Mech | MAKE | ANSI 49 | 4600000% | 9 | 4579700% | 4580500% | 4581300% | FALSE | May-2025 | 5 | 7 | 13 | 6 | LATE | LATE | ON TIME BY ENG |  | C | 5 | IMPACTED |  |  | Closed | LATE | NA | 18 | 4580807% | 100%
PZ4 | 0050545482 | 001640 | 0050545482-001640 | Y12 MERCURY TREATMENT FACILITY | 4580700% |  | ASP | FRC | WF1693128 | Mech | MAKE | ANSI 49 | 4600000% | 8 | 4579800% | 4580600% | 4580600% | FALSE | May-2025 | 5 | 7 | 7 | 0 | ON TIME | ON TIME | ON TIME BY ENG |  | C | -2 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4580907% | 100%
PZ4 | 0050545482 | 001640 | 0050545482-001640 | Y12 MERCURY TREATMENT FACILITY | 4580700% |  | ASP | FRC | WF1693146 | Mech | MAKE | ANSI 49 | 4600000% | 8 | 4579800% | 4580600% | 4581700% | FALSE | May-2025 | 5 | 7 | 14 | 7 | LATE | LATE | ON TIME BY ENG |  | C | 7 | IMPACTED |  |  | Closed | LATE | NA | 18 | 4580907% | 100%
PZ4 | 0050545482 | 001640 | 0050545482-001640 | Y12 MERCURY TREATMENT FACILITY | 4580700% |  | ASP | FRC | WF1693165 | Mech | MAKE | ANSI 49 | 4600000% | 8 | 4579800% | 4580600% | 4581100% | FALSE | May-2025 | 5 | 7 | 10 | 3 | LATE | LATE | ON TIME BY ENG |  | C | 3 | IMPACTED |  |  | Closed | LATE | NA | 18 | 4580907% | 100%
PZ4 | 0050545482 | 001640 | 0050545482-001640 | Y12 MERCURY TREATMENT FACILITY | 4580700% |  | ASP | FRC | WF1693140 | Mech | BUY | ANSI 49 | 4600000% | 8 | 4579800% | 4581000% | 4581300% | FALSE | May-2025 | 5 | 9 | 12 | 3 | LATE | LATE | ON TIME BY ENG |  | C | 5 | IMPACTED |  |  | Closed | LATE | NA | 17 | 4581042% | 100%
PZ4 | 0050545482 | 001640 | 0050545482-001640 | Y12 MERCURY TREATMENT FACILITY | 4580700% |  | ASP | FRC | WF1693161 | Mech | BUY | ANSI 49 | 4600000% | 8 | 4579800% | 4581000% | 4581000% | FALSE | May-2025 | 5 | 9 | 9 | 0 | ON TIME | ON TIME | ON TIME BY ENG |  | C | 2 | IMPACTED |  |  | Closed | LATE | NA | 17 | 4581042% | 100%
PZ4 | 0051329560 | 000010 | 0051329560-000010 | STANDALONE CONNECT TO VETERANS ES-43368 | 4581400% |  | DMA | KGF | WF1693768 | Mech | BUY | ANSI 49 | 4591800% | 12 | 4579900% | 4581100% | 4581000% | FALSE | May-2025 | 5 | 9 | 8 | -1 | ON TIME | ON TIME | ON TIME BY ENG |  | C | -5 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 17 | 4581142% | 100%
PZ4 | 0051329560 | 000010 | 0051329560-000010 | STANDALONE CONNECT TO VETERANS ES-43368 | 4581400% |  | DMA | KGF | WF1694324 | Mech | MAKE | ANSI 49 | 4591800% | 11 | 4580000% | 4580700% | 4580700% | FALSE | May-2025 | 5 | 6 | 6 | 0 | ON TIME | ON TIME | ON TIME BY ENG |  | C | -6 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4581007% | 100%
PZ4 | 0051034440 | 000040 | 0051034440-000040 | LINCOLN TRANSPORTATION AND UTILITIES LIN | 4582100% |  | JRC | ISQ | WF1694419 | Mech | MAKE | ANSI 61 |  | 16 | 4580000% | 4581000% | 4580700% | FALSE | May-2025 | 5 | 7 | 6 | -1 | ON TIME | ON TIME | ON TIME BY ENG |  | C | -11 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4581307% | 100%
PZ4 | 0050762569 | 000090 | 0050762569-000090 | MCLEOD HEALTH - CAROLINA FOREST CAMHUPS H | 4580700% |  | HMA | ODE | WF1695200 | Mech | MAKE | ANSI 49 | 4591900% | 5 | 4580300% | 4581100% | 4581100% | FALSE | May-2025 | 5 | 7 | 7 | 0 | ON TIME | ON TIME | ON TIME BY ENG |  | C | 3 | IMPACTED |  |  | Closed | LATE | NA | 18 | 4581407% | 100%
PZ4 | 0050762569 | 000090 | 0050762569-000090 | MCLEOD HEALTH - CAROLINA FOREST CAMHUPS H | 4580700% |  | HMA | ODE | WF1695202 | Mech | MAKE | ANSI 49 | 4591900% | 5 | 4580300% | 4581100% | 4581100% | FALSE | May-2025 | 5 | 7 | 7 | 0 | ON TIME | ON TIME | ON TIME BY ENG |  | C | 3 | IMPACTED |  |  | Closed | LATE | NA | 18 | 4581407% | 100%
PZ4 | 0050762569 | 000090 | 0050762569-000090 | MCLEOD HEALTH - CAROLINA FOREST CAMHUPS H | 4580700% |  | HMA | ODE | WF1695208 | Mech | MAKE | ANSI 49 | 4591900% | 5 | 4580300% | 4581100% | 4581100% | FALSE | May-2025 | 5 | 7 | 7 | 0 | ON TIME | ON TIME | ON TIME BY ENG |  | C | 3 | IMPACTED |  |  | Closed | LATE | NA | 18 | 4581407% | 100%
PZ4 | 0050762569 | 000010 | 0050762569-000010 | MCLEOD HEALTH - CAROLINA FOREST CAMHUPS H | 4581400% |  | JTV | CML | WF1695848 | Mech | MAKE | ANSI 49 | 4591800% | 9 | 4580400% | 4581100% | 4581100% | FALSE | May-2025 | 5 | 6 | 6 | 0 | ON TIME | ON TIME | ON TIME BY ENG |  | C | -4 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4581407% | 100%
PZ4 | 0050988425 | 000040 | 0050988425-000040 | DC TILLMAN | 4581900% |  | RRD | OAL | WF1695930 | Mech | MAKE | ANSI 49 | 4600200% | 12 | 4580400% | 4581300% | 4581200% | FALSE | May-2025 | 5 | 8 | 7 | -1 | ON TIME | ON TIME | ON TIME BY ENG |  | C | -6 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4581607% | 100%
PZ4 | 0050988425 | 000040 | 0050988425-000040 | DC TILLMAN | 4581900% |  | RRD | OAL | WF1695932 | Mech | MAKE | ANSI 49 | 4600200% | 12 | 4580400% | 4581300% | 4581200% | FALSE | May-2025 | 5 | 8 | 7 | -1 | ON TIME | ON TIME | ON TIME BY ENG |  | C | -6 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4581607% | 100%
PZ4 | 0051198254 | 000010 | 0051198254-000010 | EOEM - STATES MANUFACTURING - AA - LEWIS | 4581700% |  | JAM | VL | WF1697130 | Mech | MAKE | ANSI 49 | 4589400% | 8 | 4580600% | 4581300% | 4581900% | FALSE | May-2025 | 5 | 6 | 10 | 4 | LATE | LATE | ON TIME BY ENG |  | C | 3 | IMPACTED |  |  | Closed | LATE | NA | 18 | 4581607% | 100%
PZ4 | 0051198254 | 000010 | 0051198254-000010 | EOEM - STATES MANUFACTURING - AA - LEWIS | 4581700% |  | JAM | VL | WF1697176 | Mech | BUY | ANSI 49 | 4589400% | 8 | 4580600% | 4581800% | 4581900% | FALSE | May-2025 | 5 | 9 | 10 | 1 | LATE | LATE | ON TIME BY ENG |  | C | 3 | IMPACTED |  |  | Closed | LATE | NA | 17 | 4581842% | 100%
PZ4 | 0051034440 | 000020 | 0051034440-000020 | LINCOLN TRANSPORTATION AND UTILITIES LIN | 4582100% |  | JRC | ISQ | WF1697178 | Mech | MAKE | ANSI 61 |  | 12 | 4580600% | 4581400% | 4581100% | FALSE | May-2025 | 5 | 7 | 4 | -3 | ON TIME | ON TIME | ON TIME BY ENG |  | C | -9 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4581707% | 100%
PZ4 | 0050762569 | 000040 | 0050762569-000040 | MCLEOD HEALTH - CAROLINA FOREST CAMHUPS H | 4582100% |  | JTV | HUP | WF1697184 | Mech | MAKE | ANSI 49 | 4591800% | 12 | 4580600% | 4581400% | 4581100% | FALSE | May-2025 | 5 | 7 | 4 | -3 | ON TIME | ON TIME | ON TIME BY ENG |  | C | -9 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4581707% | 100%
PZ4 | 0051198254 | 000010 | 0051198254-000010 | EOEM - STATES MANUFACTURING - AA - LEWIS | 4581700% |  | JAM | VL | WF1697587 | Mech | MAKE | ANSI 49 | 4589400% | 7 | 4580700% | 4581400% | 4581400% | FALSE | May-2025 | 5 | 6 | 6 | 0 | ON TIME | ON TIME | ON TIME BY ENG |  | C | -2 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4581707% | 100%
PZ4 | 0051138616 | 000070 | 0051138616-000070 | BWXT Q9 | 4583500% |  | HMA | ODE | WF1700864 | Mech | MAKE | ANSI 49 | 4620400% | 16 | 4581400% | 4582100% | 4582200% | FALSE | Jun-2025 | 5 | 6 | 6 | 0 | ON TIME | ON TIME | ON TIME BY ENG |  | C | -10 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4582407% | 100%
PZ4 | 0050754152 | 000090 | 0050754152-000090 | TOWER SEMICONDUCTOR - SAN ANTONIO - ALTE | 4583300% |  | DMA | LDT | WF1701677 | Elec | MAKE | ANSI 49 | 4592200% | 13 | 4581700% | 4582500% | 4582700% | FALSE | Jun-2025 | 5 | 7 | 9 | 2 | LATE | LATE | ON TIME BY ENG |  | C | -5 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4582807% | 100%
PZ4 | 0050665738 | 000700&710 | 0050665738-000700&710 | REX UNC HEALTHCARE S | 4583500% |  | JAM | ODE | WF1703048 | Elec | MAKE | ANSI 49 | 4593000% | 13 | 4581900% | 4582600% | 4582700% | FALSE | Jun-2025 | 5 | 6 | 7 | 1 | LATE | LATE | ON TIME BY ENG |  | C | -7 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4582907% | 100%
PZ4 | 0050665738 | 000700&710 | 0050665738-000700&710 | REX UNC HEALTHCARE S | 4583500% |  | JAM | ODE | WF1703053 | Elec | BUY | ANSI 49 | 4593000% | 13 | 4581900% | 4583100% | 4585400% | FALSE | Jun-2025 | 5 | 9 | 26 | 17 | LATE | SUPER LATE | ON TIME BY ENG |  | C | 14 | IMPACTED |  |  | Closed | LATE | NA | 17 | 4583142% | 100%
PZ4 | 0051022459 | 004500 | 0051022459-004500 | THE ROUX INSTITUTE | 4583500% |  | JMZ | DPM | WF1703053 | Elec | BUY | ANSI 49 | 4594400% | 13 | 4581900% | 4583100% | 4585400% | FALSE | Jun-2025 | 5 | 9 | 26 | 17 | LATE | SUPER LATE | ON TIME BY ENG |  | C | 14 | IMPACTED |  |  | Closed | LATE | NA | 17 | 4583142% | 100%
PZ4 | 0051020870 | 000840 | 0051020870-000840 | BUNKER HILL WTP | 4584900% |  | JAV | AL | WF1703229 | Elec | BUY | ANSI 61 | 4608000% | 23 | 4581900% | 4583100% | 4583200% | FALSE | Jun-2025 | 5 | 9 | 10 | 1 | LATE | LATE | ON TIME BY ENG |  | C | -14 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 17 | 4583142% | 100%
PZ4 | 0050988425 | 001260 | 0050988425-001260 | DC TILLMAN | 4583500% |  | RRD | OAL | WF1691406 | Elec | MAKE | ANSI 49 | 4600200% | 12 | 4582000% | 4580300% | 4585900% | FALSE | Jun-2025 | 5 | -14 | 28 | 42 | LATE | SUPER LATE | ON TIME BY ENG |  | C | 17 | IMPACTED |  |  | Closed | LATE | NA | 18 | 4580607% | 100%
PZ4 | 0050988425 | 001260 | 0050988425-001260 | DC TILLMAN | 4583500% |  | RRD | OAL | WF1703793 | Elec | BUY | ANSI 49 | 4600200% | 12 | 4582000% | 4583200% | 4585200% | FALSE | Jun-2025 | 5 | 9 | 23 | 14 | LATE | LATE | ON TIME BY ENG |  | C | 12 | IMPACTED |  |  | Closed | LATE | NA | 17 | 4583242% | 100%
PZ4 | 0050665738 | 000700&710 | 0050665738-000700&710 | REX UNC HEALTHCARE S | 4583500% |  | JAM | ODE | WF1703644 | Elec | BUY | ANSI 49 | 4593000% | 12 | 4582000% | 4583200% | 4583400% | FALSE | Jun-2025 | 5 | 9 | 11 | 2 | LATE | LATE | ON TIME BY ENG |  | C | -2 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 17 | 4583242% | 100%
PZ4 | 0051020870 | 000840 | 0051020870-000840 | BUNKER HILL WTP | 4584900% |  | JAV | AL | WF1703674 | Elec | MAKE | ANSI 61 | 4608000% | 22 | 4582000% | 4583200% | 4583200% | FALSE | Jun-2025 | 5 | 9 | 9 | 0 | ON TIME | ON TIME | ON TIME BY ENG |  | x | -14 | NOT IMPACTED |  | Found PN | Cancelled | ON TIME | NA | 0 | 4583507% | 0%
PZ4 | 0050665738 | 000700 | 0050665738-000700 | REX UNC HEALTHCARE S | 4583500% |  | JAM | ODE | WF1704391 | Elec | MAKE | ANSI 49 | 4593000% | 11 | 4582100% | 4583100% | 4583800% | FALSE | Jun-2025 | 5 | 7 | 12 | 5 | LATE | LATE | ON TIME BY ENG |  | C | 2 | IMPACTED |  |  | Closed | LATE | NA | 18 | 4583407% | 100%
PZ4 | 0051229472 | 000100 | 0051229472-000100 | FRESHPET PHASE 2A - ENNIS, TX | 4584000% |  | MGL | ISQ | WF1704344 | Mech | MAKE | ANSI 49 | 4592600% | 14 | 4582100% | 4582800% | 4582800% | FALSE | Jun-2025 | 5 | 6 | 6 | 0 | ON TIME | ON TIME | ON TIME BY ENG |  | C | -9 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4583107% | 100%
PZ4 | 0051096008 | 000080 | 0051096008-000080 | BF GOODRICH - FORT WAYNE PLANT - SUBSTAT | 4584000% |  | DRV | CML | WF1704554 | Mech | MAKE | ANSI 61 | 4592300% | 13 | 4582300% | 4583200% | 4583400% | FALSE | Jun-2025 | 5 | 7 | 9 | 2 | LATE | LATE | ON TIME BY ENG |  | C | -5 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4583507% | 100%
PZ4 | 0051138733 | 000070 | 0051138733-000070 | BWXT Q10 SUB | 4584200% |  | HMA | FRC | WF1705119 | Mech | MAKE | ANSI 49 | 4603600% | 15 | 4582400% | 4583200% | 4583400% | FALSE | Jun-2025 | 5 | 7 | 9 | 2 | LATE | LATE | ON TIME BY ENG |  | C | -7 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4583507% | 100%
PZ4 | 0051020870 | 000840 | 0051020870-000840 | BUNKER HILL WTP | 4584900% |  | JAV | AL | WF1704960 | Elec | MAKE | ANSI 61 | 4608000% | 20 | 4582400% | 4583100% | 4583300% | FALSE | Jun-2025 | 5 | 6 | 8 | 2 | LATE | LATE | ON TIME BY ENG |  | C | -13 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4583407% | 100%
PZ4 | 0051020870 | 000840 | 0051020870-000840 | BUNKER HILL WTP | 4584900% |  | JAV | AL | WF1704965 | Elec | MAKE | ANSI 61 | 4608000% | 20 | 4582400% | 4583100% | 4583300% | FALSE | Jun-2025 | 5 | 6 | 8 | 2 | LATE | LATE | ON TIME BY ENG |  | C | -13 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4583407% | 100%
PZ4 | 0051020870 | 000840 | 0051020870-000840 | BUNKER HILL WTP | 4584900% |  | JAV | AL | WF1704972 | Elec | MAKE | ANSI 61 | 4608000% | 20 | 4582400% | 4583100% | 4583300% | FALSE | Jun-2025 | 5 | 6 | 8 | 2 | LATE | LATE | ON TIME BY ENG |  | C | -13 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4583407% | 100%
PZ4 | 0051020870 | 000840 | 0051020870-000840 | BUNKER HILL WTP | 4584900% |  | JAV | AL | WF1704978 | Elec | MAKE | ANSI 61 | 4608000% | 20 | 4582400% | 4583100% | 4583300% | FALSE | Jun-2025 | 5 | 6 | 8 | 2 | LATE | LATE | ON TIME BY ENG |  | C | -13 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4583407% | 100%
PZ4 | 0051020870 | 000840 | 0051020870-000840 | BUNKER HILL WTP | 4584900% |  | JAV | AL | WF1704998 | Elec | MAKE | ANSI 61 | 4608000% | 20 | 4582400% | 4583100% | 4583300% | FALSE | Jun-2025 | 5 | 6 | 8 | 2 | LATE | LATE | ON TIME BY ENG |  | C | -13 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4583407% | 100%
PZ4 | 0051020870 | 000840 | 0051020870-000840 | BUNKER HILL WTP | 4584900% |  | JAV | AL | WF1705004 | Elec | MAKE | ANSI 61 | 4608000% | 20 | 4582400% | 4583100% | 4583300% | FALSE | Jun-2025 | 5 | 6 | 8 | 2 | LATE | LATE | ON TIME BY ENG |  | C | -13 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4583407% | 100%
PZ4 | 0051020870 | 000840 | 0051020870-000840 | BUNKER HILL WTP | 4584900% |  | JAV | AL | WF1705013 | Elec | MAKE | ANSI 61 | 4608000% | 20 | 4582400% | 4583100% | 4583300% | FALSE | Jun-2025 | 5 | 6 | 8 | 2 | LATE | LATE | ON TIME BY ENG |  | C | -13 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4583407% | 100%
PZ4 | 0051020870 | 000840 | 0051020870-000840 | BUNKER HILL WTP | 4584900% |  | JAV | AL | WF1705022 | Elec | MAKE | ANSI 61 | 4608000% | 20 | 4582400% | 4583100% | 4583300% | FALSE | Jun-2025 | 5 | 6 | 8 | 2 | LATE | LATE | ON TIME BY ENG |  | C | -13 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4583407% | 100%
PZ4 | 0051020870 | 000840 | 0051020870-000840 | BUNKER HILL WTP | 4584900% |  | JAV | AL | WF1705028 | Elec | MAKE | ANSI 61 | 4608000% | 20 | 4582400% | 4583100% | 4583300% | FALSE | Jun-2025 | 5 | 6 | 8 | 2 | LATE | LATE | ON TIME BY ENG |  | C | -13 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4583407% | 100%
PZ4 | 0051020870 | 000840 | 0051020870-000840 | BUNKER HILL WTP | 4584900% |  | JAV | AL | WF1705056 | Elec | MAKE | ANSI 61 | 4608000% | 20 | 4582400% | 4583100% | 4583300% | FALSE | Jun-2025 | 5 | 6 | 8 | 2 | LATE | LATE | ON TIME BY ENG |  | C | -13 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4583407% | 100%
PZ4 | 0051020870 | 000840 | 0051020870-000840 | BUNKER HILL WTP | 4584900% |  | JAV | AL | WF1705115 | Elec | MAKE | ANSI 61 | 4608000% | 20 | 4582400% | 4583100% | 4584600% | FALSE | Jun-2025 | 5 | 6 | 17 | 11 | LATE | LATE | ON TIME BY ENG |  | C | -4 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4583407% | 100%
PZ4 | 0051020870 | 000840 | 0051020870-000840 | BUNKER HILL WTP | 4584900% |  | JAV | AL | WF1705120 | Elec | MAKE | ANSI 61 | 4608000% | 20 | 4582400% | 4583100% | 4583300% | FALSE | Jun-2025 | 5 | 6 | 8 | 2 | LATE | LATE | ON TIME BY ENG |  | C | -13 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4583407% | 100%
PZ4 | 0050754152 | 000090 | 0050754152-000090 | TOWER SEMICONDUCTOR - SAN ANTONIO - ALTE | 4583300% |  | DMA | LDT | WF1705814 | Mech | MAKE | ANSI 49 | 4592200% | 7 | 4582500% | 4583300% | 4583200% | FALSE | Jun-2025 | 5 | 7 | 6 | -1 | ON TIME | ON TIME | ON TIME BY ENG |  | x | -2 | NOT IMPACTED |  | Wrong PN | Cancelled | ON TIME | NA | 0 | 4583607% | 0%
PZ4 | 0051283748 | 000120 | 0051283748-000120 | TOYOTA PEMC | 4583800% |  | AOB | CML | WF1705861 | Elec | MAKE | ANSI 49 | 4592900% | 10 | 4582500% | 4583400% | 4583300% | FALSE | Jun-2025 | 5 | 8 | 7 | -1 | ON TIME | ON TIME | ON TIME BY ENG |  | C | -4 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4583707% | 100%
PZ4 | 0050754152 | 000090 | 0050754152-000090 | TOWER SEMICONDUCTOR - SAN ANTONIO - ALTE | 4583300% |  | DMA | LDT | WF1706367 | Mech | MAKE | ANSI 49 | 4592200% | 6 | 4582600% | 4583300% | 4583300% | FALSE | Jun-2025 | 5 | 6 | 6 | 0 | ON TIME | ON TIME | ON TIME BY ENG |  | C | 1 | IMPACTED |  |  | Closed | LATE | NA | 18 | 4583607% | 100%
PZ4 | 0050754152 | 000090 | 0050754152-000090 | TOWER SEMICONDUCTOR - SAN ANTONIO - ALTE | 4583300% |  | DMA | LDT | WF1706423 | Mech | MAKE | ANSI 49 | 4592200% | 6 | 4582600% | 4583300% | 4584300% | FALSE | Jun-2025 | 5 | 6 | 13 | 7 | LATE | LATE | ON TIME BY ENG |  | C | 8 | IMPACTED |  |  | Closed | LATE | NA | 18 | 4583607% | 100%
PZ4 | 0050754152 | 000090 | 0050754152-000090 | TOWER SEMICONDUCTOR - SAN ANTONIO - ALTE | 4583300% |  | DMA | LDT | WF1706432 | Mech | MAKE | ANSI 49 | 4592200% | 6 | 4582600% | 4583300% | 4583300% | FALSE | Jun-2025 | 5 | 6 | 6 | 0 | ON TIME | ON TIME | ON TIME BY ENG |  | C | 1 | IMPACTED |  |  | Closed | LATE | NA | 18 | 4583607% | 100%
PZ4 | 0050754152 | 000090 | 0050754152-000090 | TOWER SEMICONDUCTOR - SAN ANTONIO - ALTE | 4583300% |  | DMA | LDT | WF1709160 | Mech | MAKE | ANSI 49 | 4592200% | 6 | 4582600% | 4583900% | 4583900% | FALSE | Jun-2025 | 5 | 10 | 10 | 0 | ON TIME | ON TIME | ON TIME BY ENG |  | C | 5 | IMPACTED |  |  | Closed | LATE | NA | 18 | 4584207% | 100%
PZ4 | 0050665738 | 000700 | 0050665738-000700 | REX UNC HEALTHCARE S | 4583500% |  | JAM | ODE | WF1706503 | Mech | MAKE | ANSI 49 | 4593000% | 8 | 4582600% | 4583400% | 4583300% | FALSE | Jun-2025 | 5 | 7 | 6 | -1 | ON TIME | ON TIME | ON TIME BY ENG |  | C | -3 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4583707% | 100%
PZ4 | 0050665738 | 000700&710 | 0050665738-000700&710 | REX UNC HEALTHCARE S | 4583500% |  | JAM | ODE | WF1707204 | Elec | BUY | ANSI 49 | 4593000% | 7 | 4582700% | 4583400% | 4583900% | FALSE | Jun-2025 | 5 | 6 | 9 | 3 | LATE | LATE | ON TIME BY ENG |  | C | 3 | IMPACTED |  |  | Closed | LATE | NA | 17 | 4583442% | 100%
PZ4 | 0050665738 | 000700&710 | 0050665738-000700&710 | REX UNC HEALTHCARE S | 4583500% |  | JAM | ODE | WF1707205 | Elec | BUY | ANSI 49 | 4593000% | 7 | 4582700% | 4583400% | 4583900% | FALSE | Jun-2025 | 5 | 6 | 9 | 3 | LATE | LATE | ON TIME BY ENG |  | C | 3 | IMPACTED |  |  | Closed | LATE | NA | 17 | 4583442% | 100%
PZ4 | 0050665738 | 000700 | 0050665738-000700 | REX UNC HEALTHCARE S | 4583500% |  | JAM | ODE | WF1707006 | Mech | MAKE | ANSI 49 | 4593000% | 7 | 4582700% | 4583400% | 4583300% | FALSE | Jun-2025 | 5 | 6 | 5 | -1 | ON TIME | ON TIME | ON TIME BY ENG |  | C | -3 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4583707% | 100%
PZ4 | 0050665738 | 000700 | 0050665738-000700 | REX UNC HEALTHCARE S | 4583500% |  | JAM | ODE | WF1707018 | Mech | MAKE | ANSI 49 | 4593000% | 7 | 4582700% | 4583400% | 4584300% | FALSE | Jun-2025 | 5 | 6 | 12 | 6 | LATE | LATE | ON TIME BY ENG |  | C | 6 | IMPACTED |  |  | Closed | LATE | NA | 18 | 4583707% | 100%
PZ4 | 0051022459 | 004500 | 0051022459-004500 | THE ROUX INSTITUTE | 4583500% |  | JMZ | DPM | WF1708345 | Mech | MAKE | ANSI 49 | 4594400% | 5 | 4583100% | 4583800% | 4584100% | FALSE | Jun-2025 | 5 | 6 | 9 | 3 | LATE | LATE | ON TIME BY ENG |  | C | 5 | IMPACTED |  |  | Closed | LATE | NA | 18 | 4584107% | 100%
PZ4 | 0051020870 | 000840 | 0051020870-000840 | BUNKER HILL WTP | 4584900% |  | ALT | AL | WF1709320 | Mech | MAKE | ANSI 61 | 4608000% | 14 | 4583200% | 4584100% | 4584600% | FALSE | Jun-2025 | 5 | 8 | 11 | 3 | LATE | LATE | ON TIME BY ENG |  | C | -4 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4584407% | 100%
PZ4 | 0051020870 | 000840 | 0051020870-000840 | BUNKER HILL WTP | 4584900% |  | ALT | AL | WF1709322 | Elec | MAKE | ANSI 61 | 4608000% | 14 | 4583200% | 4584100% | 4585400% | FALSE | Jun-2025 | 5 | 8 | 17 | 9 | LATE | LATE | ON TIME BY ENG |  | C | 4 | IMPACTED |  |  | Closed | LATE | NA | 18 | 4584407% | 100%
PZ4 | 0051383209 | 000010 | 0051383209-000010 | CORNING ARM FURNACE FIT-UP | 4584800% |  | RRD | HUP | WF1709985 | Mech | MAKE | ANSI 49 | 4595000% | 12 | 4583300% | 4584100% | 4585400% | FALSE | Jun-2025 | 5 | 7 | 16 | 9 | LATE | LATE | ON TIME BY ENG |  | C | 5 | IMPACTED |  |  | Closed | LATE | NA | 18 | 4584407% | 100%
PZ4 | 0051020870 | 000840 | 0051020870-000840 | BUNKER HILL WTP | 4584900% |  | JAV | AL | WF1709903 | Elec | MAKE | ANSI 61 | 4608000% | 13 | 4583300% | 4584000% | 4584600% | FALSE | Jun-2025 | 5 | 6 | 10 | 4 | LATE | LATE | ON TIME BY ENG |  | C | -4 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4584307% | 100%
PZ4 | 0051306085 | 000280&000290 | 0051306085-000280&000290 | CYRUSONE - CYRUSONE, INC | 4584900% |  | JRC | IGS | WF1709991 | Elec | MAKE | ANSI 49 | 4595700% | 13 | 4583300% | 4584100% | 4584600% | FALSE | Jun-2025 | 5 | 7 | 10 | 3 | LATE | LATE | ON TIME BY ENG |  | C | -4 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4584407% | 100%
PZ4 | 0051427096 | 000120 | 0051427096-000120 | MICRON ID1 - HPM/PROBE F12A | 4586800% |  | HMA | ODE | WF1709976 | Elec | MAKE | ANSI 49 | 4595300% | 26 | 4583300% | 4584100% | 4584700% | FALSE | Jun-2025 | 5 | 7 | 11 | 4 | LATE | LATE | ON TIME BY ENG |  | C | -16 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4584407% | 100%
PZ4 | 0051283748 | 000120 | 0051283748-000120 | TOYOTA PEMC | 4583800% |  | AOB | CML | WF1710702 | Mech | MAKE | ANSI 49 | 4592900% | 3 | 4583400% | 4584200% | 4585200% | FALSE | Jun-2025 | 5 | 7 | 13 | 6 | LATE | LATE | LATE BY ENG |  | C | 11 | IMPACTED |  |  | Closed | LATE | NA | 18 | 4584507% | 100%
PZ4 | 0051383209 | 000010 | 0051383209-000010 | CORNING ARM FURNACE FIT-UP | 4584800% |  | RRD | HUP | WF1710566 | Mech | MAKE | ANSI 49 | 4595000% | 11 | 4583400% | 4584100% | 4585000% | FALSE | Jun-2025 | 5 | 6 | 12 | 6 | LATE | LATE | ON TIME BY ENG |  | C | 2 | IMPACTED |  |  | Closed | LATE | NA | 18 | 4584407% | 100%
PZ4 | 0051383209 | 000010 | 0051383209-000010 | CORNING ARM FURNACE FIT-UP | 4584800% |  | RRD | HUP | WF1710577 | Mech | MAKE | ANSI 49 | 4595000% | 11 | 4583400% | 4584100% | 4586000% | FALSE | Jun-2025 | 5 | 6 | 19 | 13 | LATE | LATE | ON TIME BY ENG |  | C | 9 | IMPACTED |  |  | Closed | LATE | NA | 18 | 4584407% | 100%
PZ4 | 0051383209 | 000010 | 0051383209-000010 | CORNING ARM FURNACE FIT-UP | 4584800% |  | RRD | HUP | WF1710583 | Mech | MAKE | ANSI 49 | 4595000% | 11 | 4583400% | 4584100% | 4584800% | FALSE | Jun-2025 | 5 | 6 | 11 | 5 | LATE | LATE | ON TIME BY ENG |  | C | 1 | IMPACTED |  |  | Closed | LATE | NA | 18 | 4584407% | 100%
PZ4 | 0051383209 | 000010 | 0051383209-000010 | CORNING ARM FURNACE FIT-UP | 4584800% |  | RRD | HUP | WF1710562 | Mech | BUY | ANSI 49 | 4595000% | 11 | 4583400% | 4584600% | 4585000% | FALSE | Jun-2025 | 5 | 9 | 12 | 3 | LATE | LATE | ON TIME BY ENG |  | C | 2 | IMPACTED |  |  | Closed | LATE | NA | 17 | 4584642% | 100%
PZ4 | 0051004478 | 000010 | 0051004478-000010 | BEACON HEALTH ES-43461 | 4580000% |  | DMA | OAL | WF1712648 | Mech | MAKE | ANSI 49 | 4593900% | -28 | 4583900% | 4584600% | 4585400% | FALSE | Jul-2025 | 5 | 6 | 12 | 6 | LATE | LATE | LATE BY ENG |  | C | 39 | IMPACTED |  |  | Closed | LATE | NA | 18 | 4584907% | 100%
PZ4 | 0051306085 | 000300 | 0051306085-000300 | CYRUSONE - CYRUSONE, INC | 4589100% |  | HMA | IGS | WF1713291 | Elec | MAKE | ANSI 49 | 4578900% | 38 | 4584000% | 4584700% | 4584700% | FALSE | Jul-2025 | 5 | 6 | 6 | 0 | ON TIME | ON TIME | ON TIME BY ENG |  | C | -33 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4585007% | 100%
PZ4 | 0051306085 | 000300 | 0051306085-000300 | CYRUSONE - CYRUSONE, INC | 4589100% |  | HMA | IGS | WF1713330 | Elec | MAKE | ANSI 49 | 4578900% | 38 | 4584000% | 4584700% | 4584700% | FALSE | Jul-2025 | 5 | 6 | 6 | 0 | ON TIME | ON TIME | ON TIME BY ENG |  | C | -33 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4585007% | 100%
PZ4 | 0051306085 | 000300 | 0051306085-000300 | CYRUSONE - CYRUSONE, INC | 4589100% |  | HMA | IGS | WF1713357 | Elec | MAKE | ANSI 49 | 4578900% | 38 | 4584000% | 4584700% | 4585500% | FALSE | Jul-2025 | 5 | 6 | 12 | 6 | LATE | LATE | ON TIME BY ENG |  | C | -27 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4585007% | 100%
PZ4 | 0051306085 | 000300 | 0051306085-000300 | CYRUSONE - CYRUSONE, INC | 4589100% |  | HMA | IGS | WF1713351 | Elec | BUY | ANSI 49 | 4578900% | 38 | 4584000% | 4585200% | 4585200% | FALSE | Jul-2025 | 5 | 9 | 9 | 0 | ON TIME | ON TIME | ON TIME BY ENG |  | C | -30 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 17 | 4585242% | 100%
PZ4 | 0051020870 | 000840 | 0051020870-000840 | BUNKER HILL WTP | 4584900% |  | JAV | AL | WF1714133 | Elec | MAKE | ANSI 61 | 4608000% | 7 | 4584100% | 4584900% | 4585400% | FALSE | Jul-2025 | 5 | 7 | 10 | 3 | LATE | LATE | ON TIME BY ENG |  | C | 4 | IMPACTED |  |  | Closed | LATE | NA | 18 | 4585207% | 100%
PZ4 | 0051020870 | 000840 | 0051020870-000840 | BUNKER HILL WTP | 4584900% |  | JAV | AL | WF1714125 | Elec | BUY | ANSI 61 | 4608000% | 7 | 4584100% | 4585300% | 4585200% | FALSE | Jul-2025 | 5 | 9 | 8 | -1 | ON TIME | ON TIME | ON TIME BY ENG |  | C | 2 | IMPACTED |  |  | Closed | LATE | NA | 17 | 4585342% | 100%
PZ4 | 0051296915 | 000010 | 0051296915-000010 | EAST CAROLINA UNIVERSITY (ECU) BRODY SCH | 4586900% |  | JAM | VL | WF1714164 | Elec | MAKE | ANSI 49 | 4598200% | 21 | 4584100% | 4585200% | 4585600% | FALSE | Jul-2025 | 5 | 8 | 12 | 4 | LATE | LATE | ON TIME BY ENG |  | C | -10 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4585507% | 100%
PZ4 | 0051296915 | 000010 | 0051296915-000010 | EAST CAROLINA UNIVERSITY (ECU) BRODY SCH | 4586900% |  | JAM | VL | WF1714161 | Elec | BUY | ANSI 49 | 4598200% | 21 | 4584100% | 4585500% | 4585500% | FALSE | Jul-2025 | 5 | 11 | 11 | 0 | ON TIME | ON TIME | ON TIME BY ENG |  | C | -11 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 17 | 4585542% | 100%
PZ4 | 0050866188 | 004960 | 0050866188-004960 | JHBSPH - 528 NORTH WASHINGTON ST | 4584900% |  | JTV | VL | WF1714810 | Mech | BUY | ANSI 49 | 4595000% | 5 | 4584400% | 4585300% | 4586700% | FALSE | Jul-2025 | 5 | 7 | 17 | 10 | LATE | LATE | ON TIME BY ENG |  | C | 13 | IMPACTED |  |  | Closed | LATE | NA | 17 | 4585342% | 100%
PZ4 | 0051283748 | 000120 | 0051283748-000120 | TOYOTA PEMC | 4583800% |  | AOB | CML | WF1716071 | Mech | MAKE | ANSI 49 | 4592900% | -6 | 4584500% | 4585300% | 4584900% | FALSE | Jul-2025 | 5 | 7 | 5 | -2 | ON TIME | ON TIME | LATE BY ENG |  | C | 10 | IMPACTED |  |  | Closed | LATE | NA | 18 | 4585607% | 100%
PZ4 | 0050866188 | 004690 | 0050866188-004690 | JHBSPH - 528 NORTH WASHINGTON ST | 4584900% |  | JTV | VL | WF1715227 | Mech | MAKE | ANSI 49 | 4595000% | 5 | 4584500% | 4585200% | 4586000% | FALSE | Jul-2025 | 5 | 6 | 12 | 6 | LATE | LATE | ON TIME BY ENG |  | C | 8 | IMPACTED |  |  | Closed | LATE | NA | 18 | 4585507% | 100%
PZ4 | 0050866188 | 004690 | 0050866188-004690 | JHBSPH - 528 NORTH WASHINGTON ST | 4584900% |  | JTV | VL | WF1715221 | Mech | BUY | ANSI 49 | 4595000% | 5 | 4584500% | 4585500% | 4585900% | FALSE | Jul-2025 | 5 | 9 | 11 | 2 | LATE | LATE | ON TIME BY ENG |  | C | 7 | IMPACTED |  |  | Closed | LATE | NA | 17 | 4585542% | 100%
PZ4 | 0051461793 | 000010 | 0051461793-000010 | BURLINGTON NEW DOUBLE-END SUBSTATION | 4583800% | 4603100% | KYC | NA | WF1716883 | Elec | MAKE | ANSI 49 | 4609800% | -8 | 4584700% | 4585400% | 4585500% | FALSE | Jul-2025 | 5 | 6 | 7 | 1 | LATE | LATE | LATE BY ENG |  | C | 14 | IMPACTED |  |  | Closed | LATE | NA | 18 | 4585707% | 100%
PZ4 | 0051461793 | 000010 | 0051461793-000010 | BURLINGTON NEW DOUBLE-END SUBSTATION | 4589100% | 4603100% | KYC | NA | WF1716891 | Elec | BUY | ANSI 49 | 4609800% | 33 | 4584700% | 4585900% | 4585500% | FALSE | Jul-2025 | 5 | 9 | 7 | -2 | ON TIME | ON TIME | ON TIME BY ENG |  | C | -27 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 17 | 4585942% | 100%
PZ4 | 0051306085 | 000310 | 0051306085 -000310 | CYRUSONE - CYRUSONE, INC | 4589100% |  | HMA | IGS | WF1717670 | Elec | BUY | ANSI 49 | 4578900% | 32 | 4584800% | 4586000% | 4586700% | FALSE | Jul-2025 | 5 | 9 | 14 | 5 | LATE | LATE | ON TIME BY ENG |  | C | -19 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 17 | 4586042% | 100%
PZ4 | 0051306085 | 000310 | 0051306085 -000310 | CORNING ARM FURNACE FIT-UP | 4584800% |  | RRD | HUP | WF1718673 | Elec | BUY | ANSI 49 | 4595000% | -3 | 4585200% | 4586200% | 4585900% | FALSE | Jul-2025 | 5 | 9 | 6 | -3 | ON TIME | ON TIME | LATE BY ENG |  | C | 8 | IMPACTED |  |  | Closed | LATE | NA | 17 | 4586242% | 100%
PZ4 | 0051306085 | 000310 | 0051306085 -000310 | CYRUSONE - CYRUSONE, INC | 4589100% |  | HMA | IGS | WF1718777 | Elec | BUY | ANSI 49 | 4578900% | 30 | 4585200% | 4586200% | 4585900% | FALSE | Jul-2025 | 5 | 9 | 6 | -3 | ON TIME | ON TIME | ON TIME BY ENG |  | C | -25 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 17 | 4586242% | 100%
PZ4 | 0050866188 | 004960 | 0050866188-004960 | JHBSPH - 528 NORTH WASHINGTON ST | 4584900% |  | JTV | VL | WF1719682 | Mech | BUY | ANSI 49 | 4595000% | -3 | 4585300% | 4586300% | 4586800% | FALSE | Jul-2025 | 5 | 9 | 12 | 3 | LATE | LATE | LATE BY ENG |  | C | 14 | IMPACTED |  |  | Closed | LATE | NA | 17 | 4586342% | 100%
PZ4 | 0050728484 | 018570 | 0050728484-018570 | MDACC CSB CLINICAL SERVICES BUILDING | 4589600% |  | KYC | KGF | WF1719687 | Mech | MAKE | ANSI 49 | 4598600% | 32 | 4585300% | 4586100% | 4586300% | FALSE | Jul-2025 | 5 | 7 | 9 | 2 | LATE | LATE | ON TIME BY ENG |  | C | -24 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4586407% | 100%
PZ4 | 0050728484 | 018570 | 0050728484-018570 | MDACC CSB CLINICAL SERVICES BUILDING | 4589600% |  | KYC | KGF | WF1719693 | Mech | MAKE | ANSI 49 | 4598600% | 32 | 4585300% | 4586100% | 4586300% | FALSE | Jul-2025 | 5 | 7 | 9 | 2 | LATE | LATE | ON TIME BY ENG |  | C | -24 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4586407% | 100%
PZ4 | 0051427096 | 000120 | 0051427096-000120 | MICRON ID1 - HPM/PROBE F12A | 4585600% |  | HMA | ODE | WF1721549 | Mech | MAKE | ANSI 49 | 4595300% | 1 | 4585600% | 4586300% | 4586700% | FALSE | Jul-2025 | 5 | 6 | 8 | 2 | LATE | LATE | LATE BY ENG |  | C | 8 | IMPACTED |  |  | Closed | LATE | NA | 18 | 4586607% | 100%
PZ4 | 0051427096 | 000120 | 0051427096-000120 | MICRON ID1 - HPM/PROBE F12A | 4586800% |  | HMA | ODE | WF1721556 | Mech | MAKE | ANSI 49 | 4595300% | 9 | 4585600% | 4586300% | 4586700% | FALSE | Jul-2025 | 5 | 6 | 8 | 2 | LATE | LATE | ON TIME BY ENG |  | C | -2 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4586607% | 100%
PZ4 | 0050728484 | 018570 | 0050728484-018570 | MDACC CSB CLINICAL SERVICES BUILDING | 4589600% |  | KYC | KGF | WF1721674 | Elec | MAKE | ANSI 49 | 4598600% | 29 | 4585600% | 4586600% | 4587300% | FALSE | Jul-2025 | 5 | 7 | 12 | 5 | LATE | LATE | ON TIME BY ENG |  | C | -18 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4586907% | 100%
PZ4 | 0050728484 | 018570 | 0050728484-018570 | MDACC CSB CLINICAL SERVICES BUILDING | 4589600% |  | KYC | KGF | WF1721676 | Elec | MAKE | ANSI 49 | 4598600% | 29 | 4585600% | 4586600% | 4587500% | FALSE | Jul-2025 | 5 | 7 | 14 | 7 | LATE | LATE | ON TIME BY ENG |  | C | -16 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4586907% | 100%
PZ4 | 0050728484 | 018570 | 0050728484-018570 | MDACC CSB CLINICAL SERVICES BUILDING | 4589600% |  | KYC | KGF | WF1721678 | Elec | MAKE | ANSI 49 | 4598600% | 29 | 4585600% | 4586600% | 4587300% | FALSE | Jul-2025 | 5 | 7 | 12 | 5 | LATE | LATE | ON TIME BY ENG |  | C | -18 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4586907% | 100%
PZ4 | 0050728484 | 018570 | 0050728484-018570 | MDACC CSB CLINICAL SERVICES BUILDING | 4589600% |  | KYC | KGF | WF1721679 | Elec | MAKE | ANSI 49 | 4598600% | 29 | 4585600% | 4586600% | 4588000% | FALSE | Jul-2025 | 5 | 7 | 17 | 10 | LATE | LATE | ON TIME BY ENG |  | C | -13 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4586907% | 100%
PZ4 | 0050728484 | 018570 | 0050728484-018570 | MDACC CSB CLINICAL SERVICES BUILDING | 4589600% |  | KYC | KGF | WF1722268 | Elec | MAKE | ANSI 49 | 4598600% | 29 | 4585600% | 4586600% | 4586100% | FALSE | Jul-2025 | 5 | 7 | 4 | -3 | ON TIME | ON TIME | ON TIME BY ENG |  | x | -26 | NOT IMPACTED |  |  | Cancelled | ON TIME | NA | 0 | 4586907% | 0%
PZ4 | 0050988425 | 001260 | 0050988425-001260 | DC TILLMAN | 4594400% |  | RRD | OAL | WF1722971 | Elec | MAKE | ANSI 49 | 4600200% | 61 | 4586000% | 4586700% | 4586900% | FALSE | Jul-2025 | 5 | 6 | 8 | 2 | LATE | LATE | ON TIME BY ENG |  | C | -53 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4587007% | 100%
PZ4 | 0050988425 | 001260 | 0050988425-001260 | DC TILLMAN | 4594400% |  | RRD | OAL | WF1722976 | Elec | MAKE | ANSI 49 | 4600200% | 61 | 4586000% | 4586700% | 4586900% | FALSE | Jul-2025 | 5 | 6 | 8 | 2 | LATE | LATE | ON TIME BY ENG |  | C | -53 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4587007% | 100%
PZ4 | 0050988425 | 001260 | 0050988425-001260 | DC TILLMAN | 4594400% |  | RRD | OAL | WF1722995 | Elec | MAKE | ANSI 49 | 4600200% | 61 | 4586000% | 4586700% | 4586900% | FALSE | Jul-2025 | 5 | 6 | 8 | 2 | LATE | LATE | ON TIME BY ENG |  | C | -53 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4587007% | 100%
PZ4 | 0050988425 | 001260 | 0050988425-001260 | DC TILLMAN | 4594400% |  | RRD | OAL | WF1722997 | Elec | MAKE | ANSI 49 | 4600200% | 61 | 4586000% | 4587300% | 4586700% | FALSE | Jul-2025 | 5 | 10 | 6 | -4 | ON TIME | ON TIME | ON TIME BY ENG |  | C | -55 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4587607% | 100%
PZ4 | 0051199001 | 000010 | 0051199001-000010 | EC1&EC2&EC3 | 4587700% |  | ASP | AL | WF1723629 | Elec | MAKE | RAL 7035 | 4598700% | 13 | 4586100% | 4586800% | 4586900% | FALSE | Jul-2025 | 5 | 6 | 7 | 1 | LATE | LATE | ON TIME BY ENG |  | C | -7 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4587107% | 100%
PZ4 | 0051199001 | 000010 | 0051199001-000010 | EC1&EC2&EC3 | 4587700% |  | ASP | AL | WF1723039 | Elec | BUY | RAL 7035 | 4598700% | 13 | 4586100% | 4587000% | 4588200% | FALSE | Jul-2025 | 5 | 8 | 16 | 8 | LATE | LATE | ON TIME BY ENG |  | C | 4 | IMPACTED |  |  | Closed | LATE | NA | 17 | 4587042% | 100%
PZ4 | 0051199001 | 000010 | 0051199001-000010 | EC1&EC2&EC3 | 4587700% |  | ASP | AL | WF1723841 | Elec | BUY | RAL 7035 | 4598700% | 13 | 4586100% | 4587300% | 4588200% | FALSE | Jul-2025 | 5 | 9 | 16 | 7 | LATE | LATE | ON TIME BY ENG |  | C | 4 | IMPACTED |  |  | Closed | LATE | NA | 17 | 4587342% | 100%
PZ4 | 0051199001 | 000010 | 0051199001-000010 | EC1&EC2&EC3 | 4587700% |  | ASP | AL | WF1723790 | Elec | BUY | RAL 7035 | 4598700% | 13 | 4586100% | 4587400% | 4586800% | FALSE | Jul-2025 | 5 | 10 | 6 | -4 | ON TIME | ON TIME | ON TIME BY ENG |  | C | -8 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 17 | 4587442% | 100%
PZ4 | 0051199001 | 000010 | 0051199001-000010 | EC1&EC2&EC3 | 4587700% |  | ASP | AL | WF1723765 | Elec | BUY | RAL 7035 | 4598700% | 13 | 4586100% | 4587500% | 4586800% | FALSE | Jul-2025 | 5 | 11 | 6 | -5 | ON TIME | ON TIME | ON TIME BY ENG |  | C | -8 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 17 | 4587542% | 100%
PZ4 | 0051199001 | 000010 | 0051199001-000010 | EC1&EC2&EC3 | 4587700% |  | ASP | AL | WF1723759 | Elec | BUY | RAL 7035 | 4598700% | 13 | 4586100% | 4587600% | 4586800% | FALSE | Jul-2025 | 5 | 12 | 6 | -6 | ON TIME | ON TIME | ON TIME BY ENG |  | C | -8 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 17 | 4587642% | 100%
PZ4 | 0051072452 | 000020&000470 | 0051072452-000020&000470 | UNITEDHEALTHCARE FOR PARSONS ELECTRIC | 4589800% |  | DRV | VL | WF1724577 | Elec | MAKE | ANSI 49 | 4600800% | 27 | 4586200% | 4587300% | 4588000% | FALSE | Jul-2025 | 5 | 8 | 13 | 5 | LATE | LATE | ON TIME BY ENG |  | C | -15 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4587607% | 100%
PZ4 | 0051072452 | 000020&000470 | 0051072452-000020&000470 | UNITEDHEALTHCARE FOR PARSONS ELECTRIC | 4589800% |  | DRV | VL | WF1724591 | Elec | MAKE | ANSI 49 | 4600800% | 27 | 4586200% | 4587300% | 4588800% | FALSE | Jul-2025 | 5 | 8 | 19 | 11 | LATE | LATE | ON TIME BY ENG |  | C | -9 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4587607% | 100%
PZ4 | 0051072452 | 000020&000470 | 0051072452-000020&000470 | UNITEDHEALTHCARE FOR PARSONS ELECTRIC | 4589800% |  | DRV | VL | WF1724586 | Elec | BUY | ANSI 49 | 4600800% | 27 | 4586200% | 4587600% | 4587400% | FALSE | Jul-2025 | 5 | 11 | 9 | -2 | ON TIME | ON TIME | ON TIME BY ENG |  | x | -19 | NOT IMPACTED |  | Wrong Classification in SAP | Cancelled | ON TIME | NA | 0 | 4587642% | 0%
PZ4 | 0050465708 | 000270 | 0050465708-000270 | COLLIER COUNTY NCWRF ELECTRICAL SERVICE | 4590000% |  | DEV | LDT | WF1725577 | Elec | BUY | ANSI 49 | 4602100% | 25 | 4586600% | 4587600% | 4586700% | FALSE | Jul-2025 | 5 | 9 | 2 | -7 | ON TIME | ON TIME | ON TIME BY ENG |  | C | -24 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 17 | 4587642% | 100%
PZ4 | 0051427096 | 000120 | 0051427096-000120 | MICRON ID1 - HPM/PROBE F12A | 4586800% |  | HMA | ODE | WF1727097 | Mech | MAKE | ANSI 49 | 4595300% | 1 | 4586800% | 4587600% | 4588300% | FALSE | Jul-2025 | 5 | 7 | 12 | 5 | LATE | LATE | LATE BY ENG |  | C | 12 | IMPACTED |  |  | Closed | LATE | NA | 18 | 4587907% | 100%
PZ4 | 0051427096 | 000120 | 0051427096-000120 | MICRON ID1 - HPM/PROBE F12A | 4586800% |  | HMA | ODE | WF1727106 | Mech | MAKE | ANSI 49 | 4595300% | 1 | 4586800% | 4587600% | 4588200% | FALSE | Jul-2025 | 5 | 7 | 11 | 4 | LATE | LATE | LATE BY ENG |  | C | 11 | IMPACTED |  |  | Closed | LATE | NA | 18 | 4587907% | 100%
PZ4 | 0051427096 | 000120 | 0051427096-000120 | MICRON ID1 - HPM/PROBE F12A | 4586800% |  | HMA | ODE | WF1727108 | Mech | BUY | ANSI 49 | 4595300% | 1 | 4586800% | 4588000% | 4588300% | FALSE | Jul-2025 | 5 | 9 | 12 | 3 | LATE | LATE | LATE BY ENG |  | C | 12 | IMPACTED |  |  | Closed | LATE | NA | 17 | 4588042% | 100%
PZ4 | 0051199001 | 000010 | 0051199001-000010 | EC1&EC2&EC3 | 4587700% |  | ASP | AL | WF1727653 | Mech | MAKE | RAL 7035 | 4598700% | 7 | 4586900% | 4587600% | 4588100% | FALSE | Jul-2025 | 5 | 6 | 9 | 3 | LATE | LATE | ON TIME BY ENG |  | C | 3 | IMPACTED |  |  | Closed | LATE | NA | 18 | 4587907% | 100%
PZ4 | 0051199001 | 000010 | 0051199001-000010 | EC1&EC2&EC3 | 4587700% |  | ASP | AL | WF1727836 | Mech | MAKE | RAL 7035 | 4598700% | 7 | 4586900% | 4588000% | 4588200% | FALSE | Jul-2025 | 5 | 8 | 10 | 2 | LATE | LATE | ON TIME BY ENG |  | C | 4 | IMPACTED |  |  | Closed | LATE | NA | 18 | 4588307% | 100%
PZ4 | 0051199001 | 000010 | 0051199001-000010 | EC1&EC2&EC3 | 4587700% |  | ASP | AL | WF1727675 | Elec | BUY | RAL 7035 | 4598700% | 7 | 4586900% | 4588100% | 4588300% | FALSE | Jul-2025 | 5 | 9 | 11 | 2 | LATE | LATE | ON TIME BY ENG |  | C | 5 | IMPACTED |  |  | Closed | LATE | NA | 17 | 4588142% | 100%
PZ4 | 0051306085 | 000310 | 0051306085 -000310 | CYRUSONE - CYRUSONE, INC | 4589100% |  | HMA | IGS | WF1727722 | Elec | BUY | ANSI 49 | 4578900% | 17 | 4586900% | 4588100% | 4589400% | FALSE | Jul-2025 | 5 | 9 | 18 | 9 | LATE | LATE | ON TIME BY ENG |  | C | 2 | IMPACTED |  |  | Closed | LATE | NA | 17 | 4588142% | 100%
PZ4 | 0050753978 | 003800 | 0050753978-003800 | KAISER SAN JOSE MEDICAL CENTER HOSPITAL | 4589800% |  | ALT | HUP | WF1727648 | Elec | MAKE | ANSI 49 | 4620700% | 22 | 4586900% | 4587600% | 4588800% | FALSE | Jul-2025 | 5 | 6 | 14 | 8 | LATE | LATE | ON TIME BY ENG |  | C | -9 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4587907% | 100%
PZ4 | 0051306085 | 000310 | 0051306085 -000310 | CYRUSONE - CYRUSONE, INC | 4589100% |  | HMA | IGS | WF1729134 | Mech | MAKE | ANSI 49 | 4578900% | 15 | 4587300% | 4588100% | 4588900% | FALSE | Aug-2025 | 5 | 7 | 13 | 6 | LATE | LATE | ON TIME BY ENG |  | C | -3 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4588407% | 100%
PZ4 | 0051306085 | 000310 | 0051306085 -000310 | CYRUSONE - CYRUSONE, INC | 4589100% |  | HMA | IGS | WF1729021 | Mech | BUY | ANSI 49 | 4578900% | 15 | 4587300% | 4588300% | 4588200% | FALSE | Aug-2025 | 5 | 9 | 8 | -1 | ON TIME | ON TIME | ON TIME BY ENG |  | C | -8 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 17 | 4588342% | 100%
PZ4 | 0050442535 | 000170 | 0050442535-000170 | RRMC GENERATOR REPLACEMENT PROJECT | 4594500% |  | ATA | CML | WF1729188 | Mech | MAKE | ANSI 49 | 4603500% | 53 | 4587300% | 4588100% | 4588300% | FALSE | Aug-2025 | 5 | 7 | 9 | 2 | LATE | LATE | ON TIME BY ENG |  | C | -44 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4588407% | 100%
PZ4 | 0051427096 | 000120 | 0051427096-000120 | MICRON ID1 - HPM/PROBE F12A | 4586800% |  | HMA | ODE | WF1729833 | Mech | MAKE | ANSI 49 | 4595300% | -5 | 4587400% | 4588200% | 4588200% | FALSE | Aug-2025 | 5 | 7 | 7 | 0 | ON TIME | ON TIME | LATE BY ENG |  | C | 11 | IMPACTED |  |  | Closed | LATE | NA | 18 | 4588507% | 100%
PZ4 | 0051072452 | 000020&000470 | 0051072452-000020&000470 | UNITEDHEALTHCARE FOR PARSONS ELECTRIC | 4589800% |  | DRV | VL | WF1729717 | Elec | MAKE | ANSI 49 | 4600800% | 19 | 4587400% | 4588100% | 4588800% | FALSE | Aug-2025 | 5 | 6 | 11 | 5 | LATE | LATE | ON TIME BY ENG |  | C | -9 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4588407% | 100%
PZ4 | 0051072452 | 000020&000470 | 0051072452-000020&000470 | UNITEDHEALTHCARE FOR PARSONS ELECTRIC | 4589800% |  | DRV | VL | WF1729834 | Elec | BUY | ANSI 49 | 4600800% | 19 | 4587400% | 4588400% | 4588400% | FALSE | Aug-2025 | 5 | 9 | 9 | 0 | ON TIME | ON TIME | ON TIME BY ENG |  | x | -11 | NOT IMPACTED |  |  | Cancelled | ON TIME | NA | 0 | 4588442% | 0%
PZ4 | 0051072452 | 000020&000470 | 0051072452-000020&000470 | UNITEDHEALTHCARE FOR PARSONS ELECTRIC | 4589800% |  | DRV | VL | WF1729812 | Elec | BUY | ANSI 49 | 4600800% | 19 | 4587400% | 4588400% | 4588300% | FALSE | Aug-2025 | 5 | 9 | 8 | -1 | ON TIME | ON TIME | ON TIME BY ENG |  | C | -12 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 17 | 4588442% | 100%
PZ4 | 0050728484 | 018570 | 0050728484-018570 | MDACC CSB CLINICAL SERVICES BUILDING | 4589600% |  | KYC | KGF | WF1730149 | Mech | MAKE | ANSI 49 | 4598600% | 16 | 4587500% | 4588300% | 4588700% | FALSE | Aug-2025 | 5 | 7 | 9 | 2 | LATE | LATE | ON TIME BY ENG |  | C | -8 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4588607% | 100%
PZ4 | 0051306085 | 000310 | 0051306085 -000310 | CYRUSONE - CYRUSONE, INC | 4589100% |  | HMA | IGS | WF1730939 | Mech | MAKE | ANSI 49 | 4578900% | 12 | 4587600% | 4588400% | 4588300% | FALSE | Aug-2025 | 5 | 7 | 6 | -1 | ON TIME | ON TIME | ON TIME BY ENG |  | C | -7 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4588707% | 100%
PZ4 | 0050728484 | 018570 | 0050728484-018570 | MDACC CSB CLINICAL SERVICES BUILDING | 4589600% |  | KYC | KGF | WF1730892 | Mech | MAKE | ANSI 49 | 4598600% | 15 | 4587600% | 4588300% | 4588300% | FALSE | Aug-2025 | 5 | 6 | 6 | 0 | ON TIME | ON TIME | ON TIME BY ENG |  | C | -10 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4588607% | 100%
PZ4 | 0051072452 | 000020&000470 | 0051072452-000020&000470 | UNITEDHEALTHCARE FOR PARSONS ELECTRIC | 4589800% |  | DRV | VL | WF1730884 | Elec | BUY | ANSI 49 | 4600800% | 17 | 4587600% | 4588800% | 4588900% | FALSE | Aug-2025 | 5 | 9 | 10 | 1 | LATE | LATE | ON TIME BY ENG |  | C | -8 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 17 | 4588842% | 100%
PZ4 | 0051217009 | 000550 | 0051217009-000550 | HORIZON HEALTH - EMERGENCY POWER UPGRADE | 4591200% |  | JAM | FRC | WF1730741 | Elec | MAKE | ANSI 49 | 4575900% | 27 | 4587600% | 4588300% | 4588300% | FALSE | Aug-2025 | 10 | 6 | 6 | 0 | ON TIME | ON TIME | ON TIME BY ENG |  | C | -22 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4588607% | 100%
PZ4 | 0050753978 | 003800 | 0050753978-003800 | KAISER SAN JOSE MEDICAL CENTER HOSPITAL | 4589800% |  | ALT | HUP | WF1731450 | Elec | MAKE | ANSI 49 | 4620700% | 16 | 4587700% | 4588400% | 4588300% | FALSE | Aug-2025 | 5 | 6 | 5 | -1 | ON TIME | ON TIME | ON TIME BY ENG |  | C | -12 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4588707% | 100%
PZ4 | 0051072452 | 000020&000470 | 0051072452-000020&000470 | UNITEDHEALTHCARE FOR PARSONS ELECTRIC | 4589800% |  | DRV | VL | WF1731333 | Elec | BUY | ANSI 49 | 4600800% | 16 | 4587700% | 4588900% | 4588900% | FALSE | Aug-2025 | 5 | 9 | 9 | 0 | ON TIME | ON TIME | ON TIME BY ENG |  | C | -8 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 17 | 4588942% | 100%
PZ4 | 0051472151 | 000010 & 000020 | 0051472151-000010 & 000020 | SEA NEMA DOC1033717255 EQUIPOS ELECTRICO | 4591100% |  | OAC | ODE | WF1731525 | Elec | BUY | ANSI 49 | 4601000% | 25 | 4587700% | 4588900% | 4590200% | FALSE | Aug-2025 | 10 | 9 | 18 | 9 | LATE | LATE | ON TIME BY ENG |  | C | -8 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 17 | 4588942% | 100%
PZ4 | 0051306085 | 000310 | 0051306085 -000310 | CYRUSONE - CYRUSONE, INC | 4589100% |  | HMA | IGS | WF1731688 | Elec | BUY | ANSI 49 | 4578900% | 10 | 4587900% | 4589100% | 4588800% | FALSE | Aug-2025 | 5 | 10 | 7 | -3 | ON TIME | ON TIME | ON TIME BY ENG |  | C | -4 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 17 | 4589142% | 100%
PZ4 | 0051306085 | 000310 | 0051306085 -000310 | CYRUSONE - CYRUSONE, INC | 4589100% |  | HMA | IGS | WF1731689 | Elec | BUY | ANSI 49 | 4578900% | 10 | 4587900% | 4589100% | 4588800% | FALSE | Aug-2025 | 5 | 10 | 7 | -3 | ON TIME | ON TIME | ON TIME BY ENG |  | C | -4 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 17 | 4589142% | 100%
PZ4 | 0051199001 | 000010 | 0051199001-000010 | EC1&EC2&EC3 | 4587700% |  | ASP | AL | WF1732182 | Elec | BUY | RAL 7035 | 4598700% | -2 | 4588000% | 4589000% | 4588900% | FALSE | Aug-2025 | 5 | 9 | 8 | -1 | ON TIME | ON TIME | LATE BY ENG |  | C | 9 | IMPACTED |  |  | Closed | LATE | NA | 17 | 4589042% | 100%
PZ4 | 0050753978 | 003780 | 0050753978-003780 | KAISER SAN JOSE MEDICAL CENTER HOSPITAL | 4589800% |  | RAS | CML | WF1732336 | Elec | BUY | ANSI 49 | 4602600% | 15 | 4588000% | 4589000% | 4589600% | FALSE | Aug-2025 | 5 | 9 | 13 | 4 | LATE | LATE | ON TIME BY ENG |  | C | -3 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 17 | 4589042% | 100%
PZ4 | 0051515918 | 000010 | 0051515918-000010 | COLLEY MARKS | 4591200% |  | JAV | KGF | WF1732364 | Mech | MAKE | ANSI 49 | 4602100% | 25 | 4588000% | 4589000% | 4588800% | FALSE | Aug-2025 | 10 | 9 | 7 | -2 | ON TIME | ON TIME | ON TIME BY ENG |  | C | -19 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4589307% | 100%
PZ4 | 0051306085 | 000310 | 0051306085-000310 | CYRUSONE - CYRUSONE, INC | 4589100% |  | HMA | IGS | WF1732947 | Elec | BUY | ANSI 49 | 4578900% | 9 | 4588100% | 4589100% | 4588800% | FALSE | Aug-2025 | 5 | 9 | 6 | -3 | ON TIME | ON TIME | ON TIME BY ENG |  | C | -4 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 17 | 4589142% | 100%
PZ4 | 0050753978 | 003790 | 0050753978-003790 | KAISER SAN JOSE MEDICAL CENTER HOSPITAL | 4589800% |  | RAS | ODE | WF1733695 | Mech | MAKE | ANSI 49 | 4617700% | 13 | 4588200% | 4589000% | 4589000% | FALSE | Aug-2025 | 5 | 7 | 7 | 0 | ON TIME | ON TIME | ON TIME BY ENG |  | C | -7 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4589307% | 100%
PZ4 | 0050753978 | 003790 | 0050753978-003790 | KAISER SAN JOSE MEDICAL CENTER HOSPITAL | 4589800% |  | RAS | ODE | WF1733700 | Mech | MAKE | ANSI 49 | 4617700% | 13 | 4588200% | 4589400% | 4590100% | FALSE | Aug-2025 | 5 | 9 | 14 | 5 | LATE | LATE | ON TIME BY ENG |  | C | 2 | IMPACTED |  |  | Closed | LATE | NA | 18 | 4589707% | 100%
PZ4 | 0051472151 | 000010 & 000020 | 0051472151-000010 & 000020 | SEA NEMA DOC1033717255 EQUIPOS ELECTRICO | 4591100% |  | OAC | ODE | WF1733486 | Elec | MAKE | ANSI 49 | 4601000% | 22 | 4588200% | 4588900% | 4590900% | FALSE | Aug-2025 | 10 | 6 | 20 | 14 | LATE | LATE | ON TIME BY ENG |  | X | -3 | NOT IMPACTED |  | Oneshuttle barrier | Cancelled | ON TIME | NA | 0 | 4589207% | 0%
PZ4 | 0051139077 | 000030&000110&000290 | 0051139077-000030&000110&000290 | NORTHROP B307 3000 KVA SUBSTATIONS - PAL | 4589800% |  | AOB | OAL | WF1734669 | Elec | MAKE | ANSI 49 | 4611200% | 11 | 4588400% | 4589400% | 4591000% | FALSE | Aug-2025 | 5 | 7 | 19 | 12 | LATE | LATE | ON TIME BY ENG |  | C | 9 | IMPACTED |  |  | Closed | LATE | NA | 18 | 4589707% | 100%
PZ4 | 0050753978 | 003790 | 0050753978-003790 | KAISER SAN JOSE MEDICAL CENTER HOSPITAL | 4589800% |  | RAS | ODE | WF1734560 | Mech | BUY | ANSI 49 | 4617700% | 11 | 4588400% | 4589600% | 4590100% | FALSE | Aug-2025 | 5 | 9 | 12 | 3 | LATE | LATE | ON TIME BY ENG |  | C | 2 | IMPACTED |  |  | Closed | LATE | NA | 17 | 4589642% | 100%
PZ4 | 0050753978 | 003790 | 0050753978-003790 | KAISER SAN JOSE MEDICAL CENTER HOSPITAL | 4589800% |  | RAS | ODE | WF1734562 | Mech | MAKE | ANSI 49 | 4617700% | 11 | 4588400% | 4589600% | 4590200% | FALSE | Aug-2025 | 5 | 9 | 13 | 4 | LATE | LATE | ON TIME BY ENG |  | C | 3 | IMPACTED |  |  | Closed | LATE | NA | 18 | 4589907% | 100%
PZ4 | 0051139077 | 000030&000110&000290 | 0051139077-000030&000110&000290 | NORTHROP B307 3000 KVA SUBSTATIONS - PAL | 4589800% |  | AOB | OAL | WF1734673 | Elec | BUY | ANSI 49 | 4602600% | 11 | 4588400% | 4589600% | 4588800% | FALSE | Aug-2025 | 5 | 9 | 3 | -6 | ON TIME | ON TIME | ON TIME BY ENG |  | x | -9 | NOT IMPACTED |  | PN Active in plant | Cancelled | ON TIME | NA | 0 | 4589642% | 0%
PZ4 | 0051436816 | 000030 | 0051436816-000030 | SPACEX STARBASE GIGABAY UNIT SUBSTATIONS | 4601700% | 4601000% | DMA | KGF | WF1734559 | Elec | MAKE | RAL9003 | 4609800% | 96 | 4588400% | 4589100% | 4589100% | FALSE | Aug-2025 | 10 | 6 | 6 | 0 | ON TIME | ON TIME | ON TIME BY ENG |  | C | -83 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4589407% | 100%
PZ4 | 0051139077 | 000030&000110&000290 | 0051139077-000030&000110&000290 | NORTHROP B307 3000 KVA SUBSTATIONS - PAL | 4589800% |  | AOB | OAL | WF1735314 | Mech | MAKE | ANSI 49 | 4611200% | 10 | 4588700% | 4589400% | 4589400% | FALSE | Aug-2025 | 5 | 6 | 6 | 0 | ON TIME | ON TIME | ON TIME BY ENG |  | C | -5 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4589707% | 100%
PZ4 | 0051027340 | 000100 | 0051027340-000100 | PSTV CC NORMAL GEAR | 4589800% |  | MGL | FRC | WF1735409 | Mech | MAKE | ANSI 49 | 4602100% | 10 | 4588700% | 4589500% | 4589900% | FALSE | Aug-2025 | 5 | 7 | 10 | 3 | LATE | LATE | ON TIME BY ENG |  | C | 1 | IMPACTED |  |  | Closed | LATE | NA | 18 | 4589807% | 100%
PZ4 | 0051139077 | 000030&000110&000290 | 0051139077-000030&000110&000290 | NORTHROP B307 3000 KVA SUBSTATIONS - PAL | 4589800% |  | AOB | OAL | WF1735305 | Mech | BUY | ANSI 49 | 4602600% | 10 | 4588700% | 4589700% | 4589700% | FALSE | Aug-2025 | 5 | 9 | 9 | 0 | ON TIME | ON TIME | ON TIME BY ENG |  | C | -2 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 17 | 4589742% | 100%
PZ4 | 0051027340 | 000100 | 0051027340-000100 | PSTV CC NORMAL GEAR | 4589800% |  | MGL | FRC | WF1735363 | Mech | BUY | ANSI 49 | 4602100% | 10 | 4588700% | 4589700% | 4589800% | FALSE | Aug-2025 | 5 | 9 | 10 | 1 | LATE | LATE | ON TIME BY ENG |  | C | 1 | IMPACTED |  |  | Closed | LATE | NA | 17 | 4589742% | 100%
PZ4 | 0050753978 | 003780 | 0050753978-003780 | KAISER SAN JOSE MEDICAL CENTER HOSPITAL | 4589800% |  | RAS | CML | WF1735982 | Mech | MAKE | ANSI 49 | 4602600% | 9 | 4588800% | 4589500% | 4589900% | FALSE | Aug-2025 | 5 | 6 | 9 | 3 | LATE | LATE | ON TIME BY ENG |  | C | 1 | IMPACTED |  |  | Closed | LATE | NA | 18 | 4589807% | 100%
PZ4 | 0050753978 | 003790 | 0050753978-003790 | KAISER SAN JOSE MEDICAL CENTER HOSPITAL | 4589800% |  | RAS | ODE | WF1735821 | Mech | MAKE | ANSI 49 | 4617700% | 9 | 4588800% | 4589500% | 4589400% | FALSE | Aug-2025 | 5 | 6 | 5 | -1 | ON TIME | ON TIME | ON TIME BY ENG |  | C | -5 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4589807% | 100%
PZ4 | 0051359498 | 000080 | 0051359498-000080 | KSFB PROPERY IMPROVEMENTS PHASE 1 STATE | 4589800% |  | JRC | RCI | WF1735924 | Mech | MAKE | ANSI 49 | 4602100% | 9 | 4588800% | 4589500% | 4589400% | FALSE | Aug-2025 | 5 | 6 | 5 | -1 | ON TIME | ON TIME | ON TIME BY ENG |  | C | -5 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4589807% | 100%
PZ4 | 0051139077 | 000030&000110&000290 | 0051139077-000030&000110&000290 | NORTHROP B307 3000 KVA SUBSTATIONS - PAL | 4589800% |  | AOB | OAL | WF1735914 | Elec | MAKE | ANSI 49 | 4611200% | 9 | 4588800% | 4589500% | 4589500% | FALSE | Aug-2025 | 5 | 6 | 6 | 0 | ON TIME | ON TIME | ON TIME BY ENG |  | C | -4 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4589807% | 100%
PZ4 | 0051436816 | 000030 | 0051436816-000030 | SPACEX STARBASE GIGABAY UNIT SUBSTATIONS | 4601700% | 4601000% | DMA | KGF | WF1735912 | Elec | MAKE | RAL9003 | 4609800% | 94 | 4588800% | 4589500% | 4589400% | FALSE | Aug-2025 | 10 | 6 | 5 | -1 | ON TIME | ON TIME | ON TIME BY ENG |  | C | -82 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4589807% | 100%
PZ4 | 0050847146 | 000200 | 0050847146-000200 | M003 REPLACE ELECTRICAL SUBSTATION 3C | 4589500% |  | ASP | DPM | WF1736534 | Elec | BUY | ANSI 49 | 4588900% | 5 | 4588900% | 4590100% | 4589800% | FALSE | Aug-2025 | 5 | 9 | 8 | -1 | ON TIME | ON TIME | ON TIME BY ENG |  | C | 4 | IMPACTED |  |  | Closed | LATE | NA | 17 | 4590142% | 100%
PZ4 | 0051072452 | 000020 | 0051072452-000020 | UNITEDHEALTHCARE FOR PARSONS ELECTRIC | 4589800% |  | DRV | VL | WF1736745 | Mech | MAKE | ANSI 49 | 4600800% | 8 | 4588900% | 4589800% | 4590100% | FALSE | Aug-2025 | 5 | 8 | 9 | 1 | LATE | LATE | ON TIME BY ENG |  | C | 2 | IMPACTED |  |  | Closed | LATE | NA | 18 | 4590107% | 100%
PZ4 | 0051229942 | 000120 | 0051229942-000120 | MICRON ID1 - PROJECT OPAL - WSP - BLDG B | 4580300% |  | MGL | AL | WF1737060 | Elec | BUY | ANSI 49 | 4588800% | -64 | 4589000% | 4590200% | 4590300% | FALSE | Aug-2025 | 5 | 9 | 10 | 1 | LATE | LATE | LATE BY ENG |  | C | 73 | IMPACTED |  |  | Closed | LATE | NA | 17 | 4590242% | 100%
PZ4 | 0051359498 | 000080 | 0051359498-000080 | KSFB PROPERY IMPROVEMENTS PHASE 1 STATE | 4589800% |  | JRC | RCI | WF1737041 | Elec | MAKE | ANSI 49 | 4602100% | 7 | 4589000% | 4589700% | 4589700% | FALSE | Aug-2025 | 5 | 6 | 6 | 0 | ON TIME | ON TIME | ON TIME BY ENG |  | C | -2 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4590007% | 100%
PZ4 | 0051072452 | 000020 | 0051072452-000020 | UNITEDHEALTHCARE FOR PARSONS ELECTRIC | 4589800% |  | DRV | VL | WF1737190 | Mech | MAKE | ANSI 49 | 4600800% | 7 | 4589000% | 4589700% | 4590100% | FALSE | Aug-2025 | 5 | 6 | 8 | 2 | LATE | LATE | ON TIME BY ENG |  | C | 2 | IMPACTED |  |  | Closed | LATE | NA | 18 | 4590007% | 100%
PZ4 | 0051072452 | 000020 | 0051072452-000020 | UNITEDHEALTHCARE FOR PARSONS ELECTRIC | 4589800% |  | DRV | VL | WF1737167 | Mech | MAKE | ANSI 49 | 4600800% | 7 | 4589000% | 4589700% | 4591100% | FALSE | Aug-2025 | 5 | 6 | 16 | 10 | LATE | LATE | ON TIME BY ENG |  | C | 10 | IMPACTED |  |  | Closed | LATE | NA | 18 | 4590007% | 100%
PZ4 | 0051072452 | 000020 | 0051072452-000020 | UNITEDHEALTHCARE FOR PARSONS ELECTRIC | 4589800% |  | DRV | VL | WF1737304 | Mech | MAKE | ANSI 49 | 4600800% | 7 | 4589000% | 4589800% | 4589800% | FALSE | Aug-2025 | 5 | 7 | 7 | 0 | ON TIME | ON TIME | ON TIME BY ENG |  | C | 1 | IMPACTED |  |  | Closed | LATE | NA | 18 | 4590107% | 100%
PZ4 | 0051072452 | 000020 | 0051072452-000020 | UNITEDHEALTHCARE FOR PARSONS ELECTRIC | 4589800% |  | DRV | VL | WF1737145 | Mech | BUY | ANSI 49 | 4600800% | 7 | 4589000% | 4590200% | 4590300% | FALSE | Aug-2025 | 5 | 9 | 10 | 1 | LATE | LATE | ON TIME BY ENG |  | C | 4 | IMPACTED |  |  | Closed | LATE | NA | 17 | 4590242% | 100%
PZ4 | 0051072452 | 000470 | 0051072452-000470 | UNITEDHEALTHCARE FOR PARSONS ELECTRIC | 4589800% |  | DRV | IGS | WF1737633 | Mech | MAKE | ANSI 49 | 4600800% | 6 | 4589100% | 4589800% | 4589700% | FALSE | Aug-2025 | 5 | 6 | 5 | -1 | ON TIME | ON TIME | ON TIME BY ENG |  | C | -2 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4590107% | 100%
PZ4 | 0051072451 | 000150 | 0051072451-000150 | UNITEDHEALTHCARE FOR PARSONS ELECTRIC | 4589800% |  | DRV | IGS | WF1738333 | Mech | MAKE | ANSI 49 | 4600800% | 5 | 4589400% | 4590900% | 4590900% | FALSE | Aug-2025 | 5 | 12 | 12 | 0 | ON TIME | ON TIME | ON TIME BY ENG |  | C | 8 | IMPACTED |  |  | Closed | LATE | NA | 18 | 4591207% | 100%
PZ4 | 0051472151 | 000010 | 0051472151-000010 | SEA NEMA DOC1033717255 EQUIPOS ELECTRICO | 4591100% |  | OAC | ODE | WF1739566 | Mech | MAKE | ANSI 49 | 4601000% | 12 | 4589600% | 4590300% | 4591000% | FALSE | Aug-2025 | 10 | 6 | 11 | 5 | LATE | LATE | ON TIME BY ENG |  | C | -2 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4590607% | 100%
PZ4 | 0051461115 | 000030 | 0051461115-000030 | DENSO 203_ UNIT SUB #6 | 4593000% |  | UFA | RCI | WF1739687 | Elec | MAKE | ANSI 49 | 4601700% | 25 | 4589600% | 4590400% | 4590100% | FALSE | Aug-2025 | 5 | 7 | 4 | -3 | ON TIME | ON TIME | ON TIME BY ENG | Change Order | C | -21 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4590707% | 100%
PZ4 | 0051424832 | 000020 | 0051424832-000020 | SAPPI T103B SUBSTATION REPLACEMENT | 4593000% |  | JTV | CML | WF1739717 | Mech | MAKE | ANSI 49 | 4603700% | 25 | 4589600% | 4590500% | 4590200% | FALSE | Aug-2025 | 10 | 8 | 5 | -3 | ON TIME | ON TIME | ON TIME BY ENG |  | C | -20 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4590807% | 100%
PZ4 | 0051139077 | 000190 | 0051139077-000190 | SEA NEMA DOC1033717255 EQUIPOS ELECTRICO | 4589800% |  | OAC | ODE | WF1740256 | Mech | MAKE | ANSI 49 | 4611300% | 2 | 4589700% | 4590500% | 4590900% | FALSE | Aug-2025 | 5 | 7 | 9 | 2 | LATE | LATE | LATE BY ENG |  | C | 8 | IMPACTED |  |  | Closed | LATE | NA | 18 | 4590807% | 100%
PZ4 | 0051340498 | 000010 | 0051340498-000010 | AUS HYDRANT SYSTEM | 4591900% |  | ASP | RCI | WF1740199 | Elec | BUY | ANSI 49 | 4602100% | 17 | 4589700% | 4590900% | 4590900% | FALSE | Aug-2025 | 10 | 9 | 9 | 0 | ON TIME | ON TIME | ON TIME BY ENG |  | C | -8 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 17 | 4590942% | 100%
QED2 | SWBD | meta rsb #80 | SWBD-meta rsb #80 | meta rsb #80 | 4592600% |  | ALT | AL | WF1740203 | Elec | MAKE | ANSI 49 | NA | 22 | 4589700% | 4590400% | 4591000% | FALSE | Aug-2025 | 10 | 6 | 10 | 4 | LATE | LATE | ON TIME BY ENG |  | C | -12 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4590707% | 100%
QED2 | SWBD | meta rsb #80 | SWBD-meta rsb #80 | meta rsb #80 | 4592600% |  | ALT | AL | WF1740323 | Elec | MAKE | ANSI 49 | NA | 22 | 4589700% | 4590800% | 4592700% | FALSE | Aug-2025 | 10 | 8 | 21 | 13 | LATE | LATE | ON TIME BY ENG |  | C | 1 | IMPACTED |  |  | Closed | LATE | NA | 18 | 4591107% | 100%
QED2 | SWBD | meta rsb #80 | SWBD-meta rsb #80 | meta rsb #80 | 4592600% |  | ALT | AL | WF1740322 | Elec | MAKE | ANSI 49 | NA | 22 | 4589700% | 4590800% | 4590800% | FALSE | Aug-2025 | 10 | 8 | 8 | 0 | ON TIME | ON TIME | ON TIME BY ENG |  | C | -14 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4591107% | 100%
QED2 | SWBD | meta rsb #80 | SWBD-meta rsb #80 | meta rsb #80 | 4592600% |  | ALT | AL | WF1740321 | Elec | MAKE | ANSI 49 | NA | 22 | 4589700% | 4590800% | 4592400% | FALSE | Aug-2025 | 10 | 8 | 19 | 11 | LATE | LATE | ON TIME BY ENG |  | C | -3 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4591107% | 100%
QED2 | SWBD | meta rsb #80 | SWBD-meta rsb #80 | meta rsb #80 | 4592600% |  | ALT | AL | WF1740325 | Elec | MAKE | ANSI 49 | NA | 22 | 4589700% | 4590800% | 4591300% | FALSE | Aug-2025 | 10 | 8 | 12 | 4 | LATE | LATE | ON TIME BY ENG |  | C | -9 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4591107% | 100%
QED2 | SWBD | meta rsb #80 | SWBD-meta rsb #80 | meta rsb #80 | 4592600% |  | ALT | AL | WF1740324 | Elec | MAKE | ANSI 49 | NA | 22 | 4589700% | 4590800% | 4592000% | FALSE | Aug-2025 | 10 | 8 | 16 | 8 | LATE | LATE | ON TIME BY ENG |  | C | -5 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4591107% | 100%
QED2 | SWBD | meta rsb #80 | SWBD-meta rsb #80 | meta rsb #80 | 4592600% |  | ALT | AL | WF1740319 | Elec | BUY | ANSI 49 | NA | 22 | 4589700% | 4591100% | 4591100% | FALSE | Aug-2025 | 10 | 11 | 11 | 0 | ON TIME | ON TIME | ON TIME BY ENG |  | C | -11 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 17 | 4591142% | 100%
PZ4 | 0051436816 | 000130 | 0051436816-000130 | SPACEX STARBASE GIGABAY UNIT SUBSTATIONS | 4601700% | 4601000% | DMA | KGF | WF1740823 | Mech | MAKE | RAL9003 | 4602100% | 86 | 4589800% | 4590500% | 4591100% | FALSE | Aug-2025 | 10 | 6 | 10 | 4 | LATE | LATE | ON TIME BY ENG |  | C | -69 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4590807% | 100%
PZ4 | 0051472151 | 000020 | 0051472151-000020 | SEA NEMA DOC1033717255 EQUIPOS ELECTRICO | 4589800% |  | OAC | OAL | WF1741470 | Mech | MAKE | ANSI 49 | 4601000% | -2 | 4590100% | 4590800% | 4591200% | FALSE | Sep-2025 | 5 | 6 | 10 | 4 | LATE | LATE | LATE BY ENG |  | C | 11 | IMPACTED |  |  | Closed | LATE | NA | 18 | 4591107% | 100%
PZ4 | 0051472151 | 000020 | 0051472151-000020 | NORTHROP B307 3000 KVA SUBSTATIONS - PAL | 4589800% |  | AOB | OAL | WF1741474 | Mech | BUY | ANSI 49 | 4590500% | -2 | 4590100% | 4591100% | 4590500% | FALSE | Sep-2025 | 5 | 9 | 5 | -4 | ON TIME | ON TIME | LATE BY ENG |  | X | 6 | IMPACTED |  | PN Active in US23 | Cancelled | LATE | NA | 0 | 4591142% | 0%
PZ4 | 0051536680 | 000150 | 0051536680-000150 | UNITEDHEALTH GROUP CUL PROJECT, CHASKA, | 4590500% |  | DRV | IGS | WF1741660 | Mech | MAKE | ANSI 49 | 4602100% | 5 | 4590100% | 4591000% | 4591600% | FALSE | Sep-2025 | 10 | 8 | 11 | 3 | LATE | LATE | LATE BY ENG |  | C | 7 | IMPACTED |  |  | Closed | LATE | NA | 18 | 4591307% | 100%
PZ4 | 0050988425 | 001260 | 0050988425-001260 | DC TILLMAN | 4591200% |  | KYC | OAL | WF1741546 | Elec | BUY | ANSI 49 | 4597900% | 10 | 4590100% | 4591100% | 4591500% | FALSE | Sep-2025 | 5 | 9 | 11 | 2 | LATE | LATE | ON TIME BY ENG |  | C | 2 | IMPACTED |  |  | Closed | LATE | NA | 17 | 4591142% | 100%
QED2 | SWBD | META QED2 | SWBD-META QED2 | META QED2 | 4592600% |  | ALT | AL | WF1741521 | Elec | BUY | ANSI 49 | NA | 20 | 4590100% | 4591100% | 4591000% | FALSE | Sep-2025 | 10 | 9 | 8 | -1 | ON TIME | ON TIME | ON TIME BY ENG |  | C | -12 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 17 | 4591142% | 100%
PZ4 | 0051378345 | 000010 | 0051378345-000010 | CUMMINS POWER GENERATION DOCK DOORS | 4595400% |  | HMA | HUP | WF1741537 | Elec | MAKE | ANSI 49 | 4611500% | 40 | 4590100% | 4590800% | 4592200% | FALSE | Sep-2025 | 10 | 6 | 15 | 9 | LATE | LATE | ON TIME BY ENG |  | C | -25 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4591107% | 100%
PZ4 | 0051378345 | 000010 | 0051378345-000010 | EOEM-CUMMINS - USCG RIO BAYAMON | 4595400% |  | HMA | OAL | WF1741558 | Elec | MAKE | ANSI 61 | 4608500% | 40 | 4590100% | 4590800% | 4590500% | FALSE | Sep-2025 | 10 | 6 | 5 | -1 | ON TIME | ON TIME | ON TIME BY ENG |  | C | -35 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4591107% | 100%
QED2 | SWBD | meta rsb #80 | SWBD-meta rsb #80 | meta rsb #80 | 4592600% |  | ALT | AL | WF1742143 | Elec | BUY | ANSI 49 | NA | 19 | 4590200% | 4591200% | 4591800% | FALSE | Sep-2025 | 10 | 9 | 12 | 3 | LATE | LATE | ON TIME BY ENG |  | C | -7 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 17 | 4591242% | 100%
PZ4 | 0051004478 | 000010 | 0051004478-000010 | BEACON HEALTH ES-43461 | 4581300% |  | DMA | OAL | WF1742958 | Elec | BUY | ANSI 49 | 4593900% | -65 | 4590300% | 4591500% | 4591000% | FALSE | Sep-2025 | 5 | 9 | 6 | -3 | ON TIME | ON TIME | LATE BY ENG |  | C | 70 | IMPACTED |  |  | Closed | LATE | NA | 17 | 4591542% | 100%
PZ4 | 0051306085 | 000300 | 0051306085-000300 | CYRUSONE - CYRUSONE, INC | 4591000% |  | HMA | IGS | WF1742802 | Elec | BUY | ANSI 49 | 4578900% | 6 | 4590300% | 4591500% | 4590900% | FALSE | Sep-2025 | 5 | 9 | 5 | -4 | ON TIME | ON TIME | ON TIME BY ENG |  | C | -2 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 17 | 4591542% | 100%
PZ4 | 0051072452 | 000020 | 0051072452-000020 | UNITEDHEALTHCARE FOR PARSONS ELECTRIC | 4589800% |  | DRV | VL | WF1742903 | Elec | MAKE | ANSI 49 | 4600800% | -4 | 4590300% | 4591000% | 4591500% | FALSE | Sep-2025 | 5 | 6 | 9 | 3 | LATE | LATE | LATE BY ENG |  | C | 12 | IMPACTED |  | Active in plant | Closed | LATE | NA | 18 | 4591307% | 100%
PZ4 | 0051086218 | 003900 | 0051086218-003900 | TALLAHASSEE POLICE DEPARTMENT HEADQUARTE | 4594600% |  | JTV |  | WF1742912 | Elec | MAKE | ANSI 49 | 4604900% | 32 | 4590300% | 4591000% | 4591500% | FALSE | Sep-2025 | 10 | 6 | 9 | 3 | LATE | LATE | ON TIME BY ENG |  | C | -23 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4591307% | 100%
PZ4 | 0051086218 | 003900 | 0051086218-003900 | TALLAHASSEE POLICE DEPARTMENT HEADQUARTE | 4594600% |  | JTV |  | WF1742935 | Elec | MAKE | ANSI 49 | 4604900% | 32 | 4590300% | 4591000% | 4591800% | FALSE | Sep-2025 | 10 | 6 | 11 | 5 | LATE | LATE | ON TIME BY ENG |  | C | -21 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4591307% | 100%
PZ4 | 0051086218 | 003900 | 0051086218-003900 | TALLAHASSEE POLICE DEPARTMENT HEADQUARTE | 4594600% |  | JTV |  | WF1742957 | Elec | MAKE | ANSI 49 | 4604900% | 32 | 4590300% | 4591000% | 4592300% | FALSE | Sep-2025 | 10 | 6 | 14 | 8 | LATE | LATE | ON TIME BY ENG |  | C | -18 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4591307% | 100%
PZ4 | 0051086218 | 003900 | 0051086218-003900 | TALLAHASSEE POLICE DEPARTMENT HEADQUARTE | 4594600% |  | JTV |  | WF1742985 | Elec | MAKE | ANSI 49 | 4604900% | 32 | 4590300% | 4591000% | 4592300% | FALSE | Sep-2025 | 10 | 6 | 14 | 8 | LATE | LATE | ON TIME BY ENG |  | C | -18 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4591307% | 100%
PZ4 | 0051086218 | 003900 | 0051086218-003900 | TALLAHASSEE POLICE DEPARTMENT HEADQUARTE | 4594600% |  | JTV |  | WF1742965 | Elec | BUY | ANSI 49 | 4604900% | 32 | 4590300% | 4591500% | 4591100% | FALSE | Sep-2025 | 10 | 9 | 7 | -2 | ON TIME | ON TIME | ON TIME BY ENG |  | C | -25 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 17 | 4591542% | 100%
PZ4 | 0051436816 | 000030 | 0051436816-000030 | SPACEX STARBASE GIGABAY UNIT SUBSTATIONS | 4601700% | 4601000% | DMA | KGF | WF1743044 | Mech | MAKE | RAL9003 | 4609800% | 83 | 4590300% | 4591100% | 4591800% | FALSE | Sep-2025 | 10 | 7 | 11 | 4 | LATE | LATE | ON TIME BY ENG |  | C | -65 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4591407% | 100%
PZ4 | 0051536680 | 000150 | 0051536680-000150 | UNITEDHEALTH GROUP CUL PROJECT, CHASKA, | 4590500% |  | DRV | IGS | WF1743659 | Mech | BUY | ANSI 49 | 4600800% | 2 | 4590400% | 4591600% | 4591900% | FALSE | Sep-2025 | 10 | 9 | 11 | 2 | LATE | LATE | LATE BY ENG |  | C | 10 | IMPACTED |  |  | Closed | LATE | NA | 17 | 4591642% | 100%
PZ4 | 0051217009 | 000550 | 0051217009-000550 | HORIZON HEALTH - EMERGENCY POWER UPGRADE | 4591200% |  | JAM | FRC | WF1743744 | Mech | MAKE | ANSI 49 | 4575900% | 7 | 4590400% | 4591200% | 4592300% | FALSE | Sep-2025 | 10 | 7 | 13 | 6 | LATE | LATE | LATE BY ENG |  | C | 7 | IMPACTED |  |  | Closed | LATE | NA | 18 | 4591507% | 100%
PZ4 | 0051072452 | 000020 | 0051072452-000020 | SPACEX STARBASE GIGABAY UNIT SUBSTATIONS | 4593000% |  | DEV | VL | WF1743800 | Mech | MAKE | RAL9003 | 4600800% | 19 | 4590400% | 4591200% | 4591800% | FALSE | Sep-2025 | 10 | 7 | 10 | 3 | LATE | LATE | ON TIME BY ENG |  | C | -9 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4591507% | 100%
PZ4 | 0051072452 | 000020 | 0051072452-000020 | SPACEX STARBASE GIGABAY UNIT SUBSTATIONS | 4593000% |  | DEV | VL | WF1743774 | Mech | MAKE | RAL9003 | 4600800% | 19 | 4590400% | 4591200% | 4591800% | FALSE | Sep-2025 | 10 | 7 | 10 | 3 | LATE | LATE | ON TIME BY ENG |  | C | -9 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4591507% | 100%
PZ4 | 0051436816 | 000080 | 0051436816-000080 | SPACEX STARBASE GIGABAY UNIT SUBSTATIONS | 4593000% |  | DEV | VL | WF1743757 | Mech | MAKE | RAL9003 | 4602100% | 19 | 4590400% | 4591200% | 4591900% | FALSE | Sep-2025 | 10 | 7 | 11 | 4 | LATE | LATE | ON TIME BY ENG |  | C | -8 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4591507% | 100%
PZ4 | 0051436816 | 000080 | 0051436816-000080 | SPACEX STARBASE GIGABAY UNIT SUBSTATIONS | 4593000% |  | DEV | VL | WF1743745 | Mech | MAKE | RAL9003 | 4602100% | 19 | 4590400% | 4591200% | 4591900% | FALSE | Sep-2025 | 10 | 7 | 11 | 4 | LATE | LATE | ON TIME BY ENG |  | C | -8 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4591507% | 100%
PZ4 | 0051004478 | 000010 | 0051004478-000010 | BEACON HEALTH ES-43461 | 4581300% |  | DMA | OAL | WF1744143 | Mech | MAKE | ANSI 49 | 4593900% | -67 | 4590500% | 4591200% | 4591700% | FALSE | Sep-2025 | 5 | 6 | 8 | 2 | LATE | LATE | LATE BY ENG |  | C | 74 | IMPACTED |  |  | Closed | LATE | NA | 18 | 4591507% | 100%
PZ4 | 0051340498 | 000010 | 0051340498-000010 | AUS HYDRANT SYSTEM | 4591900% |  | ASP | RCI | WF1744180 | Mech | MAKE | ANSI 49 | 4602100% | 11 | 4590500% | 4591200% | 4591800% | FALSE | Sep-2025 | 10 | 6 | 9 | 3 | LATE | LATE | ON TIME BY ENG |  | C | -2 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4591507% | 100%
QED2 | SWBD | switchboard f2.0 | SWBD-switchboard f2.0 | switchboard f2.0 | 4592600% |  | ALT | AL | WF1744192 | Elec | MAKE | ANSI 49 | NA | 16 | 4590500% | 4591200% | 4592300% | FALSE | Sep-2025 | 10 | 6 | 12 | 6 | LATE | LATE | ON TIME BY ENG |  | C | -4 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4591507% | 100%
QED2 | SWBD | switchboard f2.0 | SWBD-switchboard f2.0 | switchboard f2.0 | 4592600% |  | ALT | AL | WF1744181 | Elec | MAKE | ANSI 49 | NA | 16 | 4590500% | 4591200% | 4592400% | FALSE | Sep-2025 | 10 | 6 | 13 | 7 | LATE | LATE | ON TIME BY ENG |  | C | -3 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4591507% | 100%
QED2 | SWBD | switchboard f2.0 | SWBD-switchboard f2.0 | switchboard f2.0 | 4592600% |  | ALT | AL | WF1744169 | Elec | MAKE | ANSI 49 | NA | 16 | 4590500% | 4591200% | 4592400% | FALSE | Sep-2025 | 10 | 6 | 13 | 7 | LATE | LATE | ON TIME BY ENG |  | C | -3 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4591507% | 100%
QED2 | SWBD | switchboard f2.0 | SWBD-switchboard f2.0 | switchboard f2.0 | 4592600% |  | ALT | AL | WF1744166 | Elec | MAKE | ANSI 49 | NA | 16 | 4590500% | 4591200% | 4592400% | FALSE | Sep-2025 | 10 | 6 | 13 | 7 | LATE | LATE | ON TIME BY ENG |  | C | -3 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4591507% | 100%
QED2 | SWBD | switchboard f2.0 | SWBD-switchboard f2.0 | switchboard f2.0 | 4592600% |  | ALT | AL | WF1744145 | Elec | MAKE | ANSI 49 | NA | 16 | 4590500% | 4591200% | 4592500% | FALSE | Sep-2025 | 10 | 6 | 14 | 8 | LATE | LATE | ON TIME BY ENG |  | C | -2 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4591507% | 100%
QED2 | SWBD | switchboard f2.0 | SWBD-switchboard f2.0 | switchboard f2.0 | 4592600% |  | ALT | AL | WF1744219 | Elec | MAKE | ANSI 49 | NA | 16 | 4590500% | 4591200% | 4591200% | FALSE | Sep-2025 | 10 | 6 | 6 | 0 | ON TIME | ON TIME | ON TIME BY ENG |  | C | -10 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4591507% | 100%
QED2 | SWBD | switchboard f2.0 | SWBD-switchboard f2.0 | switchboard f2.0 | 4592600% |  | ALT | AL | WF1744209 | Elec | MAKE | ANSI 49 | NA | 16 | 4590500% | 4591200% | 4592500% | FALSE | Sep-2025 | 10 | 6 | 14 | 8 | LATE | LATE | ON TIME BY ENG |  | C | -2 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4591507% | 100%
QED2 | SWBD | switchboard f2.0 | SWBD-switchboard f2.0 | switchboard f2.0 | 4592600% |  | ALT | AL | WF1744206 | Elec | MAKE | ANSI 49 | NA | 16 | 4590500% | 4591200% | 4592500% | FALSE | Sep-2025 | 10 | 6 | 14 | 8 | LATE | LATE | ON TIME BY ENG |  | C | -2 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4591507% | 100%
QED2 | SWBD | switchboard f2.0 | SWBD-switchboard f2.0 | switchboard f2.0 | 4592600% |  | ALT | AL | WF1744203 | Elec | MAKE | ANSI 49 | NA | 16 | 4590500% | 4591200% | 4592400% | FALSE | Sep-2025 | 10 | 6 | 13 | 7 | LATE | LATE | ON TIME BY ENG |  | C | -3 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4591507% | 100%
QED2 | SWBD | switchboard f2.0 | SWBD-switchboard f2.0 | switchboard f2.0 | 4592600% |  | ALT | AL | WF1744245 | Elec | MAKE | ANSI 49 | NA | 16 | 4590500% | 4591500% | 4592200% | FALSE | Sep-2025 | 10 | 7 | 11 | 4 | LATE | LATE | ON TIME BY ENG |  | C | -5 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4591807% | 100%
QED2 | SWBD | switchboard f2.0 | SWBD-switchboard f2.0 | switchboard f2.0 | 4592600% |  | ALT | AL | WF1744236 | Elec | MAKE | ANSI 49 | NA | 16 | 4590500% | 4591500% | 4592700% | FALSE | Sep-2025 | 10 | 7 | 15 | 8 | LATE | LATE | ON TIME BY ENG |  | C | 1 | IMPACTED |  |  | Closed | LATE | NA | 18 | 4591807% | 100%
QED2 | SWBD | switchboard f2.0 | SWBD-switchboard f2.0 | switchboard f2.0 | 4592600% |  | ALT | AL | WF1744229 | Elec | MAKE | ANSI 49 | NA | 16 | 4590500% | 4591500% | 4592500% | FALSE | Sep-2025 | 10 | 7 | 14 | 7 | LATE | LATE | ON TIME BY ENG |  | C | -2 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4591807% | 100%
QED2 | SWBD | meta rsb Proyecto META SWB | SWBD-meta rsb Proyecto META SWB | meta rsb Proyecto META SWB | 4592600% |  | ALT | AL | WF1744137 | Elec | BUY | ANSI 49 | NA | 16 | 4590500% | 4591700% | 4592500% | FALSE | Sep-2025 | 10 | 9 | 14 | 5 | LATE | LATE | ON TIME BY ENG |  | C | -2 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 17 | 4591742% | 100%
QED2 | SWBD | meta rsb Proyecto META SWB | SWBD-meta rsb Proyecto META SWB | meta rsb Proyecto META SWB | 4592600% |  | ALT | AL | WF1744136 | Elec | BUY | ANSI 49 | NA | 16 | 4590500% | 4591700% | 4592300% | FALSE | Sep-2025 | 10 | 9 | 12 | 3 | LATE | LATE | ON TIME BY ENG |  | C | -4 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 17 | 4591742% | 100%
PZ4 | 0051436816 | 000080 | 0051436816-000080 | SPACEX STARBASE GIGABAY UNIT SUBSTATIONS | 4593000% |  | DEV | VL | WF1744149 | Mech | MAKE | RAL9003 | 4602100% | 18 | 4590500% | 4591200% | 4591900% | FALSE | Sep-2025 | 10 | 6 | 10 | 4 | LATE | LATE | ON TIME BY ENG |  | C | -8 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4591507% | 100%
PZ4 | 0051536680 | 000150 | 0051536680-000150 | UNITEDHEALTH GROUP CUL PROJECT, CHASKA, | 4590500% |  | DRV | IGS | WF1745812 | Mech | MAKE | ANSI 49 | 4600800% | -3 | 4590900% | 4591600% | 4592000% | FALSE | Sep-2025 | 10 | 6 | 8 | 2 | LATE | LATE | LATE BY ENG |  | C | 10 | IMPACTED |  |  | Closed | LATE | NA | 18 | 4591907% | 100%
PZ4 | 0051472151 | 000010 & 000020 | 0051472151-000010 & 000020 | SEA NEMA DOC1033717255 EQUIPOS ELECTRICO | 4591100% |  | OAC | ODE | WF1745721 | Elec | MAKE | ANSI 49 | 4601000% | 3 | 4590900% | 4591600% | 4591200% | FALSE | Sep-2025 | 10 | 6 | 4 | -2 | ON TIME | ON TIME | LATE BY ENG |  | C | 2 | IMPACTED |  |  | Closed | LATE | NA | 18 | 4591907% | 100%
QED2 | SWBD | switchboard f2.0 | SWBD-switchboard f2.0 | switchboard f2.0 | 4592600% |  | ALT | AL | WF1745785 | Elec | MAKE | ANSI 49 | NA | 14 | 4590900% | 4591600% | 4592700% | FALSE | Sep-2025 | 10 | 6 | 13 | 7 | LATE | LATE | ON TIME BY ENG |  | C | 1 | IMPACTED |  |  | Closed | LATE | NA | 18 | 4591907% | 100%
QED2 | SWBD | switchboard f2.0 | SWBD-switchboard f2.0 | switchboard f2.0 | 4592600% |  | ALT | AL | WF1745767 | Elec | MAKE | ANSI 49 | NA | 14 | 4590900% | 4591600% | 4592400% | FALSE | Sep-2025 | 10 | 6 | 11 | 5 | LATE | LATE | ON TIME BY ENG |  | C | -3 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4591907% | 100%
QED2 | SWBD | META 2.0 | SWBD-META 2.0 | META 2.0 | 4592600% |  | ALT | AL | WF1745908 | Elec | MAKE | ANSI 49 | NA | 14 | 4590900% | 4591800% | 4592700% | FALSE | Sep-2025 | 10 | 8 | 13 | 5 | LATE | LATE | ON TIME BY ENG |  | C | 1 | IMPACTED |  |  | Closed | LATE | NA | 18 | 4592107% | 100%
QED2 | SWBD | switchboard f2.0 | SWBD-switchboard f2.0 | switchboard f2.0 | 4592600% |  | ALT | AL | WF1745782 | Elec | BUY | ANSI 49 | NA | 14 | 4590900% | 4591900% | 4591800% | FALSE | Sep-2025 | 10 | 9 | 7 | -2 | ON TIME | ON TIME | ON TIME BY ENG |  | C | -7 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 17 | 4591942% | 100%
PZ4 | 0051199001 | 000010 | 0051199001-000010 | EC1&EC2&EC3 | 4593600% |  | ASP | AL | WF1746349 | Elec | BUY | RAL 7035 | 4598700% | 19 | 4591000% | 4592200% | 4592200% | FALSE | Sep-2025 | 5 | 9 | 8 | -1 | ON TIME | ON TIME | ON TIME BY ENG |  | C | -11 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 17 | 4592242% | 100%
QED2 | SWBD | meta 2.0 | SWBD-meta 2.0 | meta 2.0 | 4592600% |  | ALT | AL | WF1746541 | Elec | BUY | ANSI 49 | NA | 13 | 4591000% | 4592200% | 4592700% | FALSE | Sep-2025 | 10 | 9 | 12 | 3 | LATE | LATE | ON TIME BY ENG |  | C | 1 | IMPACTED |  |  | Closed | LATE | NA | 17 | 4592242% | 100%
PZ4 | 0050754152 | 000090 | 0050754152-000090 | TOWER SEMICONDUCTOR - SAN ANTONIO - ALTE | 4583900% |  | DMA | LDT | WF1747019 | Mech | MAKE | ANSI 49 | 4592200% | -53 | 4591100% | 4591900% | 4591500% | FALSE | Sep-2025 | 5 | 7 | 3 | -4 | ON TIME | ON TIME | LATE BY ENG |  | C | 55 | IMPACTED |  |  | Closed | LATE | NA | 18 | 4592207% | 100%
PZ4 | 0051199001 | 000010 | 0051199001-000010 | EC1&EC2&EC3 | 4593600% |  | ASP | AL | WF1747868 | Elec | BUY | RAL 7035 | 4598700% | 17 | 4591200% | 4592600% | 4593100% | FALSE | Sep-2025 | 5 | 11 | 13 | 2 | LATE | LATE | ON TIME BY ENG | Supply asked for a spare | C | -4 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 17 | 4592642% | 100%
PZ4 | 0051306085 | 000300 | 0051306085-000300 | CYRUSONE - CYRUSONE, INC | 4591000% |  | HMA | IGS | WF1747814 | Elec | BUY | ANSI 49 | 4578900% | -3 | 4591200% | 4592500% | 4592500% | FALSE | Sep-2025 | 5 | 10 | 9 | -1 | ON TIME | ON TIME | LATE BY ENG |  | C | 11 | IMPACTED |  |  | Closed | LATE | NA | 17 | 4592542% | 100%
QED2 | SWBD | meta 2.0 | SWBD-meta 2.0 | meta 2.0 | 4592600% |  | ALT | AL | WF1747702 | Elec | MAKE | ANSI 49 | NA | 11 | 4591200% | 4592200% | 4591900% | FALSE | Sep-2025 | 10 | 7 | 5 | -2 | ON TIME | ON TIME | ON TIME BY ENG |  | C | -6 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4592507% | 100%
PZ4 | 0051442285 | 000110 | 0051442285-000110 | GIGABAY 15KV SUBSTATIONS REV3 STARBASE T | 4594500% |  | DMA | KGF | WF1747718 | Mech | MAKE | RAL9003 | 4600800% | 24 | 4591200% | 4592200% | 4591900% | FALSE | Sep-2025 | 10 | 7 | 5 | -2 | ON TIME | ON TIME | ON TIME BY ENG |  | C | -19 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4592507% | 100%
PZ4 | 0051424832 | 000020 | 0051424832-000020 | SAPPI T103B SUBSTATION REPLACEMENT | 4593000% |  | JTV | CML | WF1749894 | Elec | MAKE | ANSI 49 | 4603700% | 10 | 4591700% | 4592400% | 4592400% | FALSE | Sep-2025 | 10 | 6 | 6 | 0 | ON TIME | ON TIME | ON TIME BY ENG |  | C | -5 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4592707% | 100%
PZ4 | 0051424832 | 000020 | 0051424832-000020 | SAPPI T103B SUBSTATION REPLACEMENT | 4593000% |  | JTV | CML | WF1749895 | Elec | MAKE | ANSI 49 | 4603700% | 10 | 4591700% | 4592400% | 4592300% | FALSE | Sep-2025 | 10 | 6 | 5 | -1 | ON TIME | ON TIME | ON TIME BY ENG |  | C | -6 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4592707% | 100%
PZ4 | 0051086218 | 003900 | 0051086218-003900 | TALLAHASSEE POLICE DEPARTMENT HEADQUARTE | 4594600% |  | JTV |  | WF1749839 | Elec | MAKE | ANSI 49 | ON-HOLD | 22 | 4591700% | 4592400% | 4592700% | FALSE | Sep-2025 | 10 | 6 | 8 | 2 | LATE | LATE | ON TIME BY ENG |  | C | -14 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4592707% | 100%
PZ4 | 051576246 | 000020&30&40&50&60 | 051576246-000020&30&40&50&60 | AT&T 1420 BROADWAY STREET LUBBOCK TX | 4595400% |  | JAM | IGS | WF1749869 | Elec | BUY | ANSI 49 | 4605200% | 28 | 4591700% | 4592900% | 4593200% | FALSE | Sep-2025 | 10 | 9 | 12 | 3 | LATE | LATE | ON TIME BY ENG |  | C | -17 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 17 | 4592942% | 100%
PZ4 | 0051576246 | 000020&30&40&50&60 | 0051576246-000020&30&40&50&60 | AT&T 1420 BROADWAY STREET LUBBOCK TX | 4595400% |  | JAM | IGS | WF1749888 | Elec | BUY | ANSI 49 | 4605200% | 28 | 4591700% | 4592900% | 4591800% | FALSE | Sep-2025 | 10 | 9 | 2 | -7 | ON TIME | ON TIME | ON TIME BY ENG |  | X | -27 | NOT IMPACTED |  | PN IN OTHER WF | Cancelled | ON TIME | NA | 0 | 4592942% | 0%
PZ4 | 0051576246 | 000020&30&40&50&60 | 0051576246-000020&30&40&50&60 | AT&T 1420 BROADWAY STREET LUBBOCK TX | 4595400% |  | JAM | IGS | WF1750068 | Elec | BUY | ANSI 49 | 4605200% | 28 | 4591700% | 4592900% | 4591800% | FALSE | Sep-2025 | 5 | 9 | 2 | -7 | ON TIME | ON TIME | ON TIME BY ENG |  | x | -27 | NOT IMPACTED |  | Wrong template | Cancelled | ON TIME | NA | 0 | 4592942% | 0%
PZ4 | 0051576246 | 000020&30&40&50&60 | 0051576246-000020&30&40&50&60 | AT&T 1420 BROADWAY STREET LUBBOCK TX | 4595400% |  | JAM | IGS | WF1750094 | Elec | BUY | ANSI 49 | 4605200% | 28 | 4591700% | 4592900% | 4591800% | FALSE | Sep-2025 | 5 | 9 | 2 | -7 | ON TIME | ON TIME | ON TIME BY ENG |  | x | -27 | NOT IMPACTED |  | Wrong template | Cancelled | ON TIME | NA | 0 | 4592942% | 0%
QED2 | SWBD | meta rsb #80 | SWBD-meta rsb #80 | meta rsb #80 | 4592600% |  | ALT | AL | WF1750559 | Elec | BUY | ANSI 49 | NA | 7 | 4591800% | 4593000% | 4592700% | FALSE | Sep-2025 | 10 | 9 | 7 | -2 | ON TIME | ON TIME | LATE BY ENG |  | C | 1 | IMPACTED |  |  | Closed | LATE | NA | 17 | 4593042% | 100%
QED2 | SWBD | meta rsb #80 | SWBD-meta rsb #80 | meta rsb #80 | 4592600% |  | ALT | AL | WF1750577 | Elec | BUY | ANSI 49 | NA | 7 | 4591800% | 4593000% | 4592700% | FALSE | Sep-2025 | 10 | 9 | 7 | -2 | ON TIME | ON TIME | LATE BY ENG |  | C | 1 | IMPACTED |  |  | Closed | LATE | NA | 17 | 4593042% | 100%
QED2 | SWBD | meta rsb #80 | SWBD-meta rsb #80 | meta rsb #80 | 4592600% |  | ALT | AL | WF1750707 | Elec | BUY | ANSI 49 | NA | 7 | 4591800% | 4593000% | 4592400% | FALSE | Sep-2025 | 10 | 9 | 5 | -4 | ON TIME | ON TIME | LATE BY ENG |  | C | -3 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 17 | 4593042% | 100%
PZ4 | 0051442285 | 000070 | 0051442285-000070 | GIGABAY 15KV SUBSTATIONS REV3 STARBASE T | 4594500% |  | DEV | KGF | WF1750555 | Mech | MAKE | RAL9003 | 4600800% | 20 | 4591800% | 4592500% | 4593300% | FALSE | Sep-2025 | 10 | 6 | 12 | 6 | LATE | LATE | ON TIME BY ENG |  | C | -9 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4592807% | 100%
PZ4 | 0051442285 | 000070 | 0051442285-000070 | GIGABAY 15KV SUBSTATIONS REV3 STARBASE T | 4594500% |  | DEV | KGF | WF1750597 | Mech | MAKE | RAL9003 | 4600800% | 20 | 4591800% | 4592500% | 4593800% | FALSE | Sep-2025 | 10 | 6 | 15 | 9 | LATE | LATE | ON TIME BY ENG |  | C | -6 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4592807% | 100%
PZ4 | 0051442285 | 000070 | 0051442285-000070 | GIGABAY 15KV SUBSTATIONS REV3 STARBASE T | 4594500% |  | DEV | KGF | WF1750669 | Mech | BUY | RAL9003 | 4600800% | 20 | 4591800% | 4592500% | 4593200% | FALSE | Sep-2025 | 10 | 6 | 11 | 5 | LATE | LATE | ON TIME BY ENG |  | C | -10 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 17 | 4592542% | 100%
PZ4 | 0051442285 | 000070 | 0051442285-000070 | GIGABAY 15KV SUBSTATIONS REV3 STARBASE T | 4594500% |  | DEV | KGF | WF1751222 | Mech | MAKE | RAL9003 | 4600800% | 19 | 4591900% | 4592600% | 4592900% | FALSE | Sep-2025 | 10 | 6 | 7 | 1 | LATE | LATE | ON TIME BY ENG |  | C | -13 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4592907% | 100%
PZ4 | 0051442285 | 000070 | 0051442285-000070 | GIGABAY 15KV SUBSTATIONS REV3 STARBASE T | 4594500% |  | DEV | KGF | WF1751205 | Mech | MAKE | RAL9003 | 4600800% | 19 | 4591900% | 4592600% | 4594300% | FALSE | Sep-2025 | 10 | 6 | 17 | 11 | LATE | LATE | ON TIME BY ENG |  | C | -3 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4592907% | 100%
PZ4 | 0051442285 | 000070 | 0051442285-000070 | GIGABAY 15KV SUBSTATIONS REV3 STARBASE T | 4594500% |  | DEV | KGF | WF1751144 | Mech | MAKE | RAL9003 | 4600800% | 19 | 4591900% | 4592600% | 4594500% | FALSE | Sep-2025 | 10 | 6 | 19 | 13 | LATE | LATE | ON TIME BY ENG |  | C | 1 | IMPACTED |  |  | Closed | LATE | NA | 18 | 4592907% | 100%
PZ4 | 0051442285 | 000080 | 0051442285-000080 | GIGABAY 15KV SUBSTATIONS REV3 STARBASE T | 4594500% |  | DEV | KGF | WF1751204 | Mech | MAKE | RAL9003 | 4600800% | 19 | 4591900% | 4592600% | 4594500% | FALSE | Sep-2025 | 10 | 6 | 19 | 13 | LATE | LATE | ON TIME BY ENG |  | C | 1 | IMPACTED |  |  | Closed | LATE | NA | 18 | 4592907% | 100%
PZ4 | 0051442285 | 000070 | 0051442285-000070 | GIGABAY 15KV SUBSTATIONS REV3 STARBASE T | 4594500% |  | DEV | KGF | WF1751231 | Mech | MAKE | RAL9003 | 4600800% | 19 | 4591900% | 4592900% | 4594300% | FALSE | Sep-2025 | 10 | 7 | 17 | 10 | LATE | LATE | ON TIME BY ENG |  | C | -3 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4593207% | 100%
PZ4 | 0051442285 | 000070 | 0051442285-000070 | GIGABAY 15KV SUBSTATIONS REV3 STARBASE T | 4594500% |  | DEV | KGF | WF1751236 | Mech | MAKE | RAL9003 | 4600800% | 19 | 4591900% | 4592900% | 4594300% | FALSE | Sep-2025 | 10 | 7 | 17 | 10 | LATE | LATE | ON TIME BY ENG |  | C | -3 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4593207% | 100%
PZ4 | 0051442285 | 000070 | 0051442285-000070 | GIGABAY 15KV SUBSTATIONS REV3 STARBASE T | 4594500% |  | DEV | KGF | WF1751133 | Mech | BUY | RAL9003 | 4600800% | 19 | 4591900% | 4593100% | 4593200% | FALSE | Sep-2025 | 10 | 9 | 10 | 1 | LATE | LATE | ON TIME BY ENG |  | C | -10 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 17 | 4593142% | 100%
PZ4 | 0051576246 | 000020&30&40&50&60 | 0051576246-000020&30&40&50&60 | AT&T 1420 BROADWAY STREET LUBBOCK TX | 4595400% |  | JAM | IGS | WF1751246 | Elec | MAKE | ANSI 49 | 4605200% | 26 | 4591900% | 4592900% | 4595000% | FALSE | Sep-2025 | 10 | 7 | 22 | 15 | LATE | SUPER LATE | ON TIME BY ENG |  | C | -5 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4593207% | 100%
PZ4 | 051576246 | 000020&30&40&50&60 | 051576246-000020&30&40&50&60 | AT&T 1420 BROADWAY STREET LUBBOCK TX | 4595400% |  | JAM | IGS | WF1751267 | Elec | MAKE | ANSI 49 | 4603000% | 26 | 4591900% | 4592900% | 4595400% | FALSE | Sep-2025 | 10 | 7 | 26 | 19 | LATE | SUPER LATE | ON TIME BY ENG |  | C | 1 | IMPACTED |  |  | Closed | LATE | NA | 18 | 4593207% | 100%
PZ4 | 0051576246 | 000020&30&40&50&60 | 0051576246-000020&30&40&50&60 | AT&T 1420 BROADWAY STREET LUBBOCK TX | 4595400% |  | JAM | IGS | WF1751250 | Elec | MAKE | ANSI 49 | 4605200% | 26 | 4591900% | 4593000% | 4595000% | FALSE | Sep-2025 | 10 | 8 | 22 | 14 | LATE | LATE | ON TIME BY ENG |  | C | -5 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4593307% | 100%
PZ4 | 0051576246 | 000020&30&40&50&60 | 0051576246-000020&30&40&50&60 | AT&T 1420 BROADWAY STREET LUBBOCK TX | 4595400% |  | JAM | IGS | WF1751244 | Elec | BUY | ANSI 49 | 4605200% | 26 | 4591900% | 4593100% | 4594300% | FALSE | Sep-2025 | 10 | 9 | 17 | 8 | LATE | LATE | ON TIME BY ENG |  | C | -10 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 17 | 4593142% | 100%
PZ4 | 0051576246 | 000020&30&40&50&60 | 0051576246-000020&30&40&50&60 | AT&T 1420 BROADWAY STREET LUBBOCK TX | 4595400% |  | JAM | IGS | WF1751253 | Elec | MAKE | ANSI 49 | 4605200% | 26 | 4591900% | 4593100% | 4595100% | FALSE | Sep-2025 | 10 | 9 | 23 | 14 | LATE | LATE | ON TIME BY ENG |  | C | -4 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4593407% | 100%
PZ4 | 0051576246 | 000020&30&40&50&60 | 0051576246-000020&30&40&50&60 | AT&T 1420 BROADWAY STREET LUBBOCK TX | 4595400% |  | JAM | IGS | WF1751255 | Elec | MAKE | ANSI 49 | 4605200% | 26 | 4591900% | 4593300% | 4595200% | FALSE | Sep-2025 | 10 | 11 | 24 | 13 | LATE | LATE | ON TIME BY ENG |  | C | -3 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4593607% | 100%
PZ4 | 0051576246 | 000020&30&40&50&60 | 0051576246-000020&30&40&50&60 | AT&T 1420 BROADWAY STREET LUBBOCK TX | 4595400% |  | JAM | IGS | WF1751258 | Elec | MAKE | ANSI 49 | 4605200% | 26 | 4591900% | 4593400% | 4595200% | FALSE | Sep-2025 | 10 | 11 | 24 | 13 | LATE | LATE | ON TIME BY ENG |  | C | -3 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4593707% | 100%
PZ4 | 0051576246 | 000020&30&40&50&60 | 0051576246-000020&30&40&50&60 | AT&T 1420 BROADWAY STREET LUBBOCK TX | 4595400% |  | JAM | IGS | WF1751260 | Elec | MAKE | ANSI 49 | 4605200% | 26 | 4591900% | 4593500% | 4595300% | FALSE | Sep-2025 | 10 | 11 | 25 | 14 | LATE | LATE | ON TIME BY ENG |  | C | -2 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4593807% | 100%
PZ4 | 0051576246 | 000020&30&40&50&60 | 0051576246-000020&30&40&50&60 | AT&T 1420 BROADWAY STREET LUBBOCK TX | 4595400% |  | JAM | IGS | WF1751263 | Elec | MAKE | ANSI 49 | 4605200% | 26 | 4591900% | 4593600% | 4595300% | FALSE | Sep-2025 | 10 | 12 | 25 | 13 | LATE | LATE | ON TIME BY ENG |  | C | -2 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4593907% | 100%
PZ4 | 0051576246 | 000020&30&40&50&60 | 0051576246-000020&30&40&50&60 | AT&T 1420 BROADWAY STREET LUBBOCK TX | 4595400% |  | JAM | IGS | WF1752607 | Elec | BUY | ANSI 49 | 4605200% | 26 | 4591900% | 4593700% | 4595200% | FALSE | Sep-2025 | 10 | 13 | 24 | 11 | LATE | LATE | ON TIME BY ENG |  | C | -3 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 17 | 4593742% | 100%
PZ4 | 0051576246 | 000020&30&40&50&60 | 0051576246-000020&30&40&50&60 | AT&T 1420 BROADWAY STREET LUBBOCK TX | 4595400% |  | JAM | IGS | WF1751270 | Elec | MAKE | ANSI 49 | 4605200% | 26 | 4591900% | 4593800% | 4593200% | FALSE | Sep-2025 | 10 | 14 | 10 | -4 | ON TIME | ON TIME | ON TIME BY ENG |  | C | -17 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4594107% | 100%
PZ4 | 0051536680 | 000030&90 | 0051536680-000030&90 | UNITEDHEALTH GROUP CUL PROJECT, CHASKA, | 4597500% |  | DRV |  | WF1751293 | Elec | MAKE | ANSI 49 | 4614800% | 41 | 4591900% | 4593900% | 4594600% | FALSE | Sep-2025 | 10 | 15 | 20 | 5 | LATE | LATE | ON TIME BY ENG |  | C | -21 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4594207% | 100%
PZ4 | 0051536680 | 000030&90 | 0051536680-000030&90 | UNITEDHEALTH GROUP CUL PROJECT, CHASKA, | 4597500% |  | DRV |  | WF1751310 | Elec | MAKE | ANSI 49 | 4614800% | 41 | 4591900% | 4594000% | 4592600% | FALSE | Sep-2025 | 10 | 16 | 6 | -10 | ON TIME | ON TIME | ON TIME BY ENG |  | C | -35 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4594307% | 100%
PZ4 | 0051442285 | 000080 | 0051442285-000080 | GIGABAY 15KV SUBSTATIONS REV3 STARBASE T | 4594500% |  | DEV | KGF | WF1751996 | Mech | MAKE | RAL9003 | 4600800% | 18 | 4592200% | 4592900% | 4594300% | FALSE | Sep-2025 | 10 | 6 | 16 | 10 | LATE | LATE | ON TIME BY ENG |  | C | -3 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4593207% | 100%
PZ4 | 0051442285 | 000080 | 0051442285-000080 | GIGABAY 15KV SUBSTATIONS REV3 STARBASE T | 4594500% |  | DEV | KGF | WF1751991 | Mech | MAKE | RAL9003 | 4600800% | 18 | 4592200% | 4592900% | 4593400% | FALSE | Sep-2025 | 10 | 6 | 10 | 4 | LATE | LATE | ON TIME BY ENG |  | C | -8 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4593207% | 100%
PZ4 | 0051442285 | 000080 | 0051442285-000080 | GIGABAY 15KV SUBSTATIONS REV3 STARBASE T | 4594500% |  | DEV | KGF | WF1751976 | Mech | MAKE | RAL9003 | 4600800% | 18 | 4592200% | 4592900% | 4594500% | FALSE | Sep-2025 | 10 | 6 | 18 | 12 | LATE | LATE | ON TIME BY ENG |  | C | 1 | IMPACTED |  |  | Closed | LATE | NA | 18 | 4593207% | 100%
PZ4 | 0051449809 | 000010 | 0051449809-000010 | HYRDO BUS 480V SWGR | 4594500% |  | JAV |  | WF1752083 | Elec | MAKE | ANSI 49 | 4610800% | 18 | 4592200% | 4593000% | 4592600% | FALSE | Sep-2025 | 10 | 7 | 5 | -2 | ON TIME | ON TIME | ON TIME BY ENG |  | C | -14 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4593307% | 100%
PZ4 | 0051442285 | 000080 | 0051442285-000080 | GIGABAY 15KV SUBSTATIONS REV3 STARBASE T | 4594500% |  | DEV | KGF | WF1751974 | Mech | BUY | RAL9003 | 4600800% | 18 | 4592200% | 4593200% | 4594300% | FALSE | Sep-2025 | 10 | 9 | 16 | 7 | LATE | LATE | ON TIME BY ENG |  | C | -3 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 17 | 4593242% | 100%
PZ4 | 0051442285 | 000070 | 0051442285-000070 | GIGABAY 15KV SUBSTATIONS REV3 STARBASE T | 4594500% |  | DEV | KGF | WF1752117 | Elec | BUY | RAL9003 | 4600800% | 18 | 4592200% | 4593200% | 4593300% | FALSE | Sep-2025 | 10 | 9 | 10 | 1 | LATE | LATE | ON TIME BY ENG |  | C | -9 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 17 | 4593242% | 100%
PZ4 | 0051442285 | 000070 | 0051442285-000070 | GIGABAY 15KV SUBSTATIONS REV3 STARBASE T | 4594500% |  | DEV | KGF | WF1752089 | Mech | MAKE | RAL9003 | 4600800% | 18 | 4592200% | 4593200% | 4594500% | FALSE | Sep-2025 | 10 | 9 | 18 | 9 | LATE | LATE | ON TIME BY ENG |  | C | 1 | IMPACTED |  |  | Closed | LATE | NA | 18 | 4593507% | 100%
PZ4 | 0050988425 | 001260 | 0050988425-001260 | DC TILLMAN | 4591200% |  | KYC | OAL | WF1753559 | Mech | MAKE | ANSI 49 | 4597900% | -9 | 4592400% | 4593200% | 4593200% | FALSE | Sep-2025 | 10 | 7 | 7 | 0 | ON TIME | ON TIME | LATE BY ENG | OCN | C | 14 | IMPACTED |  |  | Closed | LATE | NA | 18 | 4593507% | 100%
PZ4 | 0051449809 | 000010 | 0051449809-000010 | HYRDO BUS 480V SWGR | 4594500% |  | JAV | RCI | WF1754205 | Mech | MAKE | ANSI 49 | 4605200% | 15 | 4592500% | 4593300% | 4593300% | FALSE | Sep-2025 | 10 | 7 | 7 | 0 | ON TIME | ON TIME | ON TIME BY ENG |  | C | -9 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4593607% | 100%
PZ4 | 0051442285 | 000080 | 0051442285-000080 | GIGABAY 15KV SUBSTATIONS REV3 STARBASE T | 4594500% |  | DEV | KGF | WF1755425 | Mech | MAKE | RAL9003 | 4600800% | 13 | 4592900% | 4593600% | 4594500% | FALSE | Sep-2025 | 10 | 6 | 13 | 7 | LATE | LATE | ON TIME BY ENG |  | C | 1 | IMPACTED |  |  | Closed | LATE | NA | 18 | 4593907% | 100%
PZ4 | 0051576246 | 000020&30&40&50&60 | 0051576246-000020&30&40&50&60 | AT&T 1420 BROADWAY STREET LUBBOCK TX | 4595400% |  | JAM | IGS | WF1755461 | Elec | MAKE | ANSI 49 | 4603000% | 20 | 4592900% | 4593600% | 4594600% | FALSE | Sep-2025 | 10 | 6 | 14 | 8 | LATE | LATE | ON TIME BY ENG |  | C | -7 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4593907% | 100%
PZ4 | 0051096008 | 000080 | 0051096008-000080 | BF GOODRICH - FORT WAYNE PLANT - SUBSTAT | 4586500% |  | DRV | CML | WF1756153 | Mech | MAKE | ANSI 61 | 4592300% | -46 | 4593000% | 4593700% | 4593200% | FALSE | Sep-2025 | 10 | 6 | 3 | -3 | ON TIME | ON TIME | LATE BY ENG | Packout asked for covers caused by late arrival material | C | 48 | IMPACTED |  |  | Closed | LATE | NA | 18 | 4594007% | 100%
PZ4 | 0051378342 | 000010 | 0051378342-000010 | EOEM-CUMMINS - TEXAS DOT | 4595700% |  | DEV | VL | WF1756385 | Mech | MAKE | ANSI 61 | 4611400% | 20 | 4593000% | 4593900% | 4595300% | FALSE | Sep-2025 | 10 | 8 | 18 | 10 | LATE | LATE | ON TIME BY ENG |  | C | -3 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4594207% | 100%
PZ4 | 0050839092 | 002030 | 0050839092-002030 | MD ANDERSON CANCER CENTER CONSOLIDATED S | 4594000% |  | OAC | KGF | WF1756796 | Mech | MAKE | ANSI 49 | 4597100% | 8 | 4593100% | 4593900% | 4594000% | FALSE | Oct-2025 | 10 | 7 | 8 | 1 | LATE | LATE | LATE BY ENG |  | C | 1 | IMPACTED |  |  | Closed | LATE | NA | 18 | 4594207% | 100%
PZ4 | 0050839092 | 002030 | 0050839092-002030 | MD ANDERSON CANCER CENTER CONSOLIDATED S | 4594000% |  | OAC | KGF | WF1756795 | Mech | MAKE | ANSI 49 | 4597100% | 8 | 4593100% | 4593900% | 4594000% | FALSE | Oct-2025 | 10 | 7 | 8 | 1 | LATE | LATE | LATE BY ENG |  | C | 1 | IMPACTED |  |  | Closed | LATE | NA | 18 | 4594207% | 100%
PZ4 | 0050839092 | 002030 | 0050839092-002030 | MD ANDERSON CANCER CENTER CONSOLIDATED S | 4594000% |  | OAC | KGF | WF1756798 | Mech | MAKE | ANSI 49 | 4597100% | 8 | 4593100% | 4593900% | 4594000% | FALSE | Oct-2025 | 10 | 7 | 8 | 1 | LATE | LATE | LATE BY ENG |  | C | 1 | IMPACTED |  |  | Closed | LATE | NA | 18 | 4594207% | 100%
PZ4 | 0050839092 | 002030 | 0050839092-002030 | MD ANDERSON CANCER CENTER CONSOLIDATED S | 4594000% |  | OAC | KGF | WF1756782 | Mech | BUY | ANSI 49 | 4597100% | 8 | 4593100% | 4594300% | 4594000% | FALSE | Oct-2025 | 10 | 9 | 8 | -1 | ON TIME | ON TIME | LATE BY ENG |  | C | 1 | IMPACTED |  |  | Closed | LATE | NA | 17 | 4594342% | 100%
PZ4 | 0050839092 | 002030 | 0050839092-002030 | MD ANDERSON CANCER CENTER CONSOLIDATED S | 4594000% |  | OAC | KGF | WF1756814 | Mech | BUY | ANSI 49 | 4597100% | 8 | 4593100% | 4594300% | 4594100% | FALSE | Oct-2025 | 10 | 9 | 8 | -1 | ON TIME | ON TIME | LATE BY ENG |  | C | 1 | IMPACTED |  |  | Closed | LATE | NA | 17 | 4594342% | 100%
PZ4 | 0050839092 | 002030 | 0050839092-002030 | MD ANDERSON CANCER CENTER CONSOLIDATED S | 4594000% |  | OAC | KGF | WF1756800 | Mech | BUY | ANSI 49 | 4597100% | 8 | 2025-10-01 | 2025-10-13 | 4593900% | FALSE | Oct-2025 | 10 | 9 | 7 | -2 | ON TIME | ON TIME | LATE BY ENG |  | C | -2 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 17 | 4594342% | 100%
PZ4 | 0051378342 | 000010 | 0051378342-000010 | EOEM-CUMMINS - TEXAS DOT | 4595700% |  | DEV | VL | WF1756603 | Mech | MAKE | ANSI 49 | 4611400% | 19 | 4593100% | 4593800% | 4594400% | FALSE | Oct-2025 | 10 | 6 | 10 | 4 | LATE | LATE | ON TIME BY ENG |  | C | -10 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4594107% | 100%
PZ4 | 0050839092 | 002030 | 0050839092-002030 | MD ANDERSON CANCER CENTER CONSOLIDATED S | 4594000% |  | OAC | KGF | WF1757184 | Mech | MAKE | ANSI 49 | 4597100% | 7 | 4593200% | 4593900% | 4593700% | FALSE | Oct-2025 | 10 | 6 | 4 | -2 | ON TIME | ON TIME | LATE BY ENG |  | C | -4 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4594207% | 100%
PZ4 | 0050442535 | 000170 | 0050442535-000170 | RRMC GENERATOR REPLACEMENT PROJECT | 4594500% |  | ATA | CML | WF1757179 | Mech | MAKE | ANSI 49 | 4603500% | 10 | 4593200% | 4593900% | 4594500% | FALSE | Oct-2025 | 10 | 6 | 10 | 4 | LATE | LATE | ON TIME BY ENG |  | C | 1 | IMPACTED |  |  | Closed | LATE | NA | 18 | 4594207% | 100%
PZ4 | 0051576246 | 000020&30&40&50&60 | 0051576246-000020&30&40&50&60 | AT&T 1420 BROADWAY STREET LUBBOCK TX | 4595400% |  | JAM | IGS | WF1757153 | Mech | MAKE | ANSI 49 | 4605200% | 17 | 4593200% | 4593900% | 4595100% | FALSE | Oct-2025 | 10 | 6 | 14 | 8 | LATE | LATE | ON TIME BY ENG |  | C | -4 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4594207% | 100%
PZ4 | 0051576246 | 000020&30&40&50&60 | 0051576246-000020&30&40&50&60 | AT&T 1420 BROADWAY STREET LUBBOCK TX | 4595400% |  | JAM | IGS | WF1757167 | Mech | MAKE | ANSI 49 | 4605200% | 17 | 4593200% | 4593900% | 4595100% | FALSE | Oct-2025 | 10 | 6 | 14 | 8 | LATE | LATE | ON TIME BY ENG |  | C | -4 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4594207% | 100%
PZ4 | 0051576246 | 000020&30&40&50&60 | 0051576246-000020&30&40&50&60 | AT&T 1420 BROADWAY STREET LUBBOCK TX | 4595400% |  | JAM | IGS | WF1757140 | Mech | BUY | ANSI 49 | 4605200% | 17 | 4593200% | 4594400% | 4594300% | FALSE | Oct-2025 | 10 | 9 | 8 | -1 | ON TIME | ON TIME | ON TIME BY ENG |  | C | -10 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 17 | 4594442% | 100%
PZ4 | 0051378342 | 000010 | 0051378342-000010 | EOEM-CUMMINS - TEXAS DOT | 4595700% |  | DEV | VL | WF1757224 | Mech | MAKE | ANSI 61 | 4611400% | 18 | 4593200% | 4593900% | 4595400% | FALSE | Oct-2025 | 10 | 6 | 17 | 11 | LATE | LATE | ON TIME BY ENG |  | C | -2 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4594207% | 100%
PZ4 | 0050839092 | 002030 | 0050839092-002030 | MD ANDERSON CANCER CENTER CONSOLIDATED S | 4594000% |  | OAC | KGF | WF1757819 | Mech | MAKE | ANSI 49 | 4597100% | 6 | 4593300% | 4594000% | 4594000% | FALSE | Oct-2025 | 10 | 6 | 6 | 0 | ON TIME | ON TIME | LATE BY ENG |  | C | 1 | IMPACTED |  |  | Closed | LATE | NA | 18 | 4594307% | 100%
PZ4 | 0050839092 | 002030 | 0050839092-002030 | MD ANDERSON CANCER CENTER CONSOLIDATED S | 4594000% |  | OAC | KGF | WF1757818 | Mech | BUY | ANSI 49 | 4597100% | 6 | 4593300% | 4594500% | 4594100% | FALSE | Oct-2025 | 10 | 9 | 6 | -3 | ON TIME | ON TIME | LATE BY ENG |  | C | 1 | IMPACTED |  |  | Closed | LATE | NA | 17 | 4594542% | 100%
PZ4 | 0050442535 | 000170 | 0050442535-000170 | RRMC GENERATOR REPLACEMENT PROJECT | 4594500% |  | ATA | CML | WF1757866 | Elec | MAKE | ANSI 49 | 4603500% | 9 | 4593300% | 4594000% | 4594300% | FALSE | Oct-2025 | 10 | 6 | 7 | 1 | LATE | LATE | LATE BY ENG |  | C | -3 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4594307% | 100%
PZ4 | 0051442285 | 000070 | 0051442285-000070 | GIGABAY 15KV SUBSTATIONS REV3 STARBASE T | 4594500% |  | DEV | KGF | WF1758721 | Elec | BUY | RAL9003 | 4600800% | 9 | 4593300% | 4594600% | 4594400% | FALSE | Oct-2025 | 10 | 10 | 8 | -2 | ON TIME | ON TIME | LATE BY ENG |  | C | -2 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 17 | 4594642% | 100%
PZ4 | 051576246 | 000020&30&40&50&60 | 051576246-000020&30&40&50&60 | AT&T 1420 BROADWAY STREET LUBBOCK TX | 4595400% |  | JAM | IGS | WF1757806 | Mech | MAKE | ANSI 49 | 4603000% | 16 | 4593300% | 4594000% | 4595300% | FALSE | Oct-2025 | 10 | 6 | 15 | 9 | LATE | LATE | ON TIME BY ENG |  | C | -2 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4594307% | 100%
PZ4 | 051576246 | 000020&30&40&50&60 | 051576246-000020&30&40&50&60 | AT&T 1420 BROADWAY STREET LUBBOCK TX | 4595400% |  | JAM | IGS | WF1757799 | Mech | BUY | ANSI 49 | 4603000% | 16 | 4593300% | 4594500% | 4593700% | FALSE | Oct-2025 | 10 | 9 | 3 | -6 | ON TIME | ON TIME | ON TIME BY ENG |  | X | -14 | NOT IMPACTED |  | WF ACTIVE IN OTHER WF | Cancelled | ON TIME | NA | 0 | 4594542% | 0%
PZ4 | 051576246 | 000020&30&40&50&60 | 051576246-000020&30&40&50&60 | AT&T 1420 BROADWAY STREET LUBBOCK TX | 4595400% |  | JAM | IGS | WF1757815 | Mech | BUY | ANSI 49 | 4603000% | 16 | 4593300% | 4594500% | 4594100% | FALSE | Oct-2025 | 10 | 9 | 6 | -3 | ON TIME | ON TIME | ON TIME BY ENG |  | C | -10 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 17 | 4594542% | 100%
PZ4 | 051576246 | 000020&30&40&50&60 | 051576246-000020&30&40&50&60 | AT&T 1420 BROADWAY STREET LUBBOCK TX | 4595400% |  | JAM | IGS | WF1757835 | Mech | MAKE | ANSI 49 | 4603000% | 16 | 4593300% | 4594500% | 4595100% | FALSE | Oct-2025 | 10 | 9 | 13 | 4 | LATE | LATE | ON TIME BY ENG |  | C | -4 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4594807% | 100%
PZ4 | 0051378342 | 000010 | 0051378342-000010 | EOEM-CUMMINS - TEXAS DOT | 4595700% |  | DEV | VL | WF1757847 | Elec | BUY | ANSI 49 | 4611400% | 17 | 4593300% | 4594000% | 4594600% | FALSE | Oct-2025 | 10 | 6 | 10 | 4 | LATE | LATE | ON TIME BY ENG |  | C | -8 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 17 | 4594042% | 100%
PZ4 | 0051378342 | 000010 | 0051378342-000010 | EOEM-CUMMINS - TEXAS DOT | 4595700% |  | DEV | VL | WF1757849 | Mech | MAKE | ANSI 61 | 4611400% | 17 | 4593300% | 4594000% | 4595100% | FALSE | Oct-2025 | 10 | 6 | 13 | 7 | LATE | LATE | ON TIME BY ENG |  | C | -5 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4594307% | 100%
PZ4 | 0051378342 | 000010 | 0051378342-000010 | EOEM-CUMMINS - TEXAS DOT | 4595700% |  | DEV | VL | WF1757850 | Elec | MAKE | ANSI 61 | 4611400% | 17 | 4593300% | 4594000% | 4595100% | FALSE | Oct-2025 | 10 | 6 | 13 | 7 | LATE | LATE | ON TIME BY ENG |  | C | -5 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4594307% | 100%
PZ4 | 0051378342 | 000010 | 0051378342-000010 | EOEM-CUMMINS - TEXAS DOT | 4595700% |  | DEV | VL | WF1757861 | Elec | MAKE | ANSI 61 | 4611400% | 17 | 4593300% | 4594000% | 4595800% | FALSE | Oct-2025 | 10 | 6 | 18 | 12 | LATE | LATE | ON TIME BY ENG |  | C | 2 | IMPACTED |  |  | Closed | LATE | NA | 18 | 4594307% | 100%
PZ4 | 0051378342 | 000010 | 0051378342-000010 | EOEM-CUMMINS - TEXAS DOT | 4595700% |  | DEV | VL | WF1757859 | Mech | MAKE | ANSI 61 | 4611400% | 17 | 4593300% | 4594000% | 4595700% | FALSE | Oct-2025 | 10 | 6 | 17 | 11 | LATE | LATE | ON TIME BY ENG |  | C | 1 | IMPACTED |  |  | Closed | LATE | NA | 18 | 4594307% | 100%
PZ4 | 0051378342 | 000010 | 0051378342-000010 | EOEM-CUMMINS - TEXAS DOT | 4595700% |  | DEV | VL | WF1757856 | Elec | MAKE | ANSI 61 | 4611400% | 17 | 4593300% | 4594000% | 4595800% | FALSE | Oct-2025 | 10 | 6 | 18 | 12 | LATE | LATE | ON TIME BY ENG |  | C | 2 | IMPACTED |  |  | Closed | LATE | NA | 18 | 4594307% | 100%
PZ4 | 0051378342 | 000010 | 0051378342-000010 | EOEM-CUMMINS - TEXAS DOT | 4595700% |  | DEV | VL | WF1757853 | Elec | MAKE | ANSI 61 | 4611400% | 17 | 4593300% | 4594000% | 4595700% | FALSE | Oct-2025 | 10 | 6 | 17 | 11 | LATE | LATE | ON TIME BY ENG |  | C | 1 | IMPACTED |  |  | Closed | LATE | NA | 18 | 4594307% | 100%
PZ4 | 0051378342 | 000010 | 0051378342-000010 | EOEM-CUMMINS - TEXAS DOT | 4595700% |  | DEV | VL | WF1757855 | Elec | MAKE | ANSI 61 | 4611400% | 17 | 4593300% | 4594000% | 4595800% | FALSE | Oct-2025 | 10 | 6 | 18 | 12 | LATE | LATE | ON TIME BY ENG |  | C | 2 | IMPACTED |  |  | Closed | LATE | NA | 18 | 4594307% | 100%
PZ4 | 0051378342 | 000010 | 0051378342-000010 | EOEM-CUMMINS - TEXAS DOT | 4595700% |  | DEV | VL | WF1757876 | Elec | MAKE | ANSI 61 | 4611400% | 17 | 4593300% | 4594300% | 4595100% | FALSE | Oct-2025 | 10 | 7 | 13 | 6 | LATE | LATE | ON TIME BY ENG |  | C | -5 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4594607% | 100%
PZ4 | 0051378342 | 000010 | 0051378342-000010 | EOEM-CUMMINS - TEXAS DOT | 4595700% |  | DEV | VL | WF1757883 | Elec | MAKE | ANSI 61 | 4611400% | 17 | 4593300% | 4594300% | 4595400% | FALSE | Oct-2025 | 10 | 7 | 16 | 9 | LATE | LATE | ON TIME BY ENG |  | C | -2 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4594607% | 100%
PZ4 | 0051378342 | 000010 | 0051378342-000010 | EOEM-CUMMINS - TEXAS DOT | 4595700% |  | DEV | VL | WF1757880 | Elec | MAKE | ANSI 61 | 4611400% | 17 | 4593300% | 4594300% | 4595800% | FALSE | Oct-2025 | 10 | 7 | 18 | 11 | LATE | LATE | ON TIME BY ENG |  | C | 2 | IMPACTED |  |  | Closed | LATE | NA | 18 | 4594607% | 100%
PZ4 | 0051378342 | 000010 | 0051378342-000010 | EOEM-CUMMINS - TEXAS DOT | 4595700% |  | DEV | VL | WF1757878 | Elec | MAKE | ANSI 61 | 4611400% | 17 | 4593300% | 4594300% | 4595800% | FALSE | Oct-2025 | 10 | 7 | 18 | 11 | LATE | LATE | ON TIME BY ENG |  | C | 2 | IMPACTED |  |  | Closed | LATE | NA | 18 | 4594607% | 100%
PZ4 | 0051378342 | 000010 | 0051378342-000010 | EOEM-CUMMINS - TEXAS DOT | 4595700% |  | DEV | VL | WF1757841 | Mech | BUY | ANSI 61 | 4611400% | 17 | 4593300% | 4594500% | 4595100% | FALSE | Oct-2025 | 10 | 9 | 13 | 4 | LATE | LATE | ON TIME BY ENG |  | C | -5 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 17 | 4594542% | 100%
PZ4 | 051576246 | 000020&30&40&50&60 | 051576246-000020&30&40&50&60 | AT&T 1420 BROADWAY STREET LUBBOCK TX | 4595400% |  | JAM | IGS | WF1759194 | Mech | MAKE | ANSI 49 | 4603000% | 14 | 4593700% | 4594400% | 4595000% | FALSE | Oct-2025 | 10 | 6 | 10 | 4 | LATE | LATE | ON TIME BY ENG |  | C | -5 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4594707% | 100%
PZ4 | 0051378342 | 000010 | 0051378342-000010 | EOEM-CUMMINS - TEXAS DOT | 4595700% |  | DEV | VL | WF1759378 | Elec | MAKE | ANSI 61 | 4611400% | 15 | 4593700% | 4594500% | 4595100% | FALSE | Oct-2025 | 10 | 7 | 11 | 4 | LATE | LATE | ON TIME BY ENG |  | C | -5 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4594807% | 100%
PZ4 | 0050442535 | 000170 | 0050442535-000170 | RRMC GENERATOR REPLACEMENT PROJECT | 4594500% |  | ATA | CML | WF1759943 | Mech | BUY | ANSI 49 | 4603500% | 6 | 4593800% | 4595000% | 4594500% | FALSE | Oct-2025 | 10 | 9 | 6 | -3 | ON TIME | ON TIME | LATE BY ENG |  | C | 1 | IMPACTED |  |  | Closed | LATE | NA | 17 | 4595042% | 100%
PZ4 | 0051378342 | 000010 | 0051378342-000010 | EOEM-CUMMINS - TEXAS DOT | 4595700% |  | DEV | VL | WF1760055 | Elec | MAKE | ANSI 61 | 4611400% | 14 | 4593800% | 4594600% | 4595800% | FALSE | Oct-2025 | 10 | 7 | 15 | 8 | LATE | LATE | ON TIME BY ENG |  | C | 2 | IMPACTED |  |  | Closed | LATE | NA | 18 | 4594907% | 100%
PZ4 | 0051378342 | 000010 | 0051378342-000010 | EOEM-CUMMINS - TEXAS DOT | 4595700% |  | DEV | VL | WF1760037 | Elec | BUY | ANSI 61 | 4611400% | 14 | 4593800% | 4595000% | 4595400% | FALSE | Oct-2025 | 10 | 9 | 13 | 4 | LATE | LATE | ON TIME BY ENG |  | C | -2 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 17 | 4595042% | 100%
PZ4 | 0051378342 | 000010 | 0051378342-000010 | EOEM-CUMMINS - TEXAS DOT | 4595700% |  | DEV | VL | WF1760035 | Elec | BUY | ANSI 61 | 4611400% | 14 | 4593800% | 4595000% | 4595400% | FALSE | Oct-2025 | 10 | 9 | 13 | 4 | LATE | LATE | ON TIME BY ENG |  | C | -2 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 17 | 4595042% | 100%
PZ4 | 0051378345 | 000010 | 0051378345-000010 | EOEM-CUMMINS - USCG RIO BAYAMON | 4595400% |  | HMA | OAL | WF1760605 | Mech | MAKE | ANSI 61 | 4608500% | 12 | 4593900% | 4594600% | 4595700% | FALSE | Oct-2025 | 10 | 6 | 13 | 7 | LATE | LATE | ON TIME BY ENG |  | C | 2 | IMPACTED |  |  | Closed | LATE | NA | 18 | 4594907% | 100%
PZ4 | 0051378345 | 000010 | 0051378345-000010 | EOEM-CUMMINS - USCG RIO BAYAMON | 4595400% |  | HMA | OAL | WF1760609 | Mech | MAKE | ANSI 61 | 4608500% | 12 | 4593900% | 4594600% | 4595400% | FALSE | Oct-2025 | 10 | 6 | 12 | 6 | LATE | LATE | ON TIME BY ENG |  | C | 1 | IMPACTED |  |  | Closed | LATE | NA | 18 | 4594907% | 100%
PZ4 | 0051378345 | 000010 | 0051378345-000010 | EOEM-CUMMINS - USCG RIO BAYAMON | 4595400% |  | HMA | OAL | WF1760611 | Mech | MAKE | ANSI 61 | 4608500% | 12 | 4593900% | 4594600% | 4595300% | FALSE | Oct-2025 | 10 | 6 | 11 | 5 | LATE | LATE | ON TIME BY ENG |  | C | -2 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4594907% | 100%
PZ4 | 051576246 | 000020&30&40&50&60 | 051576246-000020&30&40&50&60 | AT&T 1420 BROADWAY STREET LUBBOCK TX | 4595400% |  | JAM | IGS | WF1760855 | Elec | MAKE | ANSI 49 | 4603000% | 12 | 4593900% | 4594700% | 4595400% | FALSE | Oct-2025 | 10 | 7 | 12 | 5 | LATE | LATE | ON TIME BY ENG |  | C | 1 | IMPACTED |  |  | Closed | LATE | NA | 18 | 4595007% | 100%
PZ4 | 051576246 | 000020&30&40&50&60 | 051576246-000020&30&40&50&60 | AT&T 1420 BROADWAY STREET LUBBOCK TX | 4595400% |  | JAM | IGS | WF1760784 | Elec | MAKE | ANSI 49 | 4603000% | 12 | 4593900% | 4594700% | 4594700% | FALSE | Oct-2025 | 10 | 7 | 7 | 0 | ON TIME | ON TIME | ON TIME BY ENG |  | C | -6 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4595007% | 100%
PZ4 | 0051378345 | 000010 | 0051378345-000010 | EOEM-CUMMINS - USCG RIO BAYAMON | 4595400% |  | HMA | OAL | WF1760617 | Mech | BUY | ANSI 61 | 4608500% | 12 | 4593900% | 4595100% | 4595100% | FALSE | Oct-2025 | 10 | 9 | 9 | 0 | ON TIME | ON TIME | ON TIME BY ENG |  | C | -4 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 17 | 4595142% | 100%
PZ4 | 0051378342 | 000010 | 0051378342-000010 | EOEM-CUMMINS - TEXAS DOT | 4595700% |  | DEV | VL | WF1760520 | Mech | BUY | ANSI 49 | 4611400% | 13 | 4593900% | 4595100% | 4594700% | FALSE | Oct-2025 | 10 | 9 | 7 | -2 | ON TIME | ON TIME | ON TIME BY ENG |  | C | -7 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 17 | 4595142% | 100%
PZ4 | 0051378345 | 000010 | 0051378345-000010 | EOEM-CUMMINS - USCG RIO BAYAMON | 4595400% |  | HMA | OAL | WF1761226 | Mech | MAKE | ANSI 61 | 4608500% | 11 | 4594000% | 4594700% | 4595300% | FALSE | Oct-2025 | 10 | 6 | 10 | 4 | LATE | LATE | ON TIME BY ENG |  | C | -2 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4595007% | 100%
PZ4 | 0051306085 | 000310 | 0051306085-000310 | CYRUSONE - CYRUSONE, INC | 4591000% |  | HMA | IGS | WF1762157 | Mech | MAKE | ANSI 49 | 4578900% | -24 | 4594300% | 4595100% | 4594600% | FALSE | Oct-2025 | 10 | 7 | 4 | -3 | ON TIME | ON TIME | LATE BY ENG | Supply asked for a spare CT | C | 26 | IMPACTED |  |  | Closed | LATE | NA | 18 | 4595407% | 100%
PZ4 | 0051306085 | 000310 | 0051306085-000310 | CYRUSONE - CYRUSONE, INC | 4591000% |  | HMA | IGS | WF1762078 | Mech | BUY | ANSI 49 | 4578900% | -24 | 4594300% | 4595300% | 4594600% | FALSE | Oct-2025 | 10 | 9 | 4 | -5 | ON TIME | ON TIME | LATE BY ENG | Supply asked for a spare CT | C | 26 | IMPACTED |  |  | Closed | LATE | NA | 17 | 4595342% | 100%
PZ4 | 0051306085 | 000310 | 0051306085-000310 | CYRUSONE - CYRUSONE, INC | 4591000% |  | HMA | IGS | WF1762133 | Mech | BUY | ANSI 49 | 4578900% | -24 | 4594300% | 4595300% | 4594600% | FALSE | Oct-2025 | 10 | 9 | 4 | -5 | ON TIME | ON TIME | LATE BY ENG | Supply asked for a spare CT | C | 26 | IMPACTED |  |  | Closed | LATE | NA | 17 | 4595342% | 100%
PZ4 | 0051608932 | 000010 | 0051608932-000010 | VO#XX ACTUALIZACION PZ4 TAG: 1313-SB-010 | 4595300% |  | JAT | HUP | WF1761987 | Mech | MAKE | ANSI 49 | 4588100% | 9 | 4594300% | 4595000% | 4595200% | FALSE | Oct-2025 | 10 | 6 | 8 | 2 | LATE | LATE | LATE BY ENG | RM HUPshed ahead of schedule | C | -2 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4595307% | 100%
PZ4 | 051576246 | 000020&30&40&50&60 | 051576246-000020&30&40&50&60 | AT&T 1420 BROADWAY STREET LUBBOCK TX | 4595400% |  | JAM | IGS | WF1762112 | Elec | MAKE | ANSI 49 | 4603000% | 10 | 4594300% | 4595100% | 4595300% | FALSE | Oct-2025 | 10 | 7 | 9 | 2 | LATE | LATE | ON TIME BY ENG |  | C | -2 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4595407% | 100%
PZ4 | 0051378342 | 000010 | 0051378342-000010 | EOEM-CUMMINS - TEXAS DOT | 4595700% |  | DEV | VL | WF1761923 | Mech | BUY | ANSI 61 | 4611400% | 11 | 4594300% | 4595300% | 4595200% | FALSE | Oct-2025 | 10 | 9 | 8 | -1 | ON TIME | ON TIME | ON TIME BY ENG |  | C | -4 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 17 | 4595342% | 100%
PZ4 | 0050384250 | 001230 | 0050384250-001230 | NEW PARNASSUS HEIGHTS HOSPITAL - UCSF - | 4600100% |  | HMA |  | WF1762111 | Elec | MAKE | ANSI 49 | 4627100% | 43 | 4594300% | 4595100% | 4595800% | FALSE | Oct-2025 | 10 | 7 | 12 | 5 | LATE | LATE | ON TIME BY ENG |  | C | -28 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4595407% | 100%
PZ4 | 0051199001 | 000010 | 0051199001-000010 | EC1&EC2&EC3 | 4593600% |  | ASP | AL | WF1763017 | Mech | MAKE | RAL 7035 | 4598700% | -7 | 4594400% | 4595300% | 4594600% | FALSE | Oct-2025 | 10 | 8 | 3 | -5 | ON TIME | ON TIME | LATE BY ENG | Correction in doors layout | C | 9 | IMPACTED |  |  | Closed | LATE | NA | 18 | 4595607% | 100%
PZ4 | 0051306085 | 000310 | 0051306085-000310 | CYRUSONE - CYRUSONE, INC | 4591000% |  | HMA | IGS | WF1762796 | Elec | BUY | ANSI 49 | 4578900% | -25 | 4594400% | 4595400% | 4594600% | FALSE | Oct-2025 | 10 | 9 | 3 | -6 | ON TIME | ON TIME | LATE BY ENG | Supply asked for a spare CT | C | 26 | IMPACTED |  |  | Closed | LATE | NA | 17 | 4595442% | 100%
QED2 | SWBD | SWBD 2.0 BREAKERS | SWBD-SWBD 2.0 BREAKERS | SWBD 2.0 BREAKERS | 4592600% |  | ALT | AL | WF1762777 | Elec | BUY | ANSI 49 | NA | -13 | 4594400% | 4595400% | 4594600% | FALSE | Oct-2025 | 10 | 9 | 3 | -6 | ON TIME | ON TIME | LATE BY ENG |  | C | 15 | IMPACTED |  |  | Closed | LATE | NA | 17 | 4595442% | 100%
PZ4 | 0051422641 | 000010 | 0051422641-000010 | EOEM-CUMMINS - REIDSVILLE WTP | 4597100% |  | ALT | VL | WF1762944 | Mech | MAKE | ANSI 61 | 4597100% | 20 | 4594400% | 4595200% | 4595100% | FALSE | Oct-2025 | 10 | 7 | 6 | -1 | ON TIME | ON TIME | ON TIME BY ENG |  | C | -14 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4595507% | 100%
PZ4 | 0051422641 | 000010 | 0051422641-000010 | EOEM-CUMMINS - REIDSVILLE WTP | 4597100% |  | ALT | VL | WF1762941 | Mech | MAKE | ANSI 61 | 4597100% | 20 | 4594400% | 4595200% | 4595100% | FALSE | Oct-2025 | 10 | 7 | 6 | -1 | ON TIME | ON TIME | ON TIME BY ENG |  | C | -14 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4595507% | 100%
PZ4 | 0051422641 | 000010 | 0051422641-000010 | EOEM-CUMMINS - REIDSVILLE WTP | 4597100% |  | ALT | VL | WF1762945 | Mech | BUY | ANSI 61 | 4597100% | 20 | 4594400% | 4595400% | 4595300% | FALSE | Oct-2025 | 10 | 9 | 8 | -1 | ON TIME | ON TIME | ON TIME BY ENG |  | x | -12 | NOT IMPACTED |  | wrong template | Cancelled | ON TIME | NA | 2 | 4595442% | 11.76%
PZ4 | 0051095105 | 000410 | 0051095105-000410 | GSK MARIETTA B55 | 4599600% |  | JAM |  | WF1762885 | Elec | MAKE | ANSI 49 | 4615700% | 39 | 4594400% | 4595100% | 4594600% | FALSE | Oct-2025 | 10 | 6 | 3 | -3 | ON TIME | ON TIME | ON TIME BY ENG |  | x | -33 | NOT IMPACTED |  |  | Cancelled | ON TIME | NA | 0 | 4595407% | 0%
PZ4 | 0051095105 | 000410 | 0051095105-000410 | GSK MARIETTA B55 | 4599600% |  | JAM |  | WF1762887 | Elec | BUY | ANSI 49 | 4615700% | 39 | 4594400% | 4595400% | 4594600% | FALSE | Oct-2025 | 10 | 9 | 3 | -6 | ON TIME | ON TIME | ON TIME BY ENG |  | C | -33 | NOT IMPACTED |  | Active US23 | Closed | ON TIME | NA | 17 | 4595442% | 100%
PZ4 | 0050384250 | 001230 | 0050384250-001230 | NEW PARNASSUS HEIGHTS HOSPITAL - UCSF - | 4600100% |  | HMA |  | WF1762947 | Elec | MAKE | ANSI 49 | 4627100% | 42 | 4594400% | 4595200% | 4595800% | FALSE | Oct-2025 | 10 | 7 | 11 | 4 | LATE | LATE | ON TIME BY ENG |  | C | -28 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4595507% | 100%
PZ4 | 0050384250 | 001260 | 0050384250-001260 | NEW PARNASSUS HEIGHTS HOSPITAL - UCSF - | 4600100% |  | HMA |  | WF1763020 | Elec | MAKE | ANSI 49 | 4608800% | 42 | 4594400% | 4595300% | 4595800% | FALSE | Oct-2025 | 10 | 8 | 11 | 3 | LATE | LATE | ON TIME BY ENG |  | C | -28 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4595607% | 100%
PZ4 | 0051199001 | 000010 | 0051199001-000010 | EC1&EC2&EC3 | 4593600% |  | ASP | AL | WF1763630 | See3D | BUY | ANSI 49 | 4598700% | -8 | 4594500% | 4595700% | 4595000% | FALSE | Oct-2025 | 10 | 9 | 4 | -5 | ON TIME | ON TIME | LATE BY ENG |  | x | 11 | IMPACTED |  | Obsolete PN | Cancelled | LATE | NA | 0 | 4595742% | 0%
PZ4 | 0051442285 | 000070 | 0051442285-000070 | GIGABAY 15KV SUBSTATIONS REV3 STARBASE T | 4594500% |  | DEV | KGF | WF1763566 | Mech | MAKE | RAL9003 | 4600800% | 1 | 4594500% | 4595200% | 4594600% | FALSE | Oct-2025 | 10 | 6 | 2 | -4 | ON TIME | ON TIME | LATE BY ENG | Request by mech team | C | 2 | IMPACTED |  |  | Closed | LATE | NA | 18 | 4595507% | 100%
PZ4 | 0051576246 | 000020&30&40&50&60 | 0051576246-000020&30&40&50&60 | AT&T 1420 BROADWAY STREET LUBBOCK TX | 4595400% |  | JAM | IGS | WF1763481 | Elec | MAKE | ANSI 49 | 4603000% | 8 | 4594500% | 4595200% | 4595000% | FALSE | Oct-2025 | 10 | 6 | 4 | -2 | ON TIME | ON TIME | LATE BY ENG | Missing part in related WF | C | -5 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4595507% | 100%
PZ4 | 0051354978 | 000080 | 0051354978-000080 | ADVENT HEALTH CARROLLWOOD GARDEN TOWER E | 4598100% |  | RAS | RCI | WF1763609 | Mech | MAKE | ANSI 49 | 4605200% | 27 | 4594500% | 4595300% | 4596600% | FALSE | Oct-2025 | 10 | 7 | 15 | 8 | LATE | LATE | ON TIME BY ENG |  | C | -9 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4595607% | 100%
PZ4 | 0051306085 | 000310 | 0051306085-000310 | CYRUSONE - CYRUSONE, INC | 4591000% |  | HMA | IGS | WF1764090 | Mech | MAKE | ANSI 49 | 4578900% | -27 | 4594600% | 4595300% | 4595200% | FALSE | Oct-2025 | 10 | 6 | 5 | -1 | ON TIME | ON TIME | LATE BY ENG |  | C | 30 | IMPACTED |  |  | Closed | LATE | NA | 18 | 4595607% | 100%
PZ4 | 0051306085 | 000310 | 0051306085-000310 | CYRUSONE - CYRUSONE, INC | 4591000% |  | HMA | IGS | WF1764092 | Mech | MAKE | ANSI 49 | 4578900% | -27 | 4594600% | 4595300% | 4595200% | FALSE | Oct-2025 | 10 | 6 | 5 | -1 | ON TIME | ON TIME | LATE BY ENG |  | C | 30 | IMPACTED |  |  | Closed | LATE | NA | 18 | 4595607% | 100%
PZ4 | 0051306085 | 000310 | 0051306085-000310 | CYRUSONE - CYRUSONE, INC | 4591000% |  | HMA | IGS | WF1764099 | Mech | MAKE | ANSI 49 | 4578900% | -27 | 4594600% | 4595300% | 4595200% | FALSE | Oct-2025 | 10 | 6 | 5 | -1 | ON TIME | ON TIME | LATE BY ENG |  | C | 30 | IMPACTED |  |  | Closed | LATE | NA | 18 | 4595607% | 100%
QED2 | SWBD | swbd | SWBD-swbd | swbd | 4592600% |  | ALT | AL | WF1764182 | Elec | MAKE | ANSI 49 | NA | -15 | 4594600% | 4595400% | 4595200% | FALSE | Oct-2025 | 10 | 7 | 5 | -2 | ON TIME | ON TIME | LATE BY ENG |  | C | 19 | IMPACTED |  |  | Closed | LATE | NA | 18 | 4595707% | 100%
PZ4 | 0051422641 | 000010 | 0051422641-000010 | EOEM-CUMMINS - REIDSVILLE WTP | 4597100% |  | ALT | VL | WF1764230 | Mech | MAKE | ANSI 49 | 4597100% | 18 | 4594600% | 4595700% | 4595800% | FALSE | Oct-2025 | 10 | 8 | 9 | 1 | LATE | LATE | ON TIME BY ENG |  | C | -9 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4596007% | 100%
PZ4 | 0051422641 | 000010 | 0051422641-000010 | EOEM-CUMMINS - REIDSVILLE WTP | 4597100% |  | ALT | VL | WF1764231 | Mech | MAKE | ANSI 49 | 4597100% | 18 | 4594600% | 4595700% | 4595800% | FALSE | Oct-2025 | 10 | 8 | 9 | 1 | LATE | LATE | ON TIME BY ENG |  | C | -9 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4596007% | 100%
PZ4 | 0051422641 | 000010 | 0051422641-000010 | EOEM-CUMMINS - REIDSVILLE WTP | 4597100% |  | ALT | VL | WF1764238 | Mech | BUY | ANSI 61 | 4597100% | 18 | 4594600% | 4596000% | 4595800% | FALSE | Oct-2025 | 10 | 11 | 9 | -2 | ON TIME | ON TIME | ON TIME BY ENG |  | C | -9 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 17 | 4596042% | 100%
PZ4 | JIRA | COUNTERMEASURE | JIRA-COUNTERMEASURE | NEMA 3R LIGHNING ASSY UPDATE | 4595900% |  | MGL |  | WF1764643 | Elec | MAKE | NA | NA | 9 | 4594700% | 4595400% | 4596600% | FALSE | Oct-2025 | 10 | 6 | 13 | 7 | LATE | LATE | LATE BY ENG | JIRA | C | 5 | IMPACTED |  |  | Closed | LATE | NA | 18 | 4595707% | 100%
PZ4 | JIRA | COUNTERMEASURE | JIRA-COUNTERMEASURE | NEMA 3R LIGHNING ASSY UPDATE | 4595900% |  | MGL |  | WF1764639 | Elec | BUY | NA | NA | 9 | 4594700% | 4595900% | 4595900% | FALSE | Oct-2025 | 10 | 9 | 9 | 0 | ON TIME | ON TIME | LATE BY ENG | JIRA | C | 1 | IMPACTED |  |  | Closed | LATE | NA | 17 | 4595942% | 100%
PZ4 | 0051422641 | 000010 | 0051422641-000010 | EOEM-CUMMINS - REIDSVILLE WTP | 4597100% |  | ALT | VL | WF1764572 | Mech | MAKE | ANSI 61 | 4597100% | 17 | 4594700% | 4595400% | 4595800% | FALSE | Oct-2025 | 10 | 6 | 8 | 2 | LATE | LATE | ON TIME BY ENG |  | C | -9 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4595707% | 100%
PZ4 | 0050728484 | 018570 | 0050728484-018570 | MDACC CSB CLINICAL SERVICES BUILDING | 4596600% |  | KYC | KGF | WF1765269 | Mech | MAKE | ANSI 49 | 4598600% | 13 | 4595000% | 4595700% | 4595200% | FALSE | Oct-2025 | 10 | 6 | 3 | -3 | ON TIME | ON TIME | ON TIME BY ENG |  | C | -10 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4596007% | 100%
QED2 | SWBD | meta f2.0 | SWBD-meta f2.0 | meta f2.0 | 4592600% |  | ALT | AL | WF1765360 | Elec | MAKE | ANSI 49 | NA | -17 | 4595000% | 4595800% | 4595200% | FALSE | Oct-2025 | 10 | 7 | 3 | -4 | ON TIME | ON TIME | LATE BY ENG |  | C | 19 | IMPACTED |  |  | Closed | LATE | NA | 18 | 4596107% | 100%
PZ4 | 0051608932 | 000010 | 0051608932-000010 | VO#XX ACTUALIZACION PZ4 TAG: 1313-SB-010 | 4595300% |  | JAT | HUP | WF1765254 | Mech | MAKE | ANSI 49 | 4588100% | 4 | 4595000% | 4595700% | 4595000% | FALSE | Oct-2025 | 10 | 6 | 1 | -5 | ON TIME | ON TIME | LATE BY ENG |  | X | -4 | NOT IMPACTED |  |  | Cancelled | ON TIME | NA | 0 | 4596007% | 0%
PZ4 | 051576246 | 000020&30&40&50&60 | 051576246-000020&30&40&50&60 | AT&T 1420 BROADWAY STREET LUBBOCK TX | 4595400% |  | JAM | IGS | WF1765136 | Mech | MAKE | ANSI 49 | 4603000% | 5 | 4595000% | 4595700% | 4595000% | FALSE | Oct-2025 | 10 | 6 | 1 | -5 | ON TIME | ON TIME | LATE BY ENG | Customer Change Order | x | -5 | NOT IMPACTED |  | Active in other WF | Cancelled | ON TIME | NA | 0 | 4596007% | 0%
PZ4 | 0051422641 | 000010 | 0051422641-000010 | EOEM-CUMMINS - REIDSVILLE WTP | 4597100% |  | ALT | VL | WF1765234 | Mech | MAKE | ANSI 61 | 4597100% | 16 | 4595000% | 4595700% | 4595300% | FALSE | Oct-2025 | 10 | 6 | 4 | -2 | ON TIME | ON TIME | ON TIME BY ENG |  | C | -12 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4596007% | 100%
PZ4 | 0051354978 | 000080 | 0051354978-000080 | ADVENT HEALTH CARROLLWOOD GARDEN TOWER E | 4598100% |  | RAS | RCI | WF1765333 | Mech | MAKE | ANSI 49 | 4605200% | 24 | 4595000% | 4595800% | 4596600% | FALSE | Oct-2025 | 10 | 7 | 12 | 5 | LATE | LATE | ON TIME BY ENG |  | C | -9 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4596107% | 100%
PZ4 | 0051378207 | 000260 | 0051378207-000260 | SUNY UPSTATE MEDICAL WEISKOTTEN HALL ADD | 4598900% |  | RAS | RCI | WF1765340 | Mech | MAKE | ANSI 49 | 4607600% | 30 | 4595000% | 4595800% | 4595700% | FALSE | Oct-2025 | 10 | 7 | 6 | -1 | ON TIME | ON TIME | ON TIME BY ENG |  | C | -21 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4596107% | 100%
PZ4 | 0050384250 | 001260 | 0050384250-001260 | NEW PARNASSUS HEIGHTS HOSPITAL - UCSF - | 4600100% |  | HMA |  | WF1765915 | Elec | MAKE | ANSI 49 | 4627100% | 37 | 4595100% | 4595800% | 4596600% | FALSE | Oct-2025 | 10 | 6 | 11 | 5 | LATE | LATE | ON TIME BY ENG |  | C | -23 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4596107% | 100%
PZ4 | 0050384250 | 001230 | 0050384250-001260 | NEW PARNASSUS HEIGHTS HOSPITAL - UCSF - | 4600100% |  | HMA |  | WF1765921 | Elec | MAKE | ANSI 49 | 4627100% | 37 | 4595100% | 4596100% | 4596600% | FALSE | Oct-2025 | 10 | 9 | 11 | 2 | LATE | LATE | ON TIME BY ENG |  | C | -23 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4596407% | 100%
PZ4 | 0051283748 | 000120 | 0051283748-000120 | TOYOTA PEMC EQUIPMENT REPLACEMENT | 4585600% |  | HMA |  | WF1766499 | Elec | BUY | ANSI 49 | 4587900% | -69 | 4595200% | 4596400% | 4596400% | FALSE | Oct-2025 | 10 | 9 | 8 | -1 | ON TIME | ON TIME | LATE BY ENG | JIRA | C | 75 | IMPACTED |  |  | Closed | LATE | NA | 17 | 4596442% | 100%
PZ4 | 0050728484 | 018580 | 0050728484-018580 | MDACC CSB CLINICAL SERVICES BUILDING | 4598200% |  | OAC | KFG | WF1766612 | Mech | MAKE | ANSI 49 | 4605100% | 23 | 4595200% | 4596000% | 4595900% | FALSE | Oct-2025 | 10 | 7 | 6 | -1 | ON TIME | ON TIME | ON TIME BY ENG |  | C | -14 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4596307% | 100%
PZ4 | 0051378207 | 000270 | 0051378207-000260 | SUNY UPSTATE MEDICAL WEISKOTTEN HALL ADD | 4598900% |  | RAS | FRC | WF1766476 | Mech | MAKE | ANSI 49 | 4607600% | 28 | 4595200% | 4595900% | 4595800% | FALSE | Oct-2025 | 10 | 6 | 5 | -1 | ON TIME | ON TIME | ON TIME BY ENG |  | C | -20 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4596207% | 100%
PZ4 | 0050545482 | 001630 | 0050545482-001630 | Y12 MERCURY TREATMENT FACILITY | 4581200% |  | ASP | LDT | WF1767147 | Mech | MAKE | ANSI 49 | 09/26/2025 | -101 | 4595300% | 4596100% | 4595700% | FALSE | Oct-2025 | 10 | 6 | 3 | -3 | ON TIME | ON TIME | LATE BY ENG |  | C | 103 | IMPACTED |  |  | Closed | LATE | NA | 18 | 4596407% | 100%
PZ4 | 051576246 | 000020&30&40&50&60 | 051576246-000020&30&40&50&60 | AT&T 1420 BROADWAY STREET LUBBOCK TX | 4595400% |  | JAM | IGS | WF1767159 | Elec | MAKE | ANSI 49 | 4603000% | 2 | 4595300% | 4596100% | 4595700% | FALSE | Oct-2025 | 10 | 7 | 3 | -4 | ON TIME | ON TIME | LATE BY ENG | Missed | C | 2 | IMPACTED |  |  | Closed | LATE | NA | 18 | 4596407% | 100%
PZ4 | 0011892449 | 000010 | 0011892449-000010 | EOEM-CUMMINS - REIDSVILLE WTP | 4597100% |  | ALT | VL | WF1767157 | Mech | MAKE | ANSI 61 | 4597100% | 13 | 4595300% | 4596100% | 4595800% | FALSE | Oct-2025 | 10 | 7 | 4 | -3 | ON TIME | ON TIME | ON TIME BY ENG |  | C | -9 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4596407% | 100%
PZ4 | 0050384250 | 001230&1260 | 0050384250-001230&1260 | NEW PARNASSUS HEIGHTS HOSPITAL - UCSF - | 4600100% |  | HMA |  | WF1766987 | Elec | MAKE | ANSI 49 | 4627100% | 35 | 4595300% | 4596000% | 4596600% | FALSE | Oct-2025 | 10 | 6 | 9 | 3 | LATE | LATE | ON TIME BY ENG |  | C | -23 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4596307% | 100%
PZ4 | 0050384250 | 001230&1260 | 0050384250-001230&1260 | NEW PARNASSUS HEIGHTS HOSPITAL - UCSF - | 4600100% |  | HMA |  | WF1767025 | Elec | MAKE | ANSI 49 | 4627100% | 35 | 4595300% | 4596000% | 4596600% | FALSE | Oct-2025 | 10 | 6 | 9 | 3 | LATE | LATE | ON TIME BY ENG |  | C | -23 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4596307% | 100%
PZ4 | 0050384250 | 001240&1250&001270 | 0050384250-001240&1250&001270 | NEW PARNASSUS HEIGHTS HOSPITAL - UCSF - | 4600100% |  | ASP |  | WF1767217 | Elec | MAKE | ANSI 49 | 4620300% | 35 | 4595300% | 4596400% | 4596600% | FALSE | Oct-2025 | 10 | 8 | 9 | 1 | LATE | LATE | ON TIME BY ENG |  | C | -23 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4596707% | 100%
PZ4 | 0050384250 | 001240&1250&001270 | 0050384250-001240&1250&001270 | NEW PARNASSUS HEIGHTS HOSPITAL - UCSF - | 4600100% |  | ASP |  | WF1767216 | Elec | MAKE | ANSI 49 | 4620300% | 35 | 4595300% | 4596400% | 4596800% | FALSE | Oct-2025 | 10 | 8 | 11 | 3 | LATE | LATE | ON TIME BY ENG |  | C | -21 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4596707% | 100%
PZ4 | 0050384250 | 001230&1260 | 0050384250-001230&1260 | NEW PARNASSUS HEIGHTS HOSPITAL - UCSF - | 4600100% |  | HMA |  | WF1767100 | Elec | MAKE | ANSI 49 | 4627100% | 35 | 4595300% | 4596500% | 4596800% | FALSE | Oct-2025 | 10 | 9 | 11 | 2 | LATE | LATE | ON TIME BY ENG |  | C | -21 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4596807% | 100%
PZ4 | 0051199001 | 000010 | 0051199001-000010 | EC1&EC2&EC3 | 4593600% |  |  | ODE | WF1767579 | Mech | MAKE | RAL | 4598700% | -15 | 4595400% | 4596400% | 4595900% | FALSE | Oct-2025 | 10 | 7 | 4 | -3 | ON TIME | ON TIME | LATE BY ENG | Substitution request | C | 18 | IMPACTED |  |  | Closed | LATE | NA | 18 | 4596707% | 100%
PZ4 | 0011892449 | 000010 | 0011892449-000010 | EOEM-CUMMINS - REIDSVILLE WTP | 4597100% |  | ALT | VL | WF1767492 | Mech | BUY | ANSI 61 | 4597100% | 12 | 4595400% | 4595500% | 4596400% | FALSE | Oct-2025 | 10 | 1 | 6 | 5 | LATE | LATE | ON TIME BY ENG |  | C | -6 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 17 | 4595542% | 100%
PZ4 | JIRA | COUNTERMEASURE | JIRA-COUNTERMEASURE | TME27242 | 4597300% |  | MGL |  | WF1767468 | Elec | BUY | ANSI 49 | NA | 14 | 4595400% | 4596600% | 4596800% | FALSE | Oct-2025 | 10 | 9 | 10 | 1 | LATE | LATE | ON TIME BY ENG | JIRA | C | -4 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 17 | 4596642% | 100%
PZ4 | 0051648563 | 000040 | 0051648563-000040 | ENCORE WIRE NEW PLANT 5 MCKINNEY | 4598100% |  | JAT | HUP | WF1768370 | Mech | MAKE | ANSI 49 | 4608000% | 20 | 4595400% | 4596500% | 4596600% | FALSE | Oct-2025 | 10 | 8 | 8 | 0 | ON TIME | ON TIME | ON TIME BY ENG |  | C | -9 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4596807% | 100%
PZ4 | 0051647770 | 000010 | 0051647770-000010 | SCHNEIDER ELECTRIC USA INC | 4600000% |  | DEV |  | WF1769097 | Elec | MAKE | ANSI 49 | 4605200% | 31 | 4595800% | 4596700% | 4597500% | FALSE | Oct-2025 | 10 | 8 | 13 | 5 | LATE | LATE | ON TIME BY ENG |  | C | -15 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4597007% | 100%
PZ4 | 0051647770 | 000010 | 0051647770-000010 | SCHNEIDER ELECTRIC USA INC | 4600000% |  | DEV |  | WF1769099 | Elec | BUY | ANSI 49 | 4605200% | 31 | 4595800% | 4597100% | 4595900% | FALSE | Oct-2025 | 10 | 10 | 2 | -8 | ON TIME | ON TIME | ON TIME BY ENG |  | C | -26 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 0 | 4597142% | 0%
PZ4 | 0051647770 | 000010 | 0051647770-000010 | SCHNEIDER ELECTRIC USA INC | 4600000% |  | DEV |  | WF1769103 | Elec | BUY | ANSI 49 | 4605200% | 31 | 4595800% | 4597100% | 4596700% | FALSE | Oct-2025 | 10 | 10 | 7 | -3 | ON TIME | ON TIME | ON TIME BY ENG |  | C | -21 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 17 | 4597142% | 100%
PZ4 | 0051095105 | 000410 | 0051095105-000410 | GSK MARIETTA B55 | 4599600% |  | JAM | OAL | WF1769567 | Elec | BUY | ANSI 49 | 4615700% | 28 | 4595900% | 4597200% | 4598000% | FALSE | Oct-2025 | 10 | 10 | 13 | 3 | LATE | LATE | ON TIME BY ENG |  | C | -11 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 17 | 4597242% | 100%
PZ4 | 0051647770 | 000010 | 0051647770-000010 | SCHNEIDER ELECTRIC USA INC | 4600000% |  | DEV |  | WF1769697 | Elec | MAKE | ANSI 49 | 4605200% | 30 | 4595900% | 4596700% | 4597500% | FALSE | Oct-2025 | 10 | 7 | 12 | 5 | LATE | LATE | ON TIME BY ENG |  | C | -15 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4597007% | 100%
PZ4 | 0051648563 | 000070 | 0051648563-000070 | ENCORE WIRE NEW PLANT 5 MCKINNEY | 4598100% |  | JAT | IGS | WF1770319 | Mech | MAKE | ANSI 49 | 4603500% | 16 | 4596000% | 4596800% | 4596800% | FALSE | Oct-2025 | 10 | 7 | 6 | -1 | ON TIME | ON TIME | ON TIME BY ENG |  | C | -7 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4597107% | 100%
PZ4 | 0051536680 | 000030 | 0051536680-000030 | UNITEDHEALTH GROUP CUL PROJECT, CHASKA, | 4601000% |  | DRV | AL | WF1771689 | Mech | MAKE | ANSI 49 | 4605900% | 35 | 4596400% | 4597200% | 4597300% | FALSE | Nov-2025 | 10 | 7 | 8 | 1 | LATE | LATE | ON TIME BY ENG |  | C | -24 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4597507% | 100%
PZ4 | 0051536680 | 000030 | 0051536680-000030 | UNITEDHEALTH GROUP CUL PROJECT, CHASKA, | 4601000% |  | DRV | AL | WF1771711 | Mech | MAKE | ANSI 49 | 4605900% | 35 | 4596400% | 4597200% | 4597300% | FALSE | Nov-2025 | 10 | 7 | 8 | 1 | LATE | LATE | ON TIME BY ENG |  | C | -24 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4597507% | 100%
PZ4 | 0051536680 | 000030 | 0051536680-000030 | UNITEDHEALTH GROUP CUL PROJECT, CHASKA, | 4601000% |  | DRV | AL | WF1771712 | Mech | MAKE | ANSI 49 | 4605900% | 35 | 4596400% | 4597200% | 4597300% | FALSE | Nov-2025 | 10 | 7 | 8 | 1 | LATE | LATE | ON TIME BY ENG |  | C | -24 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4597507% | 100%
PZ4 | 0051378342 | 000010 | 0051378342-000010 | EOEM-CUMMINS - TEXAS DOT | 4595700% |  | DEV | VL | WF1772295 | Elec | BUY | ANSI 61 | 4608300% | -7 | 4596500% | 4597500% | 4596800% | FALSE | Nov-2025 | 10 | 9 | 4 | -5 | ON TIME | ON TIME | LATE BY ENG | RELAY SPARE PN | C | 9 | IMPACTED |  |  | Closed | LATE | NA | 17 | 4597542% | 100%
PZ4 | 0051659711 | 000060 | 0051659711-000060 | ADVENTHEALTH ORLANDO EOB CHILLER NO. 6 | 4598900% |  | JRC | CML | WF1772317 | Elec | MAKE | ANSI 49 | 4626700% | 19 | 4596500% | 4597200% | 4597300% | FALSE | Nov-2025 | 10 | 6 | 7 | 1 | LATE | LATE | ON TIME BY ENG |  | C | -10 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4597507% | 100%
PZ4 | 0051659711 | 000060 | 0051659711-000060 | ADVENTHEALTH ORLANDO EOB CHILLER NO. 6 | 4598900% |  | JRC | CML | WF1773191 | Elec | MAKE | ANSI 49 | 4626700% | 18 | 4596600% | 4597400% | 4597300% | FALSE | Nov-2025 | 10 | 7 | 6 | -1 | ON TIME | ON TIME | ON TIME BY ENG |  | C | -10 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4597707% | 100%
QED2 | SWBD | META F2.0 | SWBD-META F2.0 | META F2.0 | 4598200% |  | ALT | AL | WF1774444 | Mech | CNG-BOM | ANSI 49 | NA | 11 | 4596800% | 4597400% | 4597500% | FALSE | Nov-2025 | 10 | 5 | 6 | 1 | LATE | LATE | ON TIME BY ENG |  | C | -3 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 11 | 4597442% | 100%
QED2 | SWBD | META F2.0 | SWBD-META F2.0 | META F2.0 | 4598200% |  | ALT | AL | WF1774367 | Mech | MAKE | ANSI 49 | NA | 11 | 4596800% | 4597500% | 4597400% | FALSE | Nov-2025 | 10 | 6 | 5 | -1 | ON TIME | ON TIME | ON TIME BY ENG |  | C | -4 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4597807% | 100%
QED2 | SWBD | META F2.0 | SWBD-META F2.0 | META F2.0 | 4598200% |  | ALT | AL | WF1774370 | Mech | BUY | ANSI 49 | NA | 11 | 4596800% | 4598000% | 4597400% | FALSE | Nov-2025 | 10 | 9 | 5 | -4 | ON TIME | ON TIME | ON TIME BY ENG |  | C | -4 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 17 | 4598042% | 100%
PZ4 | 0051095105 | 000410 | 0051095105-000410 | GSK MARIETTA B55 | 4599600% |  | JAM |  | WF1774331 | Elec | MAKE | ANSI 49 | 4615700% | 21 | 4596800% | 4597500% | 4597500% | FALSE | Nov-2025 | 10 | 6 | 6 | 0 | ON TIME | ON TIME | ON TIME BY ENG |  | C | -13 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4597807% | 100%
PZ4 | SPECIAL | SPECIAL | SPECIAL-SPECIAL | ABB BLACKLISTING | 4598500% |  | UFA |  | WF1775167 | Elec | BUY | NA | NA | 11 | 4597100% | 4598500% | 4598000% | FALSE | Nov-2025 | 10 | 11 | 6 | -5 | ON TIME | ON TIME | ON TIME BY ENG |  | C | -2 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 17 | 4598542% | 100%
PZ4 | 0051659711 | 000090 | 0051659711-000090 | ADVENTHEALTH ORLANDO EOB CHILLER NO. 6 | 4598900% |  | JRC |  | WF1775101 | Mech | MAKE | ANSI 49 | 4626700% | 15 | 4597100% | 4597900% | 4598100% | FALSE | Nov-2025 | 10 | 7 | 6 | -1 | ON TIME | ON TIME | ON TIME BY ENG |  | C | -6 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4598207% | 100%
PZ4 | 0051378207 | 000270 | 0051378207-000270 | SUNY UPSTATE MEDICAL WEISKOTTEN HALL ADD | 4598900% |  | RAS | FRC | WF1775052 | Elec | BUY | ANSI 49 | 4605100% | 15 | 4597100% | 4598100% | 4597200% | FALSE | Nov-2025 | 10 | 9 | 2 | -7 | ON TIME | ON TIME | ON TIME BY ENG |  | x | -11 | NOT IMPACTED |  |  | Cancelled | ON TIME | NA | 0 | 4598142% | 0%
PZ4 | 0051659711 | 000090 | 0051659711-000090 | ADVENTHEALTH ORLANDO EOB CHILLER NO. 6 | 4598900% |  | JRC |  | WF1775087 | Mech | BUY | ANSI 49 | 4626700% | 15 | 4597100% | 4598100% | 4598100% | FALSE | Nov-2025 | 10 | 9 | 6 | -3 | ON TIME | ON TIME | ON TIME BY ENG |  | C | -6 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 17 | 4598142% | 100%
PZ4 | 0051024393 | 000310 | 0051024393-000310 | HF CURREN AWTP MASTER PLAN IMPROVEMENTS | 4601300% | 4600600% | HMA | ISQ | WF1775291 | Elec | MAKE | ANSI 61 | 4608300% | 31 | 4597100% | 4598000% | 4600100% | FALSE | Nov-2025 | 10 | 8 | 20 | 12 | LATE | LATE | ON TIME BY ENG |  | C | -8 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4598307% | 100%
PZ4 | 0051659711 | 000090 | 0051659711-000060 | ADVENTHEALTH ORLANDO EOB CHILLER NO. 6 | 4598900% |  | JRC | CML | WF1775784 | Mech | MAKE | ANSI 49 | 4626700% | 14 | 4597200% | 4597900% | 4597800% | FALSE | Nov-2025 | 10 | 6 | 4 | -2 | ON TIME | ON TIME | ON TIME BY ENG |  | C | -7 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4598207% | 100%
PZ4 | 0051378207 | 000270 | 0051378207-000270 | SUNY UPSTATE MEDICAL WEISKOTTEN HALL ADD | 4598900% |  | RAS | FRC | WF1775909 | Mech | MAKE | ANSI 49 | 4626700% | 14 | 4597200% | 4598000% | 4597300% | FALSE | Nov-2025 | 10 | 7 | 2 | -5 | ON TIME | ON TIME | ON TIME BY ENG |  | x | -10 | NOT IMPACTED |  |  | Cancelled | ON TIME | NA | 0 | 4598307% | 0%
PZ4 | 0051378207 | 000270 | 0051378207-000270 | SUNY UPSTATE MEDICAL WEISKOTTEN HALL ADD | 4598900% |  | RAS | FRC | WF1775912 | Mech | MAKE | ANSI 49 | 4626700% | 14 | 4597200% | 4598000% |  | TRUE | Nov-2025 | 10 | 7 | 86 | 79 | LATE | SUPER LATE | ON TIME BY ENG |  | X | 76 | IMPACTED |  | PN active in existing WF | Cancelled | LATE | NA | 0 | 4598307% | 0%
PZ4 | 0051378207 | 000270 | 0051378207-000270 | SUNY UPSTATE MEDICAL WEISKOTTEN HALL ADD | 4598900% |  | RAS | FRC | WF1775913 | Mech | MAKE | ANSI 49 | 4626700% | 14 | 4597200% | 4598000% | 4598300% | FALSE | Nov-2025 | 10 | 7 | 6 | -1 | ON TIME | ON TIME | ON TIME BY ENG |  | C | -5 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4598307% | 100%
PZ4 | 0051041146 | 000100 | 0051041146-000100 | BETTIS LAB CTC | 4598900% |  | ASP |  | WF1775950 | Elec | MAKE | ANSI 49 | 4632800% | 14 | 4597200% | 4598100% | 4598700% | FALSE | Nov-2025 | 10 | 8 | 9 | 1 | LATE | LATE | ON TIME BY ENG |  | C | -3 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4598407% | 100%
PZ4 | 0051659711 | 000090 | 0051659711-000060 | ADVENTHEALTH ORLANDO EOB CHILLER NO. 6 | 4598900% |  | JRC | CML | WF1775782 | Mech | BUY | ANSI 49 | 4626700% | 14 | 4597200% | 4598200% | 4597300% | FALSE | Nov-2025 | 10 | 9 | 2 | -7 | ON TIME | ON TIME | ON TIME BY ENG |  | X | -10 | NOT IMPACTED |  | One Shuttle error | Cancelled | ON TIME | NA | 0 | 4598242% | 0%
PZ4 | 0051041146 | 000100 | 0051041146-000100 | BETTIS LAB CTC | 4598900% |  | ASP |  | WF1775901 | Elec | BUY | ANSI 49 | 4632800% | 14 | 4597200% | 4598200% | 4598100% | FALSE | Nov-2025 | 10 | 9 | 5 | -4 | ON TIME | ON TIME | ON TIME BY ENG |  | C | -6 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 17 | 4598242% | 100%
PZ4 | 0051378207 | 000270 | 0051378207-000270 | SUNY UPSTATE MEDICAL WEISKOTTEN HALL ADD | 4598900% |  | RAS | FRC | WF1775890 | Mech | BUY | ANSI 49 | 4626700% | 14 | 4597200% | 4598200% | 4598100% | FALSE | Nov-2025 | 10 | 9 | 5 | -4 | ON TIME | ON TIME | ON TIME BY ENG |  | C | -6 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 17 | 4598242% | 100%
PZ4 | 0051041146 | 000100 | 0051041146-000100 | BETTIS LAB CTC | 4598900% |  | ASP |  | WF1775947 | Elec | BUY | ANSI 49 | 4632800% | 14 | 4597200% | 4598600% | 4598700% | FALSE | Nov-2025 | 10 | 11 | 9 | -2 | ON TIME | ON TIME | ON TIME BY ENG |  | C | -3 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 17 | 4598642% | 100%
PZ4 | 0051378207 | 000270 | 0051378207-000270 | SUNY UPSTATE MEDICAL WEISKOTTEN HALL ADD | 4598900% |  | RAS | FRC | WF1776319 | Mech | MAKE | ANSI 49 | 4626700% | 13 | 4597300% | 4598000% | 4598500% | FALSE | Nov-2025 | 10 | 6 | 6 | 0 | ON TIME | ON TIME | ON TIME BY ENG |  | C | -5 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4598307% | 100%
PZ4 | 0051378207 | 000270 | 0051378207-000270 | SUNY UPSTATE MEDICAL WEISKOTTEN HALL ADD | 4598900% |  | RAS | FRC | WF1776454 | Elec | MAKE | ANSI 49 | 4626700% | 13 | 4597300% | 4598100% | 4598200% | FALSE | Nov-2025 | 10 | 7 | 5 | -2 | ON TIME | ON TIME | ON TIME BY ENG |  | C | -6 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4598407% | 100%
PZ4 | 0051659722 | 000090 | 0051659722-000090 | AHO EOB CHILLER NO. 7 | 4598900% |  | JRC |  | WF1776233 | Mech | BUY | ANSI 49 | 4629700% | 13 | 4597300% | 4598500% | 4597400% | FALSE | Nov-2025 | 10 | 9 | 2 | -7 | ON TIME | ON TIME | ON TIME BY ENG |  | X | -9 | NOT IMPACTED |  |  | Cancelled | ON TIME | NA | 0 | 4598542% | 0%
PZ4 | 0051378207 | 000270 | 0051378207-000270 | SUNY UPSTATE MEDICAL WEISKOTTEN HALL ADD | 4598900% |  | RAS | FRC | WF1776452 | Elec | BUY | ANSI 49 | 4626700% | 13 | 4597300% | 4598500% | 4598000% | FALSE | Nov-2025 | 10 | 9 | 4 | -5 | ON TIME | ON TIME | ON TIME BY ENG |  | C | -6 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 17 | 4598542% | 100%
PZ4 | 0051679732 | 000030 | 0051679732-000030 | AT&T 105 AUD – 9TH FLOOR SOUTH AON CLOUD | 4599900% |  | DRV |  | WF1776468 | Elec | MAKE | ANSI 49 | 4607600% | 19 | 4597300% | 4598100% | 4598500% | FALSE | Nov-2025 | 10 | 7 | 6 | -1 | ON TIME | ON TIME | ON TIME BY ENG |  | X | -11 | NOT IMPACTED |  |  | Cancelled | ON TIME | NA | 0 | 4598407% | 0%
PZ4 | 0051679732 | 000030 | 0051679732-000030 | AT&T 105 AUD – 9TH FLOOR SOUTH AON CLOUD | 4599900% |  | DRV |  | WF1776462 | Elec | BUY | ANSI 49 | 4607600% | 19 | 4597300% | 4598500% | 4598500% | FALSE | Nov-2025 | 10 | 9 | 6 | -3 | ON TIME | ON TIME | ON TIME BY ENG |  | X | -11 | NOT IMPACTED |  |  | Cancelled | ON TIME | NA | 1 | 4598542% | 5.882%
PZ4 | 0051442285 | 000070 | 0051442285-000070 | GIGABAY 15KV SUBSTATIONS REV3 STARBASE T | 4594700% |  | DEV | KGF | WF1777034 | Elec | BUY | RAL9003 | 4600800% | -20 | 4597400% | 4598600% | 4598000% | FALSE | Nov-2025 | 10 | 9 | 3 | -6 | ON TIME | ON TIME | LATE BY ENG |  | C | 21 | IMPACTED |  |  | Closed | LATE | NA | 17 | 4598642% | 100%
PZ4 | 0051648563 | 000070 | 0051648563-000070 | ENCORE WIRE NEW PLANT 5 MCKINNEY | 4598100% |  | JAV | ISQ | WF1776983 | Mech | MAKE | ANSI 49 | 4603500% | 6 | 4597400% | 4598100% | 4598100% | FALSE | Nov-2025 | 10 | 6 | 3 | -3 | ON TIME | ON TIME | LATE BY ENG |  | C | 0 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4598407% | 100%
PZ4 | 0051659722 | 000090 | 0051659722-000090 | AHO EOB CHILLER NO. 7 | 4598900% |  | JRC | CML | WF1776893 | Mech | MAKE | ANSI 49 | 4629700% | 12 | 4597400% | 4598100% | 4598500% | FALSE | Nov-2025 | 10 | 6 | 5 | -1 | ON TIME | ON TIME | ON TIME BY ENG |  | C | -5 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4598407% | 100%
PZ4 | 0051659722 | 000090 | 0051659722-000090 | AHO EOB CHILLER NO. 7 | 4598900% |  | JRC | CML | WF1777092 | Mech | MAKE | ANSI 49 | 4629700% | 12 | 4597400% | 4598200% | 4598100% | FALSE | Nov-2025 | 10 | 7 | 3 | -4 | ON TIME | ON TIME | ON TIME BY ENG |  | C | -6 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4598507% | 100%
PZ4 | 0051041146 | 000100 | 0051041146-000100 | BETTIS LAB CTC | 4598900% |  | ASP |  | WF1777247 | Mech | MAKE | ANSI 49 | 4632800% | 12 | 4597400% | 4598500% | 4598200% | FALSE | Nov-2025 | 10 | 8 | 4 | -4 | ON TIME | ON TIME | ON TIME BY ENG |  | C | -6 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4598807% | 100%
PZ4 | 0051095105 | 000410 | 0051095105-000410 | GSK MARIETTA B55 | 4599600% |  | JAM | OAL | WF1776965 | Elec | BUY | ANSI 49 | 4607100% | 17 | 4597400% | 4598600% | 4598000% | FALSE | Nov-2025 | 10 | 9 | 3 | -6 | ON TIME | ON TIME | ON TIME BY ENG |  | C | -11 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 17 | 4598642% | 100%
PZ4 | 0051024393 | 000310 | 0051024393-000310 | HF CURREN AWTP MASTER PLAN IMPROVEMENTS | 4601300% | 4600600% | HMA | ISQ | WF1777059 | Elec | BUY | ANSI 61 | 4608300% | 28 | 4597400% | 4598600% | 4600100% | FALSE | Nov-2025 | 10 | 9 | 17 | 8 | LATE | LATE | ON TIME BY ENG |  | C | -8 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 17 | 4598642% | 100%
PZ4 | 0051378207 | 000270 | 0051378207-000270 | SUNY UPSTATE MEDICAL WEISKOTTEN HALL ADD | 4598900% |  | RAS | FRC | WF1777521 | Mech | MAKE | ANSI 49 | 4606200% | 11 | 4597500% | 4598200% | 4598200% | FALSE | Nov-2025 | 10 | 6 | 3 | -3 | ON TIME | ON TIME | ON TIME BY ENG |  | C | -6 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4598507% | 100%
PZ4 | 0051024393 | 000310 | 0051024393-000310 | HF CURREN AWTP MASTER PLAN IMPROVEMENTS | 4601300% |  | HMA |  | WF1777613 | Elec | BUY | ANSI 61 | 4609000% | 27 | 4597500% | 4598700% | 4598500% | FALSE | Nov-2025 | 10 | 9 | 4 | -5 | ON TIME | ON TIME | ON TIME BY ENG |  | C | -20 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 17 | 4598742% | 100%
PZ4 | 0051275480 | 000950 | 0051275480-000950 | TAYLOR DAIRY ROAD WTP | 4602000% | 4600900% | OAC |  | WF1777619 | Elec | MAKE | ANSI 49 | 5112700% | 32 | 4597500% | 4598200% | 4600300% | FALSE | Nov-2025 | 10 | 6 | 17 | 11 | LATE | LATE | ON TIME BY ENG |  | C | -9 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4598507% | 100%
PZ4 | 0051095105 | 000410 | 0051095105-000410 | GSK MARIETTA B55 | 4599600% |  | JAM | OAL | WF1778438 | Mech | BUY | ANSI 49 | 4607100% | 15 | 4597800% | 4598600% | 4599200% | FALSE | Nov-2025 | 10 | 7 | 8 | 1 | LATE | LATE | ON TIME BY ENG |  | C | -5 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 17 | 4598642% | 100%
PZ4 | 0051095105 | 000410 | 0051095105-000410 | GSK MARIETTA B55 | 4599600% |  | JAM | OAL | WF1778331 | Elec | BUY | ANSI 49 | 4607100% | 15 | 4597800% | 4598800% | 4598500% | FALSE | Nov-2025 | 10 | 9 | 3 | -6 | ON TIME | ON TIME | ON TIME BY ENG |  | C | -10 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 17 | 4598842% | 100%
PZ4 | 0051095105 | 000410 | 0051095105-000410 | GSK MARIETTA B55 | 4599600% |  | JAM | OAL | WF1778342 | Elec | BUY | ANSI 49 | 4607100% | 15 | 4597800% | 4598800% | 4598700% | FALSE | Nov-2025 | 10 | 9 | 5 | -4 | ON TIME | ON TIME | ON TIME BY ENG |  | C | -8 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 17 | 4598842% | 100%
PZ4 | 0051129914 | 000750&760 | 0051129914-000750&760 | LOUISA COUNTY TECH CAMHUPS | 4602000% | 4600900% | UFA | AL | WF1778288 | Elec | MAKE | ANSI 49 | 4601400% | 31 | 4597800% | 4598500% | 4599900% | FALSE | Nov-2025 | 10 | 6 | 13 | 7 | LATE | LATE | ON TIME BY ENG |  | C | -13 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4598807% | 100%
PZ4 | 0051129914 | 000750&760 | 0051129914-000750&760 | LOUISA COUNTY TECH CAMHUPS | 4602000% | 4600900% | UFA | AL | WF1778302 | Elec | MAKE | ANSI 49 | 4601400% | 31 | 4597800% | 4598500% | 4599900% | FALSE | Nov-2025 | 10 | 6 | 13 | 7 | LATE | LATE | ON TIME BY ENG |  | C | -13 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4598807% | 100%
PZ4 | 0051129914 | 000750&760 | 0051129914-000750&760 | LOUISA COUNTY TECH CAMHUPS | 4602000% | 4600900% | UFA | AL | WF1778312 | Elec | MAKE | ANSI 49 | 4601400% | 31 | 4597800% | 4598500% | 4600200% | FALSE | Nov-2025 | 10 | 6 | 16 | 10 | LATE | LATE | ON TIME BY ENG |  | C | -10 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4598807% | 100%
PZ4 | 0051129914 | 000750&760 | 0051129914-000750&760 | LOUISA COUNTY TECH CAMHUPS | 4602000% | 4600900% | UFA | AL | WF1778278 | Elec | BUY | ANSI 49 | 4601400% | 31 | 4597800% | 4598800% | 4599900% | FALSE | Nov-2025 | 10 | 9 | 13 | 4 | LATE | LATE | ON TIME BY ENG |  | C | -13 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 17 | 4598842% | 100%
PZ4 | 0051095105 | 000400 | 0051095105-000400 | GSK MARIETTA B55 | 4599600% | 4598900% | JAM | LDT | WF1779134 | Mech | MAKE | ANSI 49 | 4609800% | 14 | 4597900% | 4598700% | 4599200% | FALSE | Nov-2025 | 10 | 7 | 8 | 1 | LATE | LATE | ON TIME BY ENG |  | C | -5 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4599007% | 100%
PZ4 | 0011981626 | 000120 | 0011981626-000120 | GENENTECH - APOLLO 11 - EQUIPMENT | 4602800% | 4602800% | KYC | ODE | WF1779165 | Elec | MAKE | ANSI 61 | 4607700% | 36 | 4597900% | 4598700% | 4600900% | FALSE | Nov-2025 | 10 | 7 | 20 | 13 | LATE | LATE | ON TIME BY ENG |  | C | -11 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4599007% | 100%
PZ4 | 0011981626 | 000120 | 0011981626-000120 | GENENTECH - APOLLO 11 - EQUIPMENT | 4602800% | 4602800% | KYC | ODE | WF1779166 | Elec | MAKE | ANSI 61 | 4607700% | 36 | 4597900% | 4598700% | 4600800% | FALSE | Nov-2025 | 10 | 7 | 19 | 12 | LATE | LATE | ON TIME BY ENG |  | C | -12 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4599007% | 100%
PZ4 | 0011981626 | 000120 | 0011981626-000120 | GENENTECH - APOLLO 11 - EQUIPMENT | 4602800% | 4602800% | KYC | ODE | WF1779138 | Elec | MAKE | ANSI 61 | 4607700% | 36 | 4597900% | 4601700% | 4600800% | FALSE | Nov-2025 | 10 | 29 | 19 | -10 | ON TIME | ON TIME | ON TIME BY ENG |  | C | -12 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4602007% | 100%
PZ4 | 0050202444 | 000260 | 0050202444-000260 | NORTHROP B421 PHASE 3 COATING HANGAR | 4563800% |  | UFA | KGF | WF1779746 | Elec | BUY | ANSI 49 | 4574100% | -234 | 4598000% | 4599200% | 4598700% | FALSE | Nov-2025 | 10 | 7 | 4 | -3 | ON TIME | ON TIME | LATE BY ENG |  | C | 238 | IMPACTED |  |  | Closed | LATE | NA | 17 | 4599242% | 100%
PZ4 | 0051027340 | 000100 | 0051027340-000100 | PSTV CC NORMAL GEAR REPLACEMENT - PSVMC | 4589800% |  | MGL | FRC | WF1779671 | Elec | Buy | ANSI 49 | 4600200% | -55 | 4598000% | 4599200% | 4598700% | FALSE | Nov-2025 | 10 | 7 | 4 | -3 | ON TIME | ON TIME | LATE BY ENG |  | C | 59 | IMPACTED |  |  | Closed | LATE | NA | 17 | 4599242% | 100%
PZ4 | 0051095105 | 000400 | 0051095105-000400 | GSK MARIETTA B55 | 4600000% |  | JAM | LDT | WF1779672 | Mech | MAKE | ANSI 49 | 4609800% | 15 | 4598000% | 4598700% | 4601700% | FALSE | Nov-2025 | 10 | 6 | 23 | 17 | LATE | SUPER LATE | ON TIME BY ENG |  | C | 11 | IMPACTED |  |  | Closed | LATE | NA | 18 | 4599007% | 100%
QED2 | SWBD | META | SWBD-META | META - DC FV2.0 - LEB - NW BUILDING (LV) | 4600600% | 4600600% | ALT | AL | WF1779687 | Elec | BUY | ANSI 49 | 4600600% | 19 | 4598000% | 4599200% | 4600000% | FALSE | Nov-2025 | 10 | 9 | 13 | 4 | LATE | LATE | ON TIME BY ENG |  | C | -4 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 17 | 4599242% | 100%
PZ4 | 0051647770 | 000010 | 0051647770-000010 | SCHNEIDER ELECTRIC USA INC | 4602900% |  | DEV | VHL | WF1779839 | Elec | MAKE | ANSI 49 | 4606400% | 36 | 4598000% | 4598800% | 4599300% | FALSE | Nov-2025 | 10 | 7 | 8 | 1 | LATE | LATE | ON TIME BY ENG |  | C | -23 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4599107% | 100%
PZ4 | 0051647770 | 000010 | 0051647770-000010 | SCHNEIDER ELECTRIC USA INC | 4602900% | 4599300% | DEV | VHL | WF1779843 | Elec | MAKE | ANSI 49 | 4606400% | 36 | 4598000% | 4598800% | 4599600% | FALSE | Nov-2025 | 10 | 7 | 11 | 4 | LATE | LATE | ON TIME BY ENG |  | C | -20 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4599107% | 100%
PZ4 | 0051647770 | 000010 | 0051647770-000010 | SCHNEIDER ELECTRIC USA INC | 4602900% | 4599300% | DEV | VHL | WF1779840 | Elec | BUY | ANSI 49 | 4606400% | 36 | 4598000% | 4599200% | 4599500% | FALSE | Nov-2025 | 10 | 9 | 10 | 1 | LATE | LATE | ON TIME BY ENG |  | C | -21 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 17 | 4599242% | 100%
PZ4 | 0050927776 | 000950 | 0050927776-000950 | REPLACE NETWORK SUBSTATIONS 9A,9B,9C,9D | 4601400% | 4600900% | ASP | CML | WF1780475 | Elec | MAKE | ANSI 49 | 4628700% | 24 | 4598100% | 4598900% | 4600800% | FALSE | Nov-2025 | 10 | 7 | 18 | 11 | LATE | LATE | ON TIME BY ENG |  | C | -5 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4599207% | 100%
PZ4 | 0050927776 | 000950 | 0050927776-000950 | REPLACE NETWORK SUBSTATIONS 9A,9B,9C,9D | 4601400% | 4600900% | ASP | CML | WF1780466 | Elec | BUY | ANSI 49 | 4628700% | 24 | 4598100% | 4599300% | 4600200% | FALSE | Nov-2025 | 10 | 9 | 15 | 6 | LATE | LATE | ON TIME BY ENG |  | C | -8 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 17 | 4599342% | 100%
PZ4 | 0051647770 | 000010 | 0051647770-000010 | SCHNEIDER ELECTRIC USA INC | 4602900% |  | DEV | VHL | WF1780471 | Elec | MAKE | ANSI 49 | 4606400% | 35 | 4598100% | 4598900% | 4598700% | FALSE | Nov-2025 | 10 | 7 | 4 | -3 | ON TIME | ON TIME | ON TIME BY ENG |  | C | -27 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4599207% | 100%
PZ4 | 0051647770 | 000010 | 0051647770-000010 | SCHNEIDER ELECTRIC USA INC | 4602900% | 4599300% | DEV | VHL | WF1780880 | Mech | MAKE | ANSI 49 | 4569900% | 34 | 4598200% | 4598900% | 4600200% | FALSE | Nov-2025 | 10 | 6 | 15 | 9 | LATE | LATE | ON TIME BY ENG |  | C | -16 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4599207% | 100%
PZ4 | 0051129914 | 000750&760 | 0051129914-000750&760 | LOUISA COUNTY TECH CAMHUPS | 4602000% | 4600900% | UFA | AL | WF1780890 | Elec | MAKE | ANSI 49 | 4609800% | 27 | 4598200% | 4598900% | 4601300% | FALSE | Nov-2025 | 10 | 6 | 21 | 15 | LATE | SUPER LATE | ON TIME BY ENG |  | C | -4 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4599207% | 100%
PZ4 | 0051129914 | 000750&760 | 0051129914-000750&760 | LOUISA COUNTY TECH CAMHUPS | 4602000% | 4600900% | UFA | AL | WF1780874 | Elec | BUY | ANSI 49 | 4569800% | 27 | 4598200% | 4599400% | 4601000% | FALSE | Nov-2025 | 10 | 9 | 20 | 11 | LATE | LATE | ON TIME BY ENG |  | C | -5 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 17 | 4599442% | 100%
PZ4 | 0051024393 | 000310 | 0051024393-000310 | HF CURREN AWTP MASTER PLAN IMPROVEMENTS | 4601300% | 4600600% | ISQ | HMA | WF1781142 | Mech | MAKE | ANSI 61 | 4609700% | 21 | 4598400% | 4599300% | 4599600% | FALSE | Nov-2025 | 10 | 7 | 10 | 3 | LATE | LATE | ON TIME BY ENG |  | C | -11 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4599607% | 100%
PZ4 | 0051611250 | 003280 | 0051611250-003280 | TEMPLE UNIVERSITY LEW KLEIN COLLEGE OF M | 4599600% | 4599300% | ATA | HUP | WF1781872 | Mech | MAKE | ANSI 49 | 4610000% | 10 | 4598500% | 4599500% | 4599600% | FALSE | Nov-2025 | 10 | 9 | 10 | 1 | LATE | LATE | ON TIME BY ENG |  | C | 1 | IMPACTED |  |  | Closed | LATE | NA | 18 | 4599807% | 100%
PZ4 | 0051611250 | 003280 | 0051611250-003280 | TEMPLE UNIVERSITY LEW KLEIN COLLEGE OF M | 4599600% | 4599300% | ATA | HUP | WF1781856 | Mech | BUY | ANSI 49 | 4610000% | 10 | 4598500% | 4599900% | 4599600% | FALSE | Nov-2025 | 10 | 11 | 10 | -1 | ON TIME | ON TIME | ON TIME BY ENG |  | C | 1 | IMPACTED |  |  | Closed | LATE | NA | 17 | 4599942% | 100%
PZ4 | 0051095105 | 000410 | 0051095105-000410 | GSK MARIETTA B55 | 4599600% |  | JAM | OAL | WF1781485 | Elec | MAKE | ANSI 49 | 4607100% | 10 | 4598500% | 4601500% |  | TRUE | Nov-2025 | 10 | 23 | 80 | 57 | LATE | SUPER LATE | ON TIME BY ENG |  | X | 71 | IMPACTED |  |  | Cancelled | LATE | NA | 0 | 4601807% | 0%
PZ4 | 0051024393 | 000310 | 0051024393-000310 | HF CURREN AWTP MASTER PLAN IMPROVEMENTS | 4601300% |  | HMA | ISQ | WF1781932 | Elec | BUY | ANSI 61 | 4609700% | 21 | 4598500% | 4600000% | 4598600% | FALSE | Nov-2025 | 10 | 12 | 2 | -10 | ON TIME | ON TIME | ON TIME BY ENG |  | x | -19 | NOT IMPACTED |  |  | Cancelled | ON TIME | NA | 0 | 4600042% | 0%
PZ4 | 0051611250 | 003280 | 0051611250-003280 | TEMPLE UNIVERSITY LEW KLEIN COLLEGE OF M | 4599600% | 4599300% | ATA | HUP | WF1782397 | Mech | MAKE | ANSI 49 | 4610000% | 9 | 4598600% | 4599500% | 4599600% | FALSE | Nov-2025 | 10 | 8 | 9 | 1 | LATE | LATE | LATE BY ENG |  | C | 1 | IMPACTED |  |  | Closed | LATE | NA | 18 | 4599807% | 100%
PZ4 | 0051611250 | 003280 | 0051611250-003280 | TEMPLE UNIVERSITY LEW KLEIN COLLEGE OF M | 4599600% | 4599300% | ATA | HUP | WF1782400 | Mech | MAKE | ANSI 49 | 4610000% | 9 | 4598600% | 4599500% | 4599500% | FALSE | Nov-2025 | 10 | 8 | 8 | 0 | ON TIME | ON TIME | LATE BY ENG |  | C | -2 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4599807% | 100%
PZ4 | 0051611250 | 003280 | 0051611250-003280 | TEMPLE UNIVERSITY LEW KLEIN COLLEGE OF M | 4599600% |  | ATA | HUP | WF1782413 | Elec | MAKE | ANSI 49 | 4609000% | 9 | 4598600% | 4599500% | 4599200% | FALSE | Nov-2025 | 10 | 8 | 5 | -3 | ON TIME | ON TIME | LATE BY ENG |  | X | -5 | NOT IMPACTED |  | PN ACTIVE IN US23 | Cancelled | ON TIME | NA | 1 | 4599807% | 5.556%
PZ4 | 0051024393 | 000310 | 0051024393-000310 | HF CURREN AWTP MASTER PLAN IMPROVEMENTS | 4601300% | 4600600% | HMA | ISQ | WF1782615 | ELec | MAKE | ANSI 61 | 4609700% | 20 | 4598600% | 4599600% | 4599600% | FALSE | Nov-2025 | 10 | 9 | 9 | 0 | ON TIME | ON TIME | ON TIME BY ENG |  | C | -11 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4599907% | 100%
PZ4 | 0051611250 | 003280 | 0051611250-003280 | TEMPLE UNIVERSITY LEW KLEIN COLLEGE OF M | 4599600% | 4599300% | ATA | HUP | WF1783156 | Elec | BUY | ANSI 49 | 4610000% | 8 | 4598700% | 4599200% | 4599600% | FALSE | Nov-2025 | 10 | 4 | 8 | 4 | LATE | LATE | LATE BY ENG |  | C | 1 | IMPACTED |  |  | Closed | LATE | NA | 17 | 4599242% | 100%
PZ4 | 0051611250 | 003280 | 0051611250-003280 | TEMPLE UNIVERSITY LEW KLEIN COLLEGE OF M | 4599600% | 4599300% | ATA | HUP | WF1783445 | Elec | MAKE | ANSI 49 | 4610000% | 8 | 4598700% | 4599900% | 4599500% | FALSE | Nov-2025 | 10 | 9 | 7 | -2 | ON TIME | ON TIME | LATE BY ENG |  | C | -2 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4600207% | 100%
PZ4 | 0051436816 | 000030 | 0051436816-000030 | SPACEX STARBASE GIGABAY UNIT SUBSTATIONS | 4601700% | 4601000% | DMA | KGF | WF1783949 | Elec | MAKE | RAL9003 | 4607700% | 22 | 4598800% | 4599900% | 4600100% | FALSE | Nov-2025 | 10 | 8 | 10 | 2 | LATE | LATE | ON TIME BY ENG |  | C | -10 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4600207% | 100%
PZ4 | 0051436816 | 000030 | 0051436816-000030 | SPACEX STARBASE GIGABAY UNIT SUBSTATIONS | 4601700% | 4601000% | DMA | KGF | WF1784326 | Elec | MAKE | RAL9003 | 4607700% | 21 | 4598900% | 4599900% | 4600100% | FALSE | Nov-2025 | 10 | 7 | 9 | 2 | LATE | LATE | ON TIME BY ENG |  | C | -10 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4600207% | 100%
PZ4 | SPECIAL | KOMAX | SPECIAL-KOMAX | BUNDLE FOR KOMAX PZ4 | 4600000% | 4600000% | UFA | NA | WF1785225 | Elec | MAKE | NA | 4600000% | 7 | 4599200% | 4600100% | 4602800% | FALSE | Dec-2025 | 10 | 8 | 23 | 15 | LATE | SUPER LATE | LATE BY ENG |  | C | 17 | IMPACTED |  |  | Closed | LATE | NA | 18 | 4600407% | 100%
PZ4 | 0051611250 | 003280 | 0051611250-003280 | TEMPLE UNIVERSITY LEW KLEIN COLLEGE OF M | 4599600% | 4599300% | ATA | HUP | WF1784934 | Elec | BUY | ANSI 49 | 4610000% | 5 | 4599200% | 4599900% | 4599600% | FALSE | Dec-2025 | 10 | 6 | 5 | -1 | ON TIME | ON TIME | LATE BY ENG |  | C | 1 | IMPACTED |  |  | Closed | LATE | NA | 17 | 4599942% | 100%
PZ4 | 0051139077 | 000030&000110&000290 | 0051139077-000030&000110&000290 | NORTHROP B307 3000 KVA SUBSTATIONS - PAL | 4598500% |  | AOB | OAL | WF1785827 | Elec | BUY | ANSI 49 | 4602600% | -7 | 4599300% | 4600300% | 4599900% | FALSE | Dec-2025 | 10 | 9 | 5 | -4 | ON TIME | ON TIME | LATE BY ENG | OBSOLETE PN, SUPPLY REQUESTED A SPARE | C | 11 | IMPACTED |  |  | Closed | LATE | NA | 17 | 4600342% | 100%
PZ4 | 0051024393 | 000310 | 0051024393-000310 | HF CURREN AWTP MASTER PLAN IMPROVEMENTS | 4601300% | 4600600% | HMA | ISQ | WF1785844 | Mech | MAKE | ANSI 61 | 4609000% | 15 | 4599300% | 4600100% | 4599400% | FALSE | Dec-2025 | 10 | 7 | 2 | -5 | ON TIME | ON TIME | ON TIME BY ENG |  | x | -13 | NOT IMPACTED |  |  | Cancelled | ON TIME | NA | 0 | 4600407% | 0%
PZ4 | 0051436816 | 000030 | 0051436816-000030 | SPACEX STARBASE GIGABAY UNIT SUBSTATIONS | 4601700% | 4601000% | DMA | KGF | WF1785760 | Mech | MAKE | RAL9003 | 4609800% | 19 | 4599300% | 4600000% | 4600000% | FALSE | Dec-2025 | 10 | 6 | 6 | 0 | ON TIME | ON TIME | ON TIME BY ENG |  | C | -11 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4600307% | 100%
PZ4 | 0051436816 | 000030 | 0051436816-000030 | SPACEX STARBASE GIGABAY UNIT SUBSTATIONS | 4601700% | 4601000% | DMA | KGF | WF1785862 | Elec | BUY | RAL9003 | 4609100% | 19 | 4599300% | 4600300% | 4600900% | FALSE | Dec-2025 | 10 | 9 | 12 | 3 | LATE | LATE | ON TIME BY ENG |  | C | -5 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 17 | 4600342% | 100%
PZ4 | 0051095105 | 000410 | 0051095105-000410 | GSK MARIETTA B55 | 4599600% | 4598900% | JAM | OAL | WF1786267 | Elec | BUY | ANSI 49 | 4609800% | 3 | 4599400% | 4600600% | 4600000% | FALSE | Dec-2025 | 10 | 9 | 5 | -4 | ON TIME | ON TIME | LATE BY ENG |  | C | 3 | IMPACTED |  |  | Closed | LATE | NA | 17 | 4600642% | 100%
PZ4 | 0051436816 | 000130 | 0051436816-000130 | SPACEX STARBASE GIGABAY UNIT SUBSTATIONS | 4601700% | 4601000% | DMA | KGF | WF1786489 | Elec | MAKE | RAL9003 | 4613900% | 18 | 4599400% | 4600200% | 4600900% | FALSE | Dec-2025 | 10 | 7 | 11 | 4 | LATE | LATE | ON TIME BY ENG |  | C | -5 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4600507% | 100%
PZ4 | 0051436816 | 000130 | 0051436816-000130 | SPACEX STARBASE GIGABAY UNIT SUBSTATIONS | 4601700% | 4601000% | DMA | KGF | WF1786367 | Elec | BUY | RAL9003 | 4613900% | 18 | 4599400% | 4600600% | 4600200% | FALSE | Dec-2025 | 10 | 9 | 7 | -2 | ON TIME | ON TIME | ON TIME BY ENG |  | C | -9 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 17 | 4600642% | 100%
PZ4 | 0051620541 | 000010 | 0051620541-000010 | RAYTHEON - MARLBOROUGH - BUILDING 2 - PH | 4603800% |  | JRC |  | WF1786486 | Elec | Buy | ANSI 49 | 4612500% | 33 | 4599400% | 4600600% | 4599500% | FALSE | Dec-2025 | 10 | 9 | 2 | -7 | ON TIME | ON TIME | ON TIME BY ENG |  | X | -28 | NOT IMPACTED |  |  | Cancelled | ON TIME | NA | 0 | 4600642% | 0%
PZ4 | 0051620541 | 000010 | 0051620541-000010 | RAYTHEON - MARLBOROUGH - BUILDING 2 - PH | 4603800% | 4603100% | JRC |  | WF1787112 | Elec | MAKE | ANSI 49 | 4612800% | 32 | 4599500% | 4600200% | 4601700% | FALSE | Dec-2025 | 10 | 6 | 14 | 8 | LATE | LATE | ON TIME BY ENG |  | C | -15 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4600507% | 100%
QED2 | SWBD | META | SWBD-META | META F2.0 | 4600600% | 4600900% | ALT | AL | WF1787249 | Mech | BUY | ANSI 49 | 4600900% | 8 | 4599500% | 4599900% | 4600000% | FALSE | Dec-2025 | 5 | 3 | 4 | 1 | LATE | LATE | ON TIME BY ENG |  | C | -4 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 9 | 4599942% | 52.94%
QED2 | SWBD | META | SWBD-META | META F2.0 | 4600600% | 4600600% | ALT | AL | WF1787231 | Mech | MAKE | ANSI 49 | 4600900% | 8 | 4599500% | 4600600% | 4599900% | FALSE | Dec-2025 | 5 | 8 | 3 | -5 | ON TIME | ON TIME | ON TIME BY ENG |  | C | -5 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4600907% | 100%
PZ4 | 0051024393 | 000310 | 0051024393-000310 | HF CURREN AWTP MASTER PLAN IMPROVEMENTS | 4601300% | 4600600% | HMA | ISQ | WF1786894 | Elec | MAKE | ANSI 61 | 4608300% | 13 | 4599500% | 4600200% | 4600800% | FALSE | Dec-2025 | 10 | 6 | 9 | 3 | LATE | LATE | ON TIME BY ENG |  | C | -4 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4600507% | 100%
PZ4 | 0051436816 | 000080 | 0051436816-000080 | SPACEX STARBASE GIGABAY UNIT SUBSTATIONS | 4602000% | 4601300% | DEV | VHL | WF1787624 | Elec | MAKE | RAL9003 | 4609200% | 17 | 4599600% | 4600300% | 4600800% | FALSE | Dec-2025 | 10 | 6 | 8 | 2 | LATE | LATE | ON TIME BY ENG |  | C | -7 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4600607% | 100%
PZ4 | 0051436816 | 000030 | 0051436816-000030 | SPACEX STARBASE GIGABAY UNIT SUBSTATIONS | 4601700% | 4601000% | DMA | KGF | WF1787536 | Elec | BUY | RAL9003 | 4609800% | 16 | 4599600% | 4600800% | 4600900% | FALSE | Dec-2025 | 10 | 9 | 9 | 0 | ON TIME | ON TIME | ON TIME BY ENG |  | C | -5 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 17 | 4600842% | 100%
PZ4 | 0051549615 | 000430 | 0051549615-000430 | GENENTECH - APOLLO 11 - EQUIPMENT | 4602800% | 4617400% | KYC | ODE | WF1787873 | Mech | MAKE | ANSI 61 | 4607700% | 22 | 4599800% | 4600600% | 4600800% | FALSE | Dec-2025 | 10 | 6 | 7 | 1 | LATE | LATE | ON TIME BY ENG |  | C | -12 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4600907% | 100%
PZ4 | 0051549615 | 000430 | 0051549615-000430 | GENENTECH - APOLLO 11 - EQUIPMENT | 4602800% | 4602800% | KYC | ODE | WF1787889 | Mech | MAKE | ANSI 49 | 4607700% | 22 | 4599800% | 4600700% | 4600400% | FALSE | Dec-2025 | 10 | 7 | 4 | -3 | ON TIME | ON TIME | ON TIME BY ENG |  | C | -14 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4601007% | 100%
PZ4 | 0050988425 | 001260 | 0050988425-001260 | DC TILLMAN | 4594400% |  | KYC | OAL | WF1788498 | Elec | MAKE | ANSI 49 | 4600200% | -40 | 4599900% | 4600800% | 4600200% | FALSE | Dec-2025 | 10 | 8 | 4 | -4 | ON TIME | ON TIME | LATE BY ENG |  | C | 39 | IMPACTED |  |  | Closed | LATE | NA | 18 | 4601107% | 100%
PZ4 | 0051549615 | 000430 | 0051549615-000430 | GENENTECH - APOLLO 11 - EQUIPMENT | 4602800% | 4602800% | KYC | ODE | WF1788202 | Mech | MAKE | ANSI 61 | 4607700% | 22 | 4599900% | 4600600% | 4600900% | FALSE | Dec-2025 | 10 | 6 | 8 | 2 | LATE | LATE | ON TIME BY ENG |  | C | -11 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4600907% | 100%
PZ4 | 0051549615 | 000430 | 0051549615-000430 | GENENTECH - APOLLO 11 - EQUIPMENT | 4602800% | 4602800% | KYC | ODE | WF1788225 | Mech | MAKE | ANSI 61 | 4607700% | 22 | 4599900% | 4600600% | 4600900% | FALSE | Dec-2025 | 10 | 6 | 8 | 2 | LATE | LATE | ON TIME BY ENG |  | C | -11 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4600907% | 100%
PZ4 | 0051611250 | 003280 | 0051611250-003280 | TEMPLE UNIVERSITY LEW KLEIN COLLEGE OF M | 4599600% | 4599300% | ATA | HUP | WF1789259 | Mech | MAKE | ANSI 49 | 4606600% | -3 | 4600000% | 4600800% | 4600900% | FALSE | Dec-2025 | 10 | 7 | 7 | 0 | ON TIME | ON TIME | LATE BY ENG |  | C | 9 | IMPACTED |  |  | Closed | LATE | NA | 18 | 4601107% | 100%
PZ4 | 0051611250 | 003280 | 0051611250-003280 | TEMPLE UNIVERSITY LEW KLEIN COLLEGE OF M | 4599600% | 4599300% | ATA | HUP | WF1789252 | Mech | MAKE | ANSI 49 | 4606600% | -3 | 4600000% | 4600800% | 4601300% | FALSE | Dec-2025 | 10 | 7 | 9 | 2 | LATE | LATE | LATE BY ENG |  | C | 11 | IMPACTED |  |  | Closed | LATE | NA | 18 | 4601107% | 100%
PZ4 | 0051611250 | 003280 | 0051611250-003280 | TEMPLE UNIVERSITY LEW KLEIN COLLEGE OF M | 4599600% | 4599300% | ATA | HUP | WF1789256 | Mech | BUY | ANSI 49 | 4606600% | -3 | 4600000% | 4601000% | 4601300% | FALSE | Dec-2025 | 10 | 9 | 9 | 0 | ON TIME | ON TIME | LATE BY ENG |  | C | 11 | IMPACTED |  |  | Closed | LATE | NA | 17 | 4601042% | 100%
PZ4 | 0051024393 | 00310 | 0051024393-00310 | HF CURREN AWTP MASTER PLAN IMPROVEMENTS | 4601300% | 4600600% | HMA | ISQ | WF1789752 | Mech | MAKE | ANSI 61 | 4608300% | 9 | 4600100% | 4600800% | 4600800% | FALSE | Dec-2025 | 10 | 6 | 5 | -1 | ON TIME | ON TIME | LATE BY ENG |  | C | -4 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4601107% | 100%
PZ4 | 0051129914 | 000760 | 0051129914-000760 | LOUISA COUNTY TECH CAMHUPS | 4602000% | 4601000% | UFA | AL | WF1790024 | Mech | MAKE | ANSI 49 | 4608400% | 14 | 4600100% | 4600900% | 4602800% | FALSE | Dec-2025 | 10 | 7 | 16 | 9 | LATE | LATE | ON TIME BY ENG |  | C | 6 | IMPACTED |  |  | Closed | LATE | NA | 18 | 4601207% | 100%
PZ4 | 0051129914 | 000750&760 | 0051129914-000750&760 | LOUISA COUNTY TECH CAMHUPS | 4602000% | 4600900% | UFA | AL | WF1789788 | Elec | Buy | ANSI 49 | 4608400% | 14 | 4600100% | 4601300% | 4601400% | FALSE | Dec-2025 | 10 | 9 | 9 | 0 | ON TIME | ON TIME | ON TIME BY ENG |  | C | -3 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 17 | 4601342% | 100%
PZ4 | 0051129914 | 000760 | 0051129914-000760 | LOUISA COUNTY TECH CAMHUPS | 4602000% | 4601000% | UFA | AL | WF1790023 | Mech | Buy | ANSI 49 | 4608400% | 14 | 4600100% | 4601300% | 4601300% | FALSE | Dec-2025 | 10 | 9 | 8 | -1 | ON TIME | ON TIME | ON TIME BY ENG |  | C | -4 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 17 | 4601342% | 100%
PZ4 | 0050927776 | 000950 | 0050927776-000950 | REPLACE NETWORK SUBSTATIONS 9A,9B,9C,9D | 4601700% | 4600900% | ASP | CML | WF1789889 | Mech | MAKE | ANSI 49 | 4631100% | 13 | 4600100% | 4600800% | 4603400% | FALSE | Dec-2025 | 10 | 6 | 20 | 14 | LATE | LATE | ON TIME BY ENG |  | C | 11 | IMPACTED |  |  | Closed | LATE | NA | 18 | 4601107% | 100%
PZ4 | 0051536680 | 000150 | 0051536680-000150 | UNITEDHEALTH GROUP CUL PROJECT, CHASKA, | 4592200% | 4592500% | DRV | ISQ | WF1789969 | Mech | MAKE | ANSI 49 | 4602000% | -58 | 4600100% | 4600800% | 4600600% | FALSE | Dec-2025 | 10 | 6 | 3 | -3 | ON TIME | ON TIME | LATE BY ENG |  | C | 56 | IMPACTED |  |  | Closed | LATE | NA | 18 | 4601107% | 100%
PZ4 | 0050927776 | 000950 | 0050927776-000950 | REPLACE NETWORK SUBSTATIONS 9A,9B,9C,9D | 4601700% | 4600900% | ASP | CML | WF1789875 | Mech | MAKE | ANSI 49 | 4631100% | 13 | 4600100% | 4600800% | 4603500% | FALSE | Dec-2025 | 10 | 6 | 21 | 15 | LATE | SUPER LATE | ON TIME BY ENG |  | C | 12 | IMPACTED |  |  | Closed | LATE | NA | 18 | 4601107% | 100%
PZ4 | 0051611250 | 003280 | 0051611250-003280 | TEMPLE UNIVERSITY LEW KLEIN COLLEGE OF M | 4599600% | 4599300% | ATA | HUP | WF1790513 | Mech | MAKE | ANSI 49 | 4606600% | -5 | 4600200% | 4600900% | 4601300% | FALSE | Dec-2025 | 10 | 6 | 7 | 1 | LATE | LATE | LATE BY ENG |  | C | 11 | IMPACTED |  |  | Closed | LATE | NA | 18 | 4601207% | 100%
PZ4 | 0051611250 | 003280 | 0051611250-003280 | TEMPLE UNIVERSITY LEW KLEIN COLLEGE OF M | 4599600% | 4599300% | ATA | HUP | WF1790597 | Mech | Buy | ANSI 49 | 4606600% | -5 | 4600200% | 4601400% | 4600300% | FALSE | Dec-2025 | 10 | 9 | 1 | -8 | ON TIME | ON TIME | LATE BY ENG |  | X | 5 | IMPACTED |  |  | Cancelled | LATE | NA | 3 | 4601442% | 17.65%
PZ4 | 0051611250 | 003280 | 0051611250-003280 | TEMPLE UNIVERSITY LEW KLEIN COLLEGE OF M | 4599600% | 4599300% | ATA | HUP | WF1790621 | Mech | MAKE | ANSI 49 | 4606600% | -5 | 4600200% | 4600900% | 4601300% | FALSE | Dec-2025 | 10 | 6 | 7 | 1 | LATE | LATE | LATE BY ENG |  | C | 11 | IMPACTED |  |  | Closed | LATE | NA | 18 | 4601207% | 100%
PZ4 | 0051615853 | 000100 | 0051615853-000100 | SPACEX CAPE GIGABAY M1/M2 UNIT SUBSTATIO | 4602000% | 4602000% | DEV | KGF | WF1790543 | Elec | MAKE | RAL9003 | 4613900% | 13 | 4600200% | 4600900% | 4601300% | FALSE | Dec-2025 | 10 | 6 | 7 | 1 | LATE | LATE | ON TIME BY ENG |  | C | -4 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4601207% | 100%
PZ4 | 0050829646 | 001060&001080 | 0050829646-001060&001080 | AT&T : 51 PEACHTREE CENTER AVE SE ATL | 4604400% | 4601300% | DRV |  | WF1790561 | Elec | MAKE | ANSI 49 | 4613400% | 31 | 4600200% | 4600900% | 4601200% | FALSE | Dec-2025 | 10 | 6 | 6 | 0 | ON TIME | ON TIME | ON TIME BY ENG |  | C | -21 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4601207% | 100%
PZ4 | 0050927776 | 000950 | 0050927776-000950 | REPLACE NETWORK SUBSTATIONS 9A,9B,9C,9D | 4601400% | 4600900% | ASP | CML | WF1790595 | Mech | BUY | ANSI 49 | 4630800% | 9 | 4600200% | 4601400% | 4600800% | FALSE | Dec-2025 | 10 | 9 | 4 | -5 | ON TIME | ON TIME | LATE BY ENG |  | X | -5 | NOT IMPACTED |  |  | Cancelled | ON TIME | NA | 16 | 4601442% | 94.12%
PZ4 | 0051611250 | 003280 | 0051611250-003280 | TEMPLE UNIVERSITY LEW KLEIN COLLEGE OF M | 4599600% | 4599300% | ATA | HUP | WF1790575 | Mech | BUY | ANSI 49 | 4606600% | -5 | 4600200% | 4600900% | 4600900% | FALSE | Dec-2025 | 10 | 6 | 5 | -1 | ON TIME | ON TIME | LATE BY ENG |  | C | 9 | IMPACTED |  |  | Closed | LATE | NA | 17 | 4600942% | 100%
PZ4 | 0051615853 | 000100 | 0051615853-000100 | SPACEX CAPE GIGABAY M1/M2 UNIT SUBSTATIO | 4602000% | 4602000% | DEV | KGF | WF1791221 | Mech | MAKE | RAL9003 | 4613900% | 12 | 4600300% | 4601000% | 4601300% | FALSE | Dec-2025 | 10 | 6 | 6 | 0 | ON TIME | ON TIME | ON TIME BY ENG |  | C | -4 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4601307% | 100%
PZ4 | 0051139077 | 000030 | 0051139077-000030 | NORTHROP B307 3000 KVA SUBSTATIONS - PAL | 4600600% |  | AOB | OAL | WF1791235 | Elec | BUY | ANSI 49 | 4606600% | 2 | 4600300% | 4601500% | 4602700% | FALSE | Dec-2025 | 10 | 9 | 13 | 4 | LATE | LATE | LATE BY ENG |  | C | 13 | IMPACTED |  |  | Closed | LATE | NA | 17 | 4601542% | 100%
PZ4 | 0050927776 | 000950 | 0050927776-000950 | REPLACE NETWORK SUBSTATIONS 9A,9B,9C,9D | 4601400% | 4600900% | ASP | CML | WF1791372 | Mech | MAKE | ANSI 49 | 4630800% | 8 | 4600300% | 4601300% | 4602700% | FALSE | Dec-2025 | 10 | 7 | 13 | 6 | LATE | LATE | LATE BY ENG |  | C | 7 | IMPACTED |  |  | Closed | LATE | NA | 18 | 4601607% | 100%
PZ4 | 0050927776 | 000950 | 0050927776-000950 | REPLACE NETWORK SUBSTATIONS 9A,9B,9C,9D | 4601700% | 4600900% | ASP | CML | WF1791343 | Mech | MAKE | ANSI 49 | 4630800% | 11 | 4600300% | 4601300% | 4603100% | FALSE | Dec-2025 | 10 | 7 | 17 | 10 | LATE | LATE | ON TIME BY ENG |  | C | 10 | IMPACTED |  |  | Closed | LATE | NA | 18 | 4601607% | 100%
PZ4 | 0051615853 | 000100 | 0051615853-000100 | SPACEX CAPE GIGABAY M1/M2 UNIT SUBSTATIO | 4602000% | 4602000% | DEV | KGF | WF1791930 | Mech | MAKE | RAL9003 | 4613900% | 11 | 4600600% | 4601300% | 4601300% | FALSE | Dec-2025 | 10 | 6 | 6 | 0 | ON TIME | ON TIME | ON TIME BY ENG |  | C | -4 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4601607% | 100%
PZ4 | 0050927776 | 000950 | 0050927776-000950 | REPLACE NETWORK SUBSTATIONS 9A,9B,9C,9D | 4601400% | 4600900% | ASP | CML | WF1792125 | Mech | MAKE | ANSI 49 | 4630800% | 7 | 4600600% | 4601400% | 4602000% | FALSE | Dec-2025 | 10 | 7 | 9 | 2 | LATE | LATE | LATE BY ENG |  | C | 3 | IMPACTED |  |  | Closed | LATE | NA | 18 | 4601707% | 100%
PZ4 | 0051129914 | 000750&760 | 0051129914-000750&760 | LOUISA COUNTY TECH CAMHUPS | 4602000% | 4600900% | UFA | AL | WF1792197 | Elec | BUY | ANSI 49 | 4609100% | 11 | 4600600% | 4602000% | 4602900% | FALSE | Dec-2025 | 10 | 11 | 15 | 4 | LATE | LATE | ON TIME BY ENG |  | C | 7 | IMPACTED |  |  | Closed | LATE | NA | 17 | 4602042% | 100%
PZ4 | 0050927776 | 000950 | 0050927776-000950 | REPLACE NETWORK SUBSTATIONS 9A,9B,9C,9D | 4601400% | 4600900% | ASP | CML | WF1792636 | Mech | MAKE | ANSI 49 | 4630800% | 6 | 4600700% | 4601400% | 4602700% | FALSE | Dec-2025 | 10 | 6 | 12 | 6 | LATE | LATE | LATE BY ENG |  | C | 7 | IMPACTED |  |  | Closed | LATE | NA | 18 | 4601707% | 100%
PZ4 | 0050927776 | 000950 | 0050927776-000950 | REPLACE NETWORK SUBSTATIONS 9A,9B,9C,9D | 4601700% | 4600900% | ASP | CML | WF1792667 | Mech | MAKE | ANSI 49 | 4630800% | 9 | 4600700% | 4601400% | 4603400% | FALSE | Dec-2025 | 10 | 6 | 17 | 11 | LATE | LATE | LATE BY ENG |  | C | 11 | IMPACTED |  |  | Closed | LATE | NA | 18 | 4601707% | 100%
PZ4 | 0050819993 | 011010 | 0050819993-011010 | RADY CHILDRENS HOSPITAL - ICU AND CONNEC | 4603800% | 4603400% | RAS | OAL | WF1792878 | Elec | MAKE | ANSI 49 | 4619000% | 24 | 4600700% | 4601500% | 4602700% | FALSE | Dec-2025 | 10 | 7 | 12 | 5 | LATE | LATE | ON TIME BY ENG |  | C | -10 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4601807% | 100%
PZ4 | 0050819993 | 011000 | 0050819993-011000 | RADY CHILDRENS HOSPITAL - ICU AND CONNEC | 4605200% | 4604800% | MGL | RCI | WF1793556 | Mech | MAKE | ANSI 49 | 4618400% | 33 | 4600800% | 4601600% | 4602000% | FALSE | Dec-2025 | 10 | 7 | 7 | 0 | ON TIME | ON TIME | ON TIME BY ENG |  | C | -24 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4601907% | 100%
PZ4 | 0051549615 | 000430 | 0051549615-000430 | GENENTECH - APOLLO 11 - EQUIPMENT | 4602800% | 4602800% | KYC | ODE | WF1793610 | Elec | BUY | ANSI 61 | 4607700% | 15 | 4600800% | 4602000% | 4601400% | FALSE | Dec-2025 | 10 | 9 | 5 | -4 | ON TIME | ON TIME | ON TIME BY ENG |  | C | -8 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 17 | 4602042% | 100%
PZ4 | 0051106129 | 000580 | 0051106129-000580 | AT&T SWITCHGEAR UPGRADE | 4602000% | 4602000% | MGL | HUP | WF1793584 | Mech | MAKE | ANSI 49 | 4608000% | 9 | 4600800% | 4601600% | 4601300% | FALSE | Dec-2025 | 10 | 7 | 4 | -3 | ON TIME | ON TIME | LATE BY ENG |  | C | -4 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4601907% | 100%
PZ4 | 0051106129 | 000580 | 0051106129-000580 | AT&T SWITCHGEAR UPGRADE | 4602000% | 4602000% | MGL | HUP | WF1793591 | Mech | MAKE | ANSI 49 | 4608000% | 9 | 4600800% | 4601600% | 4601300% | FALSE | Dec-2025 | 10 | 7 | 4 | -3 | ON TIME | ON TIME | LATE BY ENG |  | C | -4 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4601907% | 100%
PZ4 | 0051620541 | 000010 | 0051620541-000010 | RAYTHEON - MARLBOROUGH - BUILDING 2 - PH | 4600700% | 4600000% |  |  | WF1794049 | Elec | BUY | ANSI 49 |  | -2 | 4600800% | 4602000% |  | TRUE | Dec-2025 | 10 | 9 | 64 | 55 | LATE | SUPER LATE | LATE BY ENG |  | X | 65 | IMPACTED |  |  | Cancelled | LATE | NA | 0 | 4602042% | 0%
PZ4 | 0051611250 | 003280 | 0051611250-003280 | TEMPLE UNIVERSITY LEW KLEIN COLLEGE OF M | 4599600% | 4599300% | ATA | HUP | WF1793411 | Mech | BUY | ANSI 49 | 4607800% | -9 | 4600800% | 4602000% |  | TRUE | Dec-2025 | 10 | 9 | 64 | 55 | LATE | SUPER LATE | LATE BY ENG |  | X | 71 | IMPACTED |  |  | Cancelled | LATE | NA | 0 | 4602042% | 0%
PZ4 | 0051611250 | 003280 | 0051611250-003280 | TEMPLE UNIVERSITY LEW KLEIN COLLEGE OF M | 4599600% | 4599300% | ATA | HUP | WF1793560 | Mech | MAKE | ANSI 49 | 4606600% | -9 | 4600800% | 4601600% | 4601300% | FALSE | Dec-2025 | 10 | 7 | 4 | -3 | ON TIME | ON TIME | LATE BY ENG |  | C | 11 | IMPACTED |  |  | Closed | LATE | NA | 18 | 4601907% | 100%
PZ4 | 0051620541 | 000010 | 0051620541-000010 | RAYTHEON - MARLBOROUGH - BUILDING 2 - PH | 4603800% | 4603100% | JRC | GHT | WF1794223 | Elec | BUY | ANSI 49 | 4613500% | 22 | 4600900% | 4602100% | 4601400% | FALSE | Dec-2025 | 10 | 9 | 4 | -5 | ON TIME | ON TIME | ON TIME BY ENG |  | C | -16 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 17 | 4602142% | 100%
PZ4 | 0051620541 | 000010 | 0051620541-000010 | RAYTHEON - MARLBOROUGH - BUILDING 2 - PH | 4603800% | 4603100% | JRC | GHT | WF1794234 | Elec | BUY | ANSI 49 | 4613500% | 22 | 4600900% | 4602100% | 4601300% | FALSE | Dec-2025 | 10 | 9 | 3 | -6 | ON TIME | ON TIME | ON TIME BY ENG |  | C | -17 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 17 | 4602142% | 100%
PZ4 | 0051659722 | 000090 | 0051659722-000090 | AHO EOB CHILLER NO. 7 | 4599200% | 4598200% | JRC | CML | WF1794198 | Mech | MAKE | ANSI 49 | 4606900% | -14 | 4600900% | 4601600% | 4603000% | FALSE | Dec-2025 | 10 | 6 | 13 | 7 | LATE | LATE | LATE BY ENG |  | C | 25 | IMPACTED |  |  | Closed | LATE | NA | 18 | 4601907% | 100%
PZ4 | 0050927776 | 000950 | 0050927776-000950 | REPLACE NETWORK SUBSTATIONS 9A,9B,9C,9D | 4601400% | 4600900% | ASP | CML | WF1794239 | Mech | BUY | ANSI 49 | 4631900% | 4 | 4600900% | 4602100% | 4602000% | FALSE | Dec-2025 | 10 | 9 | 6 | -3 | ON TIME | ON TIME | LATE BY ENG |  | X | 3 | IMPACTED |  | Cantidades incorrectas | Cancelled | LATE | NA | 12 | 4602142% | 70.59%
PZ4 | 0051656319 | 000010 | 0051656319-000010 | NESTLÉ SILAO | 4605200% | 4604500% | OAC |  | WF1794098 | Elec | BUY | ANSI 49 | 4613500% | 32 | 4600900% | 4602100% | 4602700% | FALSE | Dec-2025 | 10 | 9 | 10 | 1 | LATE | LATE | ON TIME BY ENG |  | C | -20 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 17 | 4602142% | 100%
PZ4 | 0051656319 | 000010 | 0051656319-000010 | NESTLÉ SILAO | 4605200% | 4604500% | OAC |  | WF1794091 | Elec | BUY | ANSI 49 | 4613500% | 32 | 4600900% | 4602100% | 4603600% | FALSE | Dec-2025 | 10 | 9 | 17 | 8 | LATE | LATE | ON TIME BY ENG |  | C | -13 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 17 | 4602142% | 100%
PZ4 | 0051461793 | 000010 | 0051461793-000010 | BURLINGTON NEW DOUBLE-END SUBSTATION | 4603600% | 4603100% | HMA | FRC | WF1794690 | Mech | MAKE | ANSI 49 | 4609800% | 19 | 4601000% | 4601700% | 4602700% | FALSE | Dec-2025 | 10 | 6 | 9 | 3 | LATE | LATE | ON TIME BY ENG |  | C | -8 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4602007% | 100%
PZ4 | 0051732952 | 000010 | 0051732952-000010 | NOVO NORDISK - BLDG QC CHEM-RM LAB - CLA | 4601400% | 1/23/2026 |  | ISQ | WF1796023 | Mech | MAKE | ANSI 49 | 4613400% | 1 | 4601400% | 4602200% | 4603400% | FALSE | Dec-2025 | 10 | 7 | 12 | 5 | LATE | LATE | LATE BY ENG |  | C | 12 | IMPACTED |  |  | Closed | LATE | NA | 18 | 4602507% | 100%
PZ4 | 0051106129 | 000310 | 0051106129-000310 | AT&T SWITCHGEAR UPGRADE | 4602000% | 4602000% | OAC | VHL | WF1795898 | Mech | MAKE | ANSI 49 | 4607100% | 5 | 4601400% | 4602100% | 4602000% | FALSE | Dec-2025 | 10 | 6 | 3 | -3 | ON TIME | ON TIME | LATE BY ENG |  | C | 1 | IMPACTED |  |  | Closed | LATE | NA | 18 | 4602407% | 100%
PZ4 | 0051106129 | 000510 | 0051106129-000510 | AT&T SWITCHGEAR UPGRADE | 4602000% | 4602000% | OAC | AL | WF1795795 | Elec | MAKE | ANSI 49 | 4607100% | 5 | 4601400% | 4602100% | 4603100% | FALSE | Dec-2025 | 10 | 6 | 11 | 5 | LATE | LATE | LATE BY ENG |  | C | 9 | IMPACTED |  |  | Closed | LATE | NA | 18 | 4602407% | 100%
PZ4 | 0051106129 | 000510 | 0051106129-000510 | AT&T SWITCHGEAR UPGRADE | 4602000% | 4602000% | OAC | AL | WF1795911 | Elec | MAKE | ANSI 49 | 4607100% | 5 | 4601400% | 4602100% | 4603100% | FALSE | Dec-2025 | 10 | 6 | 11 | 5 | LATE | LATE | LATE BY ENG |  | C | 9 | IMPACTED |  |  | Closed | LATE | NA | 18 | 4602407% | 100%
PZ4 | 0051106129 | 000510 | 0051106129-000510 | AT&T SWITCHGEAR UPGRADE | 4602000% | 4602000% | OAC | AL | WF1795964 | Mech | MAKE | ANSI 49 | 4607100% | 5 | 4601400% | 4602100% | 4603100% | FALSE | Dec-2025 | 10 | 6 | 11 | 5 | LATE | LATE | LATE BY ENG |  | C | 9 | IMPACTED |  |  | Closed | LATE | NA | 18 | 4602407% | 100%
PZ4 | 0051106129 | 000310 | 0051106129-000310 | AT&T SWITCHGEAR UPGRADE | 4602000% | 4602000% | OAC | VL | WF1795986 | Mech | BUY | ANSI 49 | 4607100% | 5 | 4601400% | 4602400% | 4603500% | FALSE | Dec-2025 | 10 | 9 | 13 | 4 | LATE | LATE | LATE BY ENG |  | C | 11 | IMPACTED |  |  | Closed | LATE | NA | 17 | 4602442% | 100%
PZ4 | 0051218461 | 001970 | 0051218461-001970 | HARD LABOR CREEK WTP - WALTON COUNTY, GA | 4605000% | 4601200% | JRC | OAL | WF1795965 | Elec | MAKE | ANSI 49 | 4614200% | 26 | 4601500% | 4602200% | 4603400% | FALSE | Dec-2025 | 10 | 6 | 11 | 5 | LATE | LATE | ON TIME BY ENG |  | C | -13 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4602507% | 100%
PZ4 | 0050829646 | 001060 | 0050829646-001060 | AT&T : 51 PEACHTREE CENTER AVE SE ATL | 4605200% | 4604400% | DRV | CML | WF1796648 | Mech | MAKE | ANSI 49 | 4613200% | 26 | 4601700% | 4602500% | 4603700% | FALSE | Dec-2025 | 10 | 6 | 14 | 8 | LATE | LATE | ON TIME BY ENG |  | C | -12 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4602807% | 100%
PZ4 | 0050829646 | 001080 | 0050829646-001080 | AT&T : 51 PEACHTREE CENTER AVE SE ATL | 4605200% | 4604400% | DRV | HUP | WF1796616 | Mech | BUY | ANSI 49 | 4613400% | 26 | 4601700% | 4602700% | 4603600% | FALSE | Dec-2025 | 10 | 7 | 13 | 6 | LATE | LATE | ON TIME BY ENG |  | C | -13 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 17 | 4602742% | 100%
PZ4 | 0050829646 | 001080 | 0050829646-001080 | AT&T : 51 PEACHTREE CENTER AVE SE ATL | 4605200% | 4604400% | DRV | HUP | WF1796617 | Mech | MAKE | ANSI 49 | 4613400% | 26 | 4601700% | 4602400% | 4603000% | FALSE | Dec-2025 | 10 | 6 | 9 | 3 | LATE | LATE | ON TIME BY ENG |  | C | -17 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4602707% | 100%
PZ4 | 0050829646 | 001060 | 0050829646-001060 | AT&T : 51 PEACHTREE CENTER AVE SE ATL | 4605200% | 4604400% | DRV | CML | WF1796605 | Mech | MAKE | ANSI 49 | 4613200% | 26 | 4601700% | 4602400% | 4603400% | FALSE | Dec-2025 | 10 | 6 | 11 | 5 | LATE | LATE | ON TIME BY ENG |  | C | -15 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4602707% | 100%
PZ4 | 0050829646 | 001060 | 0050829646-001060 | AT&T : 51 PEACHTREE CENTER AVE SE ATL | 4605200% | 4604400% | DRV | CML | WF1796649 | Mech | BUY | ANSI 49 | 4613200% | 26 | 4601700% | 4602800% | 4603600% | FALSE | Dec-2025 | 10 | 8 | 13 | 5 | LATE | LATE | ON TIME BY ENG |  | C | -13 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 17 | 4602842% | 100%
PZ4 | 0050927776 | 000950 | 0050927776-000950 | REPLACE NETWORK SUBSTATIONS 9A,9B,9C,9D | 4601700% | 4601400% | ASP | CML | WF1797106 | Mech | BUY | ANSI 49 | 4618300% | -2 | 4602000% | 4602800% | 4603000% | FALSE | Dec-2025 | 10 | 7 | 8 | 1 | LATE | LATE | LATE BY ENG |  | C | 9 | IMPACTED |  |  | Closed | LATE | NA | 16 | 4602842% | 94.12%
PZ4 | 0050927776 | 000950 | 0050927776-000950 | REPLACE NETWORK SUBSTATIONS 9A,9B,9C,9D | 4601700% | 4601400% | ASP | CML | WF1797033 | Mech | BUY | ANSI 49 | 4618300% | -2 | 4602000% | 4603200% | 4603400% | FALSE | Dec-2025 | 10 | 10 | 10 | 0 | ON TIME | ON TIME | LATE BY ENG |  | C | 11 | IMPACTED |  |  | Closed | LATE | NA | 11 | 4603242% | 64.71%
PZ4 | 0050829646 | 001080 | 0050829646-001080 | AT&T : 51 PEACHTREE CENTER AVE SE ATL | 4605200% | 4604400% | DRV | HUP | WF1797108 | Mech | MAKE | ANSI 49 | 4613400% | 25 | 4602000% | 4602500% | 4603100% | FALSE | Dec-2025 | 10 | 5 | 9 | 4 | LATE | LATE | ON TIME BY ENG |  | C | -16 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4602807% | 100%
PZ4 | 0050927776 | 000950 | 0050927776-000950 | REPLACE NETWORK SUBSTATIONS 9A,9B,9C,9D | 4601700% | 4601400% | ASP | CML | WF1797190 | Mech | MAKE | ANSI 49 | 4618300% | -2 | 4602000% | 4602700% | 4603500% | FALSE | Dec-2025 | 10 | 6 | 11 | 5 | LATE | LATE | LATE BY ENG |  | C | 12 | IMPACTED |  |  | Closed | LATE | NA | 18 | 4603007% | 100%
PZ4 | 0050753978 | 003800 | 0050753978-003800 | KAISER SAN JOSE MEDICAL CENTER HOSPITAL | 4589800% |  | ALT | HUP | WF1798395 | Elec | BUY | ANSI 49 | 4608000% | -92 | 4602700% | 4602900% | 4604400% | FALSE | Jan-2026 | 10 | 3 | 14 | 11 | LATE | LATE | LATE BY ENG |  | X | 96 | IMPACTED |  |  | Cancelled | LATE | NA | 2 | 4602942% | 11.76%
PZ4 | 0051354978 | 000080 | 0051354978-000080 | ADVENT HEALTH CARROLLWOOD GARDEN TOWER E | 4598100% | 4604400% | RAS | HUP | WF1799079 | Mech | CNG-BOM | ANSI 49 | 4604200% | -34 | 4602800% | 4603100% | 4603000% | FALSE | Jan-2026 | 10 | 4 | 3 | -1 | ON TIME | ON TIME | LATE BY ENG |  | C | 31 | IMPACTED |  |  | Closed | LATE | NA | 8 | 4603142% | 72.73%
PZ4 | 0051354978 | 000080 | 0051354978-000080 | ADVENT HEALTH CARROLLWOOD GARDEN TOWER E | 4598100% | 4604400% | RAS | RCI | WF1799173 | Mech | CNG-BOM | ANSI 49 | 4604200% | -34 | 4602800% | 4603100% | 4603000% | FALSE | Jan-2026 | 10 | 4 | 3 | -1 | ON TIME | ON TIME | LATE BY ENG |  | C | 31 | IMPACTED |  |  | Closed | LATE | NA | 8 | 4603142% | 72.73%
PZ4 | 0051354978 | 000080 | 0051354978-000080 | ADVENT HEALTH CARROLLWOOD GARDEN TOWER E | 4598100% | 4604400% | RAS | RCI | WF1799067 | Mech | MAKE | ANSI 49 | 4604200% | -34 | 4602800% | 4603300% | 4603100% | FALSE | Jan-2026 | 10 | 4 | 4 | 0 | ON TIME | ON TIME | LATE BY ENG |  | C | 32 | IMPACTED |  |  | Closed | LATE | NA | 18 | 4603607% | 100%
PZ4 | 0051656319 | 000010 | 0051656319-000010 | NESTLÉ SILAO | 4605200% | 4604500% | OAC | AL | WF1799011 | Elec | BUY | ANSI 49 | 4612800% | 19 | 4602800% | 4603600% | 4603600% | FALSE | Jan-2026 | 10 | 7 | 7 | 0 | ON TIME | ON TIME | ON TIME BY ENG |  | C | -13 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 17 | 4603642% | 100%
PZ4 | 0051732952 | 000010 | 0051732952-000010 | NOVO NORDISK - BLDG QC CHEM-RM LAB - CLA | 4604500% | 4603800% |  | ISQ | WF1799816 | Mech | MAKE | ANSI 49 | 4613900% | 13 | 4602900% | 4603500% | 4603700% | FALSE | Jan-2026 | 10 | 5 | 7 | 2 | LATE | LATE | ON TIME BY ENG |  | C | -7 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4603807% | 100%
PZ4 | 0051674363 | 000010 | 0051674363-000010 | W912EF25QA023-ARMY US | 4610100% | 4609400% | HMA |  | WF1801057 | Elec | MAKE | ANSI 49 | 4620500% | 51 | 4603100% | 4603700% | 4604200% | FALSE | Jan-2026 | 10 | 5 | 8 | 3 | LATE | LATE | ON TIME BY ENG |  | C | -44 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4604007% | 100%
PZ4 | 0051674363 | 000010 | 0051674363-000010 | W912EF25QA023-ARMY US | 4610100% | 4609400% | HMA |  | WF1801061 | Elec | MAKE | ANSI 49 | 4620500% | 51 | 4603100% | 4603700% | 4604300% | FALSE | Jan-2026 | 10 | 5 | 9 | 4 | LATE | LATE | ON TIME BY ENG |  | C | -43 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4604007% | 100%
PZ4 | 0051272041 | 002870 | 0051272041-002870 | UC BERKELEY HEATHCOCK HALL | 4608000% | 4607300% | UFA |  | WF1800943 | Elec | BUY | ANSI 49 | 4621000% | 36 | 4603100% | 4603900% | 4603700% | FALSE | Jan-2026 | 10 | 6 | 5 | -1 | ON TIME | ON TIME | ON TIME BY ENG |  | C | -32 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 17 | 4603942% | 100%
PZ4 | 0051272041 | 002870 | 0051272041-002870 | UC BERKELEY HEATHCOCK HALL | 4608000% | 4607300% | UFA |  | WF1800951 | Elec | MAKE | ANSI 49 | 4619100% | 36 | 4603100% | 4603600% | 4604100% | FALSE | Jan-2026 | 10 | 4 | 7 | 3 | LATE | LATE | ON TIME BY ENG |  | C | -30 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4603907% | 100%
PZ4 | 0051674363 | 000010 | 0051674363-000010 | W912EF25QA023-ARMY US | 4610100% | 4609400% | HMA |  | WF1801632 | Elec | BUY | ANSI 49 | 4620500% | 50 | 4603400% | 4604400% | 4604900% | FALSE | Jan-2026 | 10 | 9 | 12 | 3 | LATE | LATE | ON TIME BY ENG |  | C | -39 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 17 | 4604442% | 100%
PZ4 | 0051442285 | 000080 | 0051442285-000080 | GIGABAY 15KV SUBSTATIONS REV3 STARBASE T | 4594500% | 4593200% | DEV | LDT | WF1802028 | Mech | CNG-BOM | ANSI 49 | 4604400% | -64 | 4603400% | 4604100% | 4603600% | FALSE | Jan-2026 | 10 | 6 | 3 | -3 | ON TIME | ON TIME | LATE BY ENG |  | C | 58 | IMPACTED |  |  | Closed | LATE | NA | 11 | 4604142% | 100%
PZ4 | 0051523070 | 000010 | 0051523070-000010 | NSWC RAM LAB | 4592400% | 4592400% | JAV |  | WF1801750 | Elec | BUY | ANSI 49 | 4624700% | -79 | 4603400% | 4604400% | 4603500% | FALSE | Jan-2026 | 10 | 9 | 2 | -7 | ON TIME | ON TIME | LATE BY ENG |  | X | 72 | IMPACTED |  | WITHIN OTHER WF | Cancelled | LATE | NA | 0 | 4604442% | 0%
PZ4 | 0051674363 | 000010 | 0051674363-000010 | W912EF25QA023-ARMY US | 4610100% | 4609400% | HMA |  | WF1801636 | Elec | MAKE | ANSI 49 | 4620500% | 50 | 4603400% | 4604100% | 4605000% | FALSE | Jan-2026 | 10 | 6 | 13 | 7 | LATE | LATE | ON TIME BY ENG |  | C | -38 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4604407% | 100%
PZ4 | 0051737181 | 000080 | 0051737181-000080 | BOSCH - ELECTROLYZER INFRASTRUCTURE | 4604300% | 1/14/202 | ATA |  | WF1802767 | Elec | MAKE | ANSI 49 | 4629900% | 7 | 4603500% | 4604400% | 4604100% | FALSE | Jan-2026 | 10 | 8 | 5 | -3 | ON TIME | ON TIME | LATE BY ENG |  | C | -3 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4604707% | 100%
PZ4 | 0051193435 | 000290 | 0051193435-000290 | NORTHROP B410 CHILLER UPGRADE | 4605200% | 4604500% | ASP | HUP | WF1802512 | Mech | BUY | ANSI 49 | 4617800% | 14 | 4603500% | 4604500% | 4604900% | FALSE | Jan-2026 | 10 | 9 | 11 | 2 | LATE | LATE | ON TIME BY ENG |  | C | -4 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 17 | 4604542% | 100%
PZ4 | 0051732952 | 000010 | 0051732952-000010 | NOVO NORDISK - BLDG QC CHEM-RM LAB - CLA | 4604500% | 4603800% |  | ISQ | WF1802529 | Elec | BUY | ANSI 49 | 4613300% | 9 | 4603500% | 4604500% | 4604800% | FALSE | Jan-2026 | 10 | 9 | 10 | 1 | LATE | LATE | LATE BY ENG |  | C | 2 | IMPACTED |  |  | Closed | LATE | NA | 17 | 4604542% | 100%
PZ4 | 0051218461 | 001980 | 0051218461-001980 | HARD LABOR CREEK WTP - WALTON COUNTY, GA | 4605000% | 4604300% | JRC | OAL | WF1802550 | Mech | BUY | ANSI 49 | 4613600% | 12 | 4603500% | 4604500% | 4604900% | FALSE | Jan-2026 | 10 | 9 | 11 | 2 | LATE | LATE | ON TIME BY ENG |  | C | -2 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 17 | 4604542% | 100%
PZ4 | 0051218461 | 001980 | 0051218461-001980 | HARD LABOR CREEK WTP - WALTON COUNTY, GA | 4605000% | 4604300% | JRC | OAL | WF1802551 | Mech | MAKE | ANSI 49 | 4613600% | 12 | 4603500% | 4604200% | 4605100% | FALSE | Jan-2026 | 10 | 6 | 13 | 7 | LATE | LATE | ON TIME BY ENG |  | C | 2 | IMPACTED |  |  | Closed | LATE | NA | 18 | 4604507% | 100%
PZ4 | 0051193435 | 000290 | 0051193435-000290 | NORTHROP B410 CHILLER UPGRADE | 4605200% | 4604500% | ASP | HUP | WF1802521 | Mech | MAKE | ANSI 49 | 4617800% | 14 | 4603500% | 4604200% | 4605100% | FALSE | Jan-2026 | 10 | 6 | 13 | 7 | LATE | LATE | ON TIME BY ENG |  | C | -2 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4604507% | 100%
PZ4 | SPECIAL | SPECIAL | SPECIAL-SPECIAL | MICROLOGIC 6.0 X MTZ FIJO | 4604800% | 4604800% | UFA |  | WF1803218 | Elec | BUY | ANSI 49 | NA | 9 | 4603600% | 4604800% | 4604300% | FALSE | Jan-2026 | 10 | 9 | 6 | -3 | ON TIME | ON TIME | LATE BY ENG |  | C | -4 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 17 | 4604842% | 100%
PZ4 | 0051656319 | 000010 | 0051656319-000010 | NESTLÉ SILAO | 4605200% | 4604500% | OAC | AL | WF1803392 | Mech | MAKE | ANSI 49 | 4613200% | 13 | 4603600% | 4604400% | 4605200% | FALSE | Jan-2026 | 10 | 7 | 13 | 6 | LATE | LATE | ON TIME BY ENG |  | C | 1 | IMPACTED |  |  | Closed | LATE | NA | 18 | 4604707% | 100%
PZ4 | 0051656319 | 000010 | 0051656319-000010 | NESTLÉ SILAO | 4605200% | 4604500% | OAC | AL | WF1803393 | Mech | MAKE | ANSI 49 | 4613200% | 13 | 4603600% | 4604400% | 4605200% | FALSE | Jan-2026 | 10 | 7 | 13 | 6 | LATE | LATE | ON TIME BY ENG |  | C | 1 | IMPACTED |  |  | Closed | LATE | NA | 18 | 4604707% | 100%
PZ4 | 0051656319 | 000010 | 0051656319-000010 | NESTLÉ SILAO | 4605200% | 4604500% | OAC | AL | WF1803394 | Mech | BUY | ANSI 49 | 4613200% | 13 | 4603600% | 4604900% | 4605200% | FALSE | Jan-2026 | 10 | 10 | 13 | 3 | LATE | LATE | ON TIME BY ENG |  | C | 1 | IMPACTED |  |  | Closed | LATE | NA | 14 | 4604942% | 82.35%
PZ4 | 0051656319 | 000010 | 0051656319-000010 | NESTLÉ SILAO | 4605200% | 4604500% | OAC | AL | WF1803400 | Mech | BUY | ANSI 49 | 4613200% | 13 | 4603600% | 4605000% | 4605200% | FALSE | Jan-2026 | 10 | 11 | 13 | 2 | LATE | LATE | ON TIME BY ENG |  | C | 1 | IMPACTED |  |  | Closed | LATE | NA | 14 | 4605042% | 82.35%
PZ4 | 0051656319 | 000010 | 0051656319-000010 | NESTLÉ SILAO | 4605200% | 4604500% | OAC | AL | WF1803401 | Mech | MAKE | ANSI 49 | 4613200% | 13 | 4603600% | 4604500% | 4604500% | FALSE | Jan-2026 | 10 | 8 | 8 | 0 | ON TIME | ON TIME | ON TIME BY ENG |  | C | -6 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4604807% | 100%
PZ4 | 0050829646 | 001060 | 0050829646-001060 | AT&T : 51 PEACHTREE CENTER AVE SE ATL | 4605200% | 4604400% | DRV | CML | WF1803903 | Mech | MAKE | ANSI 49 | 4613900% | 12 | 4603700% | 4604500% | 4604300% | FALSE | Jan-2026 | 10 | 7 | 5 | -2 | ON TIME | ON TIME | ON TIME BY ENG |  | C | -8 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4604807% | 100%
PZ4 | 0050829646 | 001060 | 0050829646-001060 | AT&T : 51 PEACHTREE CENTER AVE SE ATL | 4605200% | 4604400% | DRV | CML | WF1803920 | Mech | MAKE | ANSI 49 | 4613900% | 12 | 4603700% | 4604500% | 4604400% | FALSE | Jan-2026 | 10 | 7 | 6 | -1 | ON TIME | ON TIME | ON TIME BY ENG |  | C | -7 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4604807% | 100%
PZ4 | SPECIAL | SPECIAL | SPECIAL-SPECIAL | BUNDLE FOR KOMAX | 4604500% | 4604500% | UFA |  | WF1803907 | Elec | MAKE | ANSI 49 | NA | 7 | 4603700% | 4604500% | 4608400% | FALSE | Jan-2026 | 10 | 7 | 34 | 27 | LATE | SUPER LATE | LATE BY ENG |  | C | 28 | IMPACTED |  |  | Closed | LATE | NA | 18 | 4604807% | 100%
PZ4 | 0051620541 | 000010 | 0051620541-000010 | RAYTHEON - MARLBOROUGH - BUILDING 2 - PH | 4603100% | 4603800% | JRC | GHT | WF1792804 | Mech | BUY | ANSI 49 | 4612500% | -6 | 4603800% | 4604800% | 4603500% | FALSE | Jan-2026 | 10 | 7 | -4 | -11 | ON TIME | ON TIME | LATE BY ENG |  | C | 3 | IMPACTED |  |  | Closed | LATE | NA | 17 | 4604842% | 100%
PZ4 | 0051618201 | 000040 | 0051618201-000040 | EOEM - REHLKO - PANAMA CITY - MILLVILLE | 4605700% | 4605200% | DMA | KGF | WF1804277 | Mech | MAKE | ANSI 49 | 4614100% | 14 | 4603800% | 4604500% | 4604800% | FALSE | Jan-2026 | 10 | 6 | 7 | 1 | LATE | LATE | ON TIME BY ENG |  | C | -8 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4604807% | 100%
PZ4 | 0051674363 | 000010 | 0051674363-000010 | W912EF25QA023-ARMY US | 4610100% | 4609400% | HMA |  | WF1804422 | Elec | MAKE | ANSI 49 | 4606000% | 46 | 4603800% | 4604800% | 4604800% | FALSE | Jan-2026 | 10 | 7 | 7 | 0 | ON TIME | ON TIME | ON TIME BY ENG |  | C | -40 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4605107% | 100%
PZ4 | 0051618201 | 000040 | 0051618201-000040 | EOEM - REHLKO - PANAMA CITY - MILLVILLE | 4605700% | 4605200% | DMA | KGF | WF1804434 | Mech | MAKE | ANSI 49 | 4614100% | 14 | 4603800% | 4604800% | 4605000% | FALSE | Jan-2026 | 10 | 7 | 9 | 2 | LATE | LATE | ON TIME BY ENG |  | C | -6 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4605107% | 100%
PZ4 | 0051193435 | 000290 | 0051193435-000290 | NORTHROP B410 CHILLER UPGRADE | 4605200% | 4604500% | ASP | HUP | WF1805051 | Elec | MAKE | ANSI 49 | 4617800% | 10 | 4604100% | 4604800% | 4605000% | FALSE | Jan-2026 | 10 | 6 | 8 | 2 | LATE | LATE | ON TIME BY ENG |  | C | -3 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4605107% | 100%
PZ4 | 0051193435 | 000290 | 0051193435-000290 | NORTHROP B410 CHILLER UPGRADE | 4605200% | 4604500% | ASP | HUP | WF1805069 | Elec | MAKE | ANSI 49 | 4617800% | 10 | 4604100% | 4604800% | 4605100% | FALSE | Jan-2026 | 10 | 6 | 9 | 3 | LATE | LATE | ON TIME BY ENG |  | C | -2 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4605107% | 100%
PZ4 | 0051193435 | 000290 | 0051193435-000290 | NORTHROP B410 CHILLER UPGRADE | 4605200% | 4604500% | ASP | HUP | WF1805075 | Elec | MAKE | ANSI 49 | 4617800% | 10 | 4604100% | 4604800% | 4605200% | FALSE | Jan-2026 | 10 | 6 | 10 | 4 | LATE | LATE | ON TIME BY ENG |  | C | 1 | IMPACTED |  |  | Closed | LATE | NA | 18 | 4605107% | 100%
PZ4 | 0051008484 | 000500 | 0051008484-000500 | NORTH FORK PEACHTREE CREEK STORAGE TANK | 4606600% | 4605900% | DMA | RCI | WF1805186 | Mech | MAKE | ANSI 49 | 4614200% | 20 | 4604100% | 4605200% | 4606200% | FALSE | Jan-2026 | 10 | 10 | 16 | 6 | LATE | LATE | ON TIME BY ENG |  | C | -5 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4605507% | 100%
PZ4 | 0051008484 | 000500 | 0051008484-000500 | NORTH FORK PEACHTREE CREEK STORAGE TANK | 4606600% | 4605900% | DMA | RCI | WF1805305 | Mech | MAKE | ANSI 49 | 4614200% | 20 | 4604100% | 4605600% | 4605800% | FALSE | Jan-2026 | 10 | 12 | 14 | 2 | LATE | LATE | ON TIME BY ENG |  | C | -7 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4605907% | 100%
PZ4 | 0051674363 | 000010 | 0051674363-000010 | W912EF25QA023-ARMY US | 4610100% | 4603500% | HMA |  | WF1805115 | Elec | BUY | ANSI 49 | 4622300% | 45 | 4604100% | 4605100% | 4605600% | FALSE | Jan-2026 | 10 | 9 | 12 | 3 | LATE | LATE | ON TIME BY ENG |  | C | -34 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 17 | 4605142% | 100%
PZ4 | 0050927776 | 000980 | 0050927776-000980 | REPLACE NETWORK SUBSTATIONS 9A,9B,9C,9D | 4605500% | 4604800% | ASP | ODE | WF1805700 | Mech | MAKE | ANSI 49 | 4624600% | 10 | 4604200% | 4604900% | 4605000% | FALSE | Jan-2026 | 10 | 6 | 7 | 1 | LATE | LATE | ON TIME BY ENG |  | C | -4 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4605207% | 100%
PZ4 | 0051008484 | 000500 | 0051008484-000500 | NORTH FORK PEACHTREE CREEK STORAGE TANK | 4603500% | 4602800% | DMA | RCI | WF1805991 | Mech | MAKE | ANSI 49 | 4614900% | -6 | 4604200% | 4605000% | 4604800% | FALSE | Jan-2026 | 10 | 7 | 5 | -2 | ON TIME | ON TIME | LATE BY ENG |  | C | 10 | IMPACTED |  |  | Closed | LATE | NA | 18 | 4605307% | 100%
PZ4 | 051008484 | 000500 | 051008484-000500 | NORTH FORK PEACHTREE CREEK STORAGE TANK | 4603500% | 4602800% | DMA | RCI | WF1806568 | Elec | BUY | ANSI 49 | 4614900% | -7 | 4604300% | 4605000% | 4606200% | FALSE | Jan-2026 | 10 | 6 | 14 | 8 | LATE | LATE | LATE BY ENG |  | C | 20 | IMPACTED |  |  | Closed | LATE | NA | 17 | 4605042% | 100%
PZ4 | 0051343281 | 000010 | 0051343281-000010 | EAST BANK REGIONAL PUMP STATION - NASHVI | 4606600% | 4605900% | DRV | GHT | WF1806642 | Mech | MAKE | ANSI 49 | 4616900% | 18 | 4604300% | 4605100% | 4605100% | FALSE | Jan-2026 | 10 | 7 | 7 | 0 | ON TIME | ON TIME | ON TIME BY ENG |  | C | -12 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4605407% | 100%
PZ4 | 0051713006 | 000010 | 0051713006-000010 | PROJECT OPAL LLE2-MICRON TECHNOLOGY INC. | 4605200% |  | MGL |  | WF1806459 | Elec | BUY | ANSI 49 | 4612600% | 8 | 4604300% | 4605600% | 4604900% | FALSE | Jan-2026 | 10 | 10 | 5 | -5 | ON TIME | ON TIME | LATE BY ENG |  | C | -4 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 17 | 4605642% | 100%
PZ4 | SPECIAL | SPECIAL | SPECIAL-SPECIAL | ABB BLACKLIST | 4605000% | 4605000% | UFA |  | WF1806481 | Elec | OBS | ANSI 49 | 4605000% | 6 | 4604300% | 4605000% | 4604500% | FALSE | Jan-2026 | 10 | 6 | 3 | -3 | ON TIME | ON TIME | LATE BY ENG |  | X | -4 | NOT IMPACTED |  |  | Cancelled | ON TIME | NA | 2 | 4605042% | #N/A
PZ4 | 0051618201 | 000040 | 0051618201-000040 | EOEM - REHLKO - PANAMA CITY - MILLVILLE | 4605700% | 4605200% | DMA | KGF | WF1807077 | Mech | MAKE | ANSI 49 | 4614900% | 10 | 4604400% | 4605100% | 4605000% | FALSE | Jan-2026 | 10 | 6 | 5 | -1 | ON TIME | ON TIME | ON TIME BY ENG |  | C | -6 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4605407% | 100%
PZ4 | 0050544685 | 001240 | 0050544685-001240 | BJC HEALTHCARE WEST PAV EM POWER DIST | 4608700% | 4608000% |  |  | WF1807192 | Elec | MAKE | ANSI 49 | 4618800% | 32 | 4604400% | 4605100% | 4605000% | FALSE | Jan-2026 | 10 | 6 | 5 | -1 | ON TIME | ON TIME | ON TIME BY ENG |  | C | -28 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4605407% | 100%
PZ4 | 0051787649 | 000050 | 0051787649-000050 | MICRON ID1 PHASE 2 - F12A UNIT SUBSTATIO | 4606200% |  | SMA | VL | WF1807719 | Mech | CNG-BOM | ANSI 49 | 4616900% | 12 | 4604500% | 4605000% | 4605000% | FALSE | Jan-2026 | 10 | 4 | 4 | 0 | ON TIME | ON TIME | ON TIME BY ENG |  | C | -9 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 11 | 4605042% | 100%
PZ4 | 0050384250 | 001240&001250&001270 | 0050384250-001240&001250&001270 | NEW PARNASSUS HEIGHTS HOSPITAL - UCSF - | 4608000% | 4607300% | ASP |  | WF1808503 | Elec | MAKE | ANSI 49 | 4623700% | 25 | 4604800% | 4605600% | 4605800% | FALSE | Jan-2026 | 10 | 7 | 9 | 2 | LATE | LATE | ON TIME BY ENG |  | C | -17 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4605907% | 100%
PZ4 | 0051024393 | 000310 | 0051024393-000310 | HF CURREN AWTP MASTER PLAN IMPROVEMENTS | 4606600% | 4600600% | HMA | ISQ | WF1809205 | Mech | MAKE | ANSI 61 | 4609000% | 14 | 4604900% | 4605700% | 4605800% | FALSE | Jan-2026 | 10 | 7 | 8 | 1 | LATE | LATE | ON TIME BY ENG |  | C | -7 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4606007% | 100%
PZ4 | 0051129914 | 000750&760 | 0051129914-000750&760 | LOUISA COUNTY TECH CAMPUS | 4606300% | 4605600% | UFA | AL | WF1809914 | Elec | MAKE | ANSI 49 | 4617500% | 10 | 4605000% | 4605800% | 4605800% | FALSE | Jan-2026 | 10 | 7 | 7 | 0 | ON TIME | ON TIME | ON TIME BY ENG |  | C | -4 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4606107% | 100%
PZ4 | 0051129914 | 000760 | 0051129914-000760 | LOUISA COUNTY TECH CAMPUS | 4606300% | 4605600% | UFA | AL | WF1810047 | Mech | MAKE | ANSI 49 | 4617500% | 10 | 4605000% | 4606300% | 4605800% | FALSE | Jan-2026 | 10 | 10 | 7 | -3 | ON TIME | ON TIME | ON TIME BY ENG |  | C | -4 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4606607% | 100%
PZ4 | 0051129914 | 000760 | 0051129914-000760 | LOUISA COUNTY TECH CAMPUS | 4606300% | 4605600% | UFA | AL | WF1810046 | Mech | BUY | ANSI 49 | 4617500% | 10 | 4605000% | 4606300% | 4606300% | FALSE | Jan-2026 | 10 | 10 | 10 | 0 | ON TIME | ON TIME | ON TIME BY ENG |  | C | 1 | IMPACTED |  |  | Closed | LATE | NA | 17 | 4606342% | 100%
PZ4 | 0051523070 | 000010 | 0051523070-000010 | NSWC RAM LAB | 4613600% | 4612500% | JAV | RCI | WF1810695 | Mech | MAKE | ANSI 49 | 4625400% | 62 | 4605100% | 4602800% | 4606200% | FALSE | Jan-2026 | 10 | -18 | 8 | 26 | LATE | SUPER LATE | ON TIME BY ENG |  | C | -55 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4603107% | 100%
PZ4 | 0051139077 | 000030&000110&000290 | 0051139077-000030&000110&000290 | NORTHROP B307 3000 KVA SUBSTATIONS - PAL | 4589800% | NA | AOB | OAL | WF1812135 | Mech | MAKE | ANSI 49 | 4566200% | -112 | 4605500% | 4606300% | 4606300% | FALSE | Feb-2026 | 10 | 7 | 7 | 0 | ON TIME | ON TIME | LATE BY ENG |  | C | 109 | IMPACTED |  |  | Closed | LATE | NA | 18 | 4606607% | 100%
PZ4 | 0050941348 | 000150 | 0050941348-000150 | FC23-011 3000 KVA SUBSTATION U | 4605200% |  | JAM | OAL | WF1812731 | Mech | MAKE | ANSI 49 | 4617400% | -3 | 4605600% | 4606300% | 4606600% | FALSE | Feb-2026 | 10 | 6 | 9 | 3 | LATE | LATE | LATE BY ENG |  | C | 11 | IMPACTED |  |  | Closed | LATE | NA | 18 | 4606607% | 100%
PZ4 | 0050941348 | 000150 | 0050941348-000150 | FC23-011 3000 KVA SUBSTATION U | 4605200% |  | JAM | OAL | WF1812732 | Mech | MAKE | ANSI 49 | 4617400% | -3 | 4605600% | 4606300% | 4606600% | FALSE | Feb-2026 | 10 | 6 | 9 | 3 | LATE | LATE | LATE BY ENG |  | C | 11 | IMPACTED |  |  | Closed | LATE | NA | 18 | 4606607% | 100%
PZ4 | 0051024393 | 000310 | 0051024393-000310 | HF CURREN AWTP MASTER PLAN IMPROVEMENTS | 4600600% | 4601300% | HMA | ISQ | WF1813531 | Elec | BUY | ANSI 61 | 4608600% | -38 | 4605700% | 4606900% | 4606600% | FALSE | Feb-2026 | 10 | 9 | 8 | -1 | ON TIME | ON TIME | LATE BY ENG |  | C | 42 | IMPACTED |  |  | Closed | LATE | NA | 17 | 4606942% | 100%
PZ4 | SPECIAL | SPECIAL | SPECIAL-SPECIAL | CRIMP LUG LONG BARREL 2 AWG | 4607000% |  | UFA |  | WF1814100 | Elec | BUY | ANSI 49 | 4607000% | 9 | 4605800% | 4607000% | 4607000% | FALSE | Feb-2026 | 10 | 9 | 9 | 0 | ON TIME | ON TIME | LATE BY ENG |  | C | 1 | IMPACTED |  |  | Closed | LATE | NA | 17 | 4607042% | 100%
PZ4 | 0051818022 | 000010 | 0051818022-000010 | GUNDERSEN HEALTH SYSTEM HERITAGE EMERGEN | 4608000% | 4607300% | ANV | RCI | WF1814234 | Elec | MAKE | ANSI 49 | 4619500% | 17 | 4605800% | 4606500% | 4607300% | FALSE | Feb-2026 | 10 | 6 | 12 | 6 | LATE | LATE | ON TIME BY ENG |  | C | -6 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4606807% | 100%
PZ4 | 0051827227 | 000010 | 0051827227-000010 | NEW CASTLE COUNTY COURTHOUSE - CUSTOM HO | 4608700% | 4608000% | JAV | ODE | WF1814058 | Mech | MAKE | ANSI 49 | 4619800% | 22 | 4605800% | 4606500% | 4606500% | FALSE | Feb-2026 | 10 | 6 | 6 | 0 | ON TIME | ON TIME | ON TIME BY ENG |  | C | -17 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4606807% | 100%
PZ4 | 0051827227 | 000010 | 0051827227-000010 | NEW CASTLE COUNTY COURTHOUSE - CUSTOM HO | 4608700% | 4608000% | JAV | ODE | WF1814064 | Mech | MAKE | ANSI 49 | 4619800% | 22 | 4605800% | 4606500% | 4606500% | FALSE | Feb-2026 | 10 | 6 | 6 | 0 | ON TIME | ON TIME | ON TIME BY ENG |  | C | -17 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4606807% | 100%
PZ4 | 0050384250 | 001260 | 0050384250-001260 | NEW PARNASSUS HEIGHTS HOSPITAL - UCSF - | 4608700% | 4608000% | HMA | CML | WF1814275 | Mech | MAKE | ANSI 49 | 4620900% | 22 | 4605800% | 4606600% | 4607100% | FALSE | Feb-2026 | 10 | 7 | 10 | 3 | LATE | LATE | ON TIME BY ENG |  | C | -13 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4606907% | 100%
PZ4 | 0051735870 | 000010 | 0051735870-000010 | PROJECT OPAL LLE3 | 4611100% | 4609800% | JAM | RCI | WF1824746 | Mech | MAKE | ANSI 49 | 4624100% | 38 | 4605800% | 4607900% | 4609200% | FALSE | Feb-2026 | 10 | 16 | 25 | 9 | LATE | LATE | ON TIME BY ENG |  | C | -14 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4608207% | 100%
PZ4 | 0051647770 | 000010 | 0051647770-000010 | SCHNEIDER ELECTRIC USA INC | 4600000% | 4599300% | DEV | VL | WF1814660 | Mech | MAKE | ANSI 49 | 4606200% | -44 | 4605900% | 4606600% | 4607100% | FALSE | Feb-2026 | 10 | 6 | 9 | 3 | LATE | LATE | LATE BY ENG |  | C | 48 | IMPACTED |  |  | Closed | LATE | NA | 18 | 4606907% | 100%
PZ4 | 0051791572 | 000010 | 0051791572-000010 | ADVENT HEALTH CELEBRATION PATIENT TOWER | 4607800% | 4607100% | ATA | ISQ | WF1815036 | Mech | MAKE | ANSI 49 | 4619500% | 13 | 4606000% | 4606900% | 4607200% | FALSE | Feb-2026 | 10 | 6 | 9 | 3 | LATE | LATE | ON TIME BY ENG |  | C | -5 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4607207% | 100%
PZ4 | 0050384250 | 001260 | 0050384250-001260 | NEW PARNASSUS HEIGHTS HOSPITAL - UCSF - | 4608700% | 4608000% | HMA | CML | WF1815037 | Mech | BUY | ANSI 49 | 4620900% | 20 | 4606000% | 4607200% | 4607000% | FALSE | Feb-2026 | 10 | 9 | 7 | -2 | ON TIME | ON TIME | ON TIME BY ENG |  | C | -14 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 17 | 4607242% | 100%
PZ4 | 0050384250 | 001260 | 0050384250-001260 | NEW PARNASSUS HEIGHTS HOSPITAL - UCSF - | 4608700% | 4608000% | HMA | CML | WF1815038 | Mech | MAKE | ANSI 49 | 4620900% | 20 | 4606000% | 4606900% | 4607200% | FALSE | Feb-2026 | 10 | 6 | 9 | 3 | LATE | LATE | ON TIME BY ENG |  | C | -12 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4607207% | 100%
PZ4 | 0051212323 | 010200 | 0051212323-010200 | GEISINGER MEDICAL CENTER SOUTH TOWER | 4608300% | 4607600% | OHO | OAL | WF1815539 | Mech | MAKE | ANSI 49 | 4623000% | 16 | 4606200% | 4606900% | 4606700% | FALSE | Feb-2026 | 10 | 6 | 5 | -1 | ON TIME | ON TIME | ON TIME BY ENG |  | C | -11 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4607207% | 100%
PZ4 | 0050384250 | 001240 | 0050384250-001240 | NEW PARNASSUS HEIGHTS HOSPITAL - UCSF - | 4608700% | 4608000% | ASP | KGF | WF1815649 | Mech | MAKE | ANSI 49 | 4621800% | 20 | 4606200% | 4606900% | 4606700% | FALSE | Feb-2026 | 10 | 6 | 5 | -1 | ON TIME | ON TIME | ON TIME BY ENG |  | C | -15 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4607207% | 100%
PZ4 | 0051842216 | 000030 | 0051842216-000030 | FREIGHTLINER - CLEVELAND, NC. | 4608700% | 4608000% | JRC | ISQ | WF1815705 | Elec | MAKE | ANSI 49 | 4619800% | 20 | 4606200% | 4606900% | 4607200% | FALSE | Feb-2026 | 10 | 6 | 9 | 3 | LATE | LATE | ON TIME BY ENG |  | C | -12 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4607207% | 100%
PZ4 | 0051212323 | 010170 | 0051212323-010170 | GEISINGER MEDICAL CENTER SOUTH TOWER | 4608300% | 4607600% | OHO | CML | WF1815776 | Mech | MAKE | ANSI 49 | 4623100% | 16 | 4606200% | 4607000% | 4607000% | FALSE | Feb-2026 | 10 | 7 | 7 | 0 | ON TIME | ON TIME | ON TIME BY ENG |  | C | -10 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4607307% | 100%
PZ4 | 0051008484 | 000500 | 0051008484-000500 | NORTH FORK PEACHTREE CREEK STORAGE TANK | 4606600% | 4605900% | DMA | RCI | WF1815825 | Mech | MAKE | ANSI 49 | 4614900% | 5 | 4606200% | 4607100% | 4606700% | FALSE | Feb-2026 | 10 | 8 | 5 | -3 | ON TIME | ON TIME | LATE BY ENG |  | C | 1 | IMPACTED |  |  | Closed | LATE | NA | 18 | 4607407% | 100%
PZ4 | 0051129914 | 000750&760 | 0051129914-000750&760 | LOUISA COUNTY TECH CAMPUS | 4606300% | 4605600% | UFA | AL | WF1815896 | Elec | MAKE | ANSI 49 | 4617500% | 2 | 4606200% | 4607100% | 4607300% | FALSE | Feb-2026 | 10 | 8 | 10 | 2 | LATE | LATE | LATE BY ENG |  | C | 9 | IMPACTED |  |  | Closed | LATE | NA | 18 | 4607407% | 100%
PZ4 | 0051251730 | 001110 | 0051251730-001110 | AMEREN CASTLE BLUFF ENERGY CENTER | 4606600% |  | DVR |  | WF1815786 | Elec | BUY | ANSI 49 | 4626500% | 5 | 4606200% | 4607200% | 4608300% | FALSE | Feb-2026 | 10 | 9 | 16 | 7 | LATE | LATE | LATE BY ENG |  | C | 12 | IMPACTED |  |  | Closed | LATE | NA | 17 | 4607242% | 100%
PZ4 | 0051611250 | 003280 | 0051611250-003280 | TEMPLE UNIVERSITY LEW KLEIN COLLEGE OF M | 4601300% | 4599300% | ATA | HUP | WF1816679 | Elec | BUY | ANSI 49 | 4607300% | -37 | 4606300% | 4607600% | 4607100% | FALSE | Feb-2026 | 10 | 10 | 7 | -3 | ON TIME | ON TIME | LATE BY ENG |  | C | 40 | IMPACTED |  |  | Closed | LATE | NA | 17 | 4607642% | 100%
PZ4 | 0051791572 | 000010 | 0051791572-000010 | ADVENT HEALTH CELEBRATION PATIENT TOWER | 4607800% | 4607100% | ATA | ISQ | WF1816745 | Elec | MAKE | ANSI 49 | 4624000% | 12 | 4606300% | 4607200% | 4607300% | FALSE | Feb-2026 | 10 | 8 | 9 | 1 | LATE | LATE | ON TIME BY ENG |  | C | -4 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4607507% | 100%
PZ4 | 0051212323 | 010200 | 0051212323-010200 | GEISINGER MEDICAL CENTER SOUTH TOWER | 4608300% | 4607600% | OHO | OAL | WF1816621 | Mech | BUY | ANSI 49 | 4625400% | 15 | 4606300% | 4607300% | 4607700% | FALSE | Feb-2026 | 10 | 9 | 11 | 2 | LATE | LATE | ON TIME BY ENG |  | C | -5 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 17 | 4607342% | 100%
PZ4 | 0050384250 | 001250 | 0050384250-001250 | NEW PARNASSUS HEIGHTS HOSPITAL - UCSF - | 4608700% | 4608000% | ASP | VL | WF1817227 | Mech | MAKE | ANSI 49 | 4617800% | 18 | 4606400% | 4607100% | 4607300% | FALSE | Feb-2026 | 10 | 6 | 8 | 2 | LATE | LATE | ON TIME BY ENG |  | C | -11 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4607407% | 100%
PZ4 | 0050384250 | 001250 | 0050384250-001250 | NEW PARNASSUS HEIGHTS HOSPITAL - UCSF - | 4608700% | 4608000% | ASP | VL | WF1817252 | Mech | MAKE | ANSI 49 | 4617800% | 18 | 4606400% | 4607100% | 4607200% | FALSE | Feb-2026 | 10 | 6 | 7 | 1 | LATE | LATE | ON TIME BY ENG |  | C | -12 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4607407% | 100%
PZ4 | 0050384250 | 001250 | 0050384250-001250 | NEW PARNASSUS HEIGHTS HOSPITAL - UCSF - | 4608700% | 4608000% | ASP | VL | WF1817258 | Mech | MAKE | ANSI 49 | 4617800% | 18 | 4606400% | 4607100% | 4607800% | FALSE | Feb-2026 | 10 | 6 | 11 | 5 | LATE | LATE | ON TIME BY ENG |  | C | -8 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4607407% | 100%
PZ4 | 0051842216 | 000030 | 0051842216-000030 | FREIGHTLINER - CLEVELAND, NC. | 4608700% | 4608000% | JRC | ISQ | WF1817340 | Mech | MAKE | ANSI 49 | 4619800% | 18 | 4606400% | 4607200% | 4607200% | FALSE | Feb-2026 | 10 | 7 | 7 | 0 | ON TIME | ON TIME | ON TIME BY ENG |  | C | -12 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4607507% | 100%
PZ4 | 0050384250 | 001250 | 0050384250-001250 | NEW PARNASSUS HEIGHTS HOSPITAL - UCSF - | 4608700% | 4608000% | ASP | VL | WF1817261 | Mech | MAKE | ANSI 49 | 4617800% | 18 | 4606400% | 4607100% | 4607600% | FALSE | Feb-2026 | 10 | 6 | 9 | 3 | LATE | LATE | ON TIME BY ENG |  | C | -10 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4607407% | 100%
PZ4 | 0050941348 | 000150 | 0050941348-000150 | FC23-011 3000 KVA SUBSTATION U | 4606600% | 4606300% | JAM | OAL | WF1818518 | Mech | MAKE | ANSI 49 | 4617400% | 1 | 4606600% | 4607300% | 4607800% | FALSE | Feb-2026 | 10 | 6 | 9 | 3 | LATE | LATE | LATE BY ENG |  | C | 9 | IMPACTED |  |  | Closed | LATE | NA | 18 | 4607607% | 100%
PZ4 | 0051829783 | 000010 | 0051829783-000010 | OP-250808-15689594 | 4609400% | 4608700% |  |  | WF1818758 | Elec | BUY | ANSI 49 | 4622700% | 21 | 4606600% | 4607900% | 4607300% | FALSE | Feb-2026 | 10 | 10 | 6 | -4 | ON TIME | ON TIME | ON TIME BY ENG |  | X | -16 | NOT IMPACTED |  |  | Cancelled | ON TIME | NA | 2 | 4607942% | 11.76%
PZ4 | 0051829783 | 000010 | 0051829783-000010 | OP-250808-15689594 | 4609400% | 4608700% | JAM | IJF | WF1818759 | Elec | BUY | ANSI 49 | 4622700% | 21 | 4606600% | 4607900% | 4608300% | FALSE | Feb-2026 | 10 | 10 | 12 | 2 | LATE | LATE | ON TIME BY ENG |  | C | -10 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 17 | 4607942% | 100%
PZ4 | 0051212323 | 010200 | 0051212323-010200 | GEISINGER MEDICAL CENTER SOUTH TOWER | 4608300% | 4607600% | NHO | OAL | WF1824935 | Mech | BUY | ANSI 49 | 4623000% | 3 | 4607900% | 4609300% | 4608600% | FALSE | Feb-2026 | 10 | 11 | 6 | -5 | ON TIME | ON TIME | LATE BY ENG |  | C | 4 | IMPACTED |  |  | Closed | LATE | NA | 17 | 4609342% | 100%
PZ4 | 0051035589 | 000210 | 0051035589-000210 | CPS EMC UPGRADE - SAN ANTONIO - ALTERMAN | 4608700% | 4607800% | ALT | VHL | WF1826493 | Elec | MAKE | ANSI 49 | 4619700% | 5 | 4608300% | 4609200% | 4609000% | FALSE | Mar-2026 | 10 | 8 | 6 | -2 | ON TIME | ON TIME | LATE BY ENG |  | C | 2 | IMPACTED |  |  | Closed | LATE | NA | 18 | 4609507% | 100%
PZ4 | 0051428029 | 000290 | 0051428029-000290 | LMMFC SUB 7 REPLACEMENT PROJECT | 4608000% | 4606900% | MGL | ISQ | WF1818845 | Elec | BUY | ANSI 49 | 4617200% | 10 | 4606800% | 4607900% | 4607900% | FALSE | Feb-2026 | 10 | 9 | 9 | 0 | ON TIME | ON TIME | ON TIME BY ENG |  | C | -2 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 16 | 4607942% | 94.12%
PZ4 | 0051212323 | 010170 | 0051212323-010170 | GEISINGER MEDICAL CENTER SOUTH TOWER | 4608300% | 4607600% | NOH | CML | WF1819210 | Elec | MAKE | ANSI 49 | 4624400% | 11 | 4606900% | 4607600% | 4607800% | FALSE | Feb-2026 | 10 | 6 | 8 | 2 | LATE | LATE | ON TIME BY ENG |  | C | -4 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4607907% | 100%
PZ4 | 0051212323 | 010170 | 0051212323-010170 | GEISINGER MEDICAL CENTER SOUTH TOWER | 4608300% | 4607600% | NOH | CML | WF1819217 | Elec | MAKE | ANSI 49 | 4624400% | 11 | 4606900% | 4607600% | 4607600% | FALSE | Feb-2026 | 10 | 6 | 6 | 0 | ON TIME | ON TIME | ON TIME BY ENG |  | C | -6 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4607907% | 100%
PZ4 | 0051212323 | 010170 | 0051212323-010170 | GEISINGER MEDICAL CENTER SOUTH TOWER | 4608300% | 4607600% | NOH | CML | WF1819309 | Mech | MAKE | ANSI 49 | 4624400% | 11 | 4606900% | 4607600% | 4607300% | FALSE | Feb-2026 | 10 | 6 | 5 | -1 | ON TIME | ON TIME | ON TIME BY ENG |  | C | -7 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4607907% | 100%
PZ4 | 0051212323 | 010170 | 0051212323-010170 | GEISINGER MEDICAL CENTER SOUTH TOWER | 4608300% | 4607600% | NOH | CML | WF1819270 | Mech | BUY | ANSI 49 | 4624400% | 11 | 4606900% | 4607900% | 4607900% | FALSE | Feb-2026 | 10 | 9 | 9 | 0 | ON TIME | ON TIME | ON TIME BY ENG |  | C | -3 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 15 | 4607942% | 88.24%
PZ4 | 0051212323 | 010170 | 0051212323-010170 | GEISINGER MEDICAL CENTER SOUTH TOWER | 4608300% | 4607600% | NOH | CML | WF1819360 | Elec | BUY | ANSI 49 | 4624400% | 11 | 4606900% | 4607900% | 4607900% | FALSE | Feb-2026 | 10 | 9 | 9 | 0 | ON TIME | ON TIME | ON TIME BY ENG |  | C | -3 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 15 | 4607942% | 88.24%
PZ4 | 0051436816 | 000130 | 0051436816-000130 | SPACEX STARBASE GIGABAY UNIT SUBSTATIONS | 4601800% | 4601000% | DMA | HUP | WF1819957 | Elec | BUY | ANSI 49 | 4622700% | -37 | 4607000% | 4608000% | 4607900% | FALSE | Feb-2026 | 10 | 9 | 8 | -1 | ON TIME | ON TIME | LATE BY ENG |  | C | 43 | IMPACTED |  |  | Closed | LATE | NA | 16 | 4608042% | 94.12%
PZ4 | 0051848516 | 000010 | 0051848516-000010 | AT&T SLIDELL ENGINE REPLACEMENT | 4608700% | 4608000% | MGL | GHT | WF1819819 | Elec | BUY | ANSI 49 | 4620300% | 14 | 4607000% | 4608000% | 4608000% | FALSE | Feb-2026 | 10 | 9 | 9 | 0 | ON TIME | ON TIME | ON TIME BY ENG |  | C | -6 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 17 | 4608042% | 100%
PZ4 | 0051035589 | 000210 | 0051035589-000210 | CPS EMC UPGRADE - SAN ANTONIO - ALTERMAN | 4608700% | 4607800% | ALT | VHL | WF1826414 | Elec | BUY | ANSI 49 | 4619700% | 5 | 4608300% | 4609300% | 4609000% | FALSE | Mar-2026 | 10 | 9 | 6 | -3 | ON TIME | ON TIME | LATE BY ENG |  | C | 2 | IMPACTED |  |  | Closed | LATE | NA | 16 | 4609342% | 94.12%
PZ4 | 0051536680 | 000120 | 0051536680-000120 | UNITEDHEALTH GROUP CUL PROJECT, CHASKA, | 4609400% |  | OAL | CML | WF1824999 | Mech | MAKE | ANSI 49 | 4618800% | 12 | 4607900% | 4609000% | 4608500% | FALSE | Feb-2026 | 10 | 8 | 5 | -3 | ON TIME | ON TIME | ON TIME BY ENG |  | C | -8 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4609307% | 100%
PZ4 | 0051631924 | 000020 | 0051631924-000020 | 1319-V/056. M3-SPCC_PN240180-COGENERACIÓ | 4609400% | 4609000% | DMA | GHT | WF1824004 | Elec | MAKE | ANSI 49 | 4620300% | 13 | 4607800% | 4608500% | 4608500% | FALSE | Feb-2026 | 10 | 6 | 6 | 0 | ON TIME | ON TIME | ON TIME BY ENG |  | C | -8 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4608807% | 100%
PZ4 | 0051829783 | 000010 | 0051829783-000010 | OP-250808-15689594 | 4609400% | 4608700% | JAM | IJF | WF1818756 | Elec | BUY | ANSI 49 | 4622700% | 21 | 4606600% | 4607900% | 4609900% | FALSE | Feb-2026 | 10 | 10 | 24 | 14 | LATE | LATE | ON TIME BY ENG |  | C | 4 | IMPACTED |  |  | Closed | LATE | ABIGAIL ESTRELLO ORTIZ | 17 | 4607942% | 100%
PZ4 | 0051095105 | 000400 | 0051095105-000400 | GSK MARIETTA B55 | 4600000% |  | JAM | LDT | WF1820447 | Elec | BUY | ANSI 49 | 4607300% | -52 | 4607100% | 4608300% | 4607900% | FALSE | Feb-2026 | 10 | 9 | 7 | -2 | ON TIME | ON TIME | LATE BY ENG |  | C | 54 | IMPACTED |  |  | Closed | LATE | NA | 17 | 4608342% | 100%
PZ4 | 0051787649 | 000050 | 0051787649-000050 | MICRON ID1 PHASE 2 - F12A UNIT SUBSTATIO | 4606200% |  | SMA | VHL | WF1820356 | Mech | Make | ANSI 49 | 4618400% | -8 | 4607100% | 4607800% | 4607300% | FALSE | Feb-2026 | 10 | 6 | 3 | -3 | ON TIME | ON TIME | LATE BY ENG |  | C | 10 | IMPACTED |  |  | Closed | LATE | NA | 18 | 4608107% | 100%
PZ4 | 0051818022 | 000010 | 0051818022-000010 | GUNDERSEN HEALTH SYSTEM HERITAGE EMERGEN | 4608000% | 4607300% | ANV | RCI | WF1820504 | Elec | BUY | ANSI 49 | 4619500% | 8 | 4607100% | 4608300% | 4608000% | FALSE | Feb-2026 | 10 | 9 | 8 | -1 | ON TIME | ON TIME | LATE BY ENG |  | C | 1 | IMPACTED |  |  | Closed | LATE | NA | 17 | 4608342% | 100%
PZ4 | 0051212323 | 010190 | 0051212323-010190 | GEISINGER MEDICAL CENTER SOUTH TOWER | 4608300% | 4607600% | NOH | OAL | WF1820617 | Mech | MAKE | ANSI 49 | 4624400% | 9 | 4607100% | 4607900% | 4607900% | FALSE | Feb-2026 | 10 | 7 | 7 | 0 | ON TIME | ON TIME | LATE BY ENG |  | C | -3 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4608207% | 100%
PZ4 | 0051212323 | 010190 | 0051212323-010190 | GEISINGER MEDICAL CENTER SOUTH TOWER | 4608300% | 4607600% | NOH | OAL | WF1820616 | Mech | MAKE | ANSI 49 | 4624400% | 9 | 4607100% | 4607900% | 4607900% | FALSE | Feb-2026 | 10 | 7 | 7 | 0 | ON TIME | ON TIME | LATE BY ENG |  | C | -3 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4608207% | 100%
PZ4 | 0051212323 | 010190 | 0051212323-010190 | GEISINGER MEDICAL CENTER SOUTH TOWER | 4608300% | 4607600% | NOH | OAL | WF1820618 | Mech | MAKE | ANSI 49 | 4624400% | 9 | 4607100% | 4607900% | 4607900% | FALSE | Feb-2026 | 10 | 7 | 7 | 0 | ON TIME | ON TIME | LATE BY ENG |  | C | -3 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4608207% | 100%
PZ4 | 0051272041 | 002870 | 0051272041-002870 | UC BERKELEY HEATHCOCK HALL | 4608700% | 4608000% | UFA | GHT | WF1820647 | Mech | MAKE | ANSI 49 | 4619100% | 13 | 4607100% | 4607900% | 4607900% | FALSE | Feb-2026 | 10 | 7 | 7 | 0 | ON TIME | ON TIME | ON TIME BY ENG |  | C | -7 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4608207% | 100%
PZ4 | 0051733188 | 000410 | 0051733188-000410 | PROJECT ICY HOT CORE AND SHELL | 4609200% | 4608500% | DEB | HUP | WF1821083 | Mech | MAKE | ANSI 49 | 4621200% | 15 | 4607200% | 4607900% | 4608000% | FALSE | Feb-2026 | 10 | 6 | 7 | 1 | LATE | LATE | ON TIME BY ENG |  | C | -9 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4608207% | 100%
PZ4 | 0051436816 | 000030 | 0051436816-000030 | SPACEX STARBASE GIGABAY UNIT SUBSTATIONS | 4601700% | 4601000% | DMA | KGF | WF1832921 | Elec | BUY | ANSI 49 | 4610800% | -58 | 4609800% | 4611100% |  | TRUE | Mar-2026 | 10 | 10 | 3 | -7 | ON TIME | ON TIME | LATE BY ENG |  | I | 59 | IMPACTED |  |  | 59 | LATE | JUAN CARLOS MIRANDA | 1 | 4611142% | 5.882%
PZ4 | 0051631924 | 000020 | 0051631924-000020 | 1319-V/056. M3-SPCC_PN240180-COGENERACIÓ | 4609400% | 4609000% | DMA | GHT | WF1826405 | Mech | MAKE | ANSI 49 | 4620300% | 10 | 4608300% | 4609100% | 4609000% | FALSE | Mar-2026 | 10 | 7 | 6 | -1 | ON TIME | ON TIME | ON TIME BY ENG |  | C | -5 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4609407% | 100%
PZ4 | 0051631924 | 000020 | 0051631924-000020 | 1319-V/056. M3-SPCC_PN240180-COGENERACIÓ | 4609400% | 4609000% | DMA | GHT | WF1826375 | Elec | MAKE | ANSI 49 | 4620300% | 10 | 4608300% | 4609100% | 4608600% | FALSE | Mar-2026 | 10 | 7 | 4 | -3 | ON TIME | ON TIME | ON TIME BY ENG |  | C | -7 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4609407% | 100%
PZ4 | 0051829783 | 000010 | 0051829783-000010 | OP-250808-15689594 | 4609400% | 4608700% | JAM | IJF | WF1818757 | Elec | BUY | ANSI 49 | 4622700% | 21 | 4606600% | 4607900% | 4608500% | FALSE | Feb-2026 | 10 | 10 | 14 | 4 | LATE | LATE | ON TIME BY ENG |  | C | -8 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 17 | 4607942% | 100%
PZ4 | 0051829783 | 000010 | 0051829783-000010 | OP-250808-15689594 | 4609400% | 4608700% | NOH | IFJ | WF1819790 | Elec | BUY | ANSI 49 | 4619900% | 19 | 4607000% | 4608000% | 4608300% | FALSE | Feb-2026 | 10 | 9 | 10 | 1 | LATE | LATE | ON TIME BY ENG |  | C | -10 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 17 | 4608042% | 100%
PZ4 | 0051733188 | 000490 | 0051733188-000490 | PROJECT ICY HOT CORE AND SHELL | 4609800% | 4609100% | DEV | KGF | WF1821739 | Mech | BUY | ANSI 49 | 4619600% | 18 | 4607300% | 4605700% | 4608300% | FALSE | Feb-2026 | 10 | -13 | 7 | 20 | LATE | SUPER LATE | ON TIME BY ENG |  | C | -12 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 17 | 4605742% | 100%
PZ4 | 0051829783 | 000010 | 0051829783-000010 | OP-250808-15689594 | 4609400% | 4608700% | NOH | IFJ | WF1819796 | Elec | MAKE | ANSI 49 | 4619900% | 19 | 4607000% | 4607700% | 4608400% | FALSE | Feb-2026 | 10 | 6 | 11 | 5 | LATE | LATE | ON TIME BY ENG |  | C | -9 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4608007% | 100%
PZ4 | 0051829783 | 000010 | 0051829783-000010 | OP-250808-15689594 | 4609400% | 4608700% | JAM | IJF | WF1821248 | Mech | MAKE | ANSI 49 | 4619900% | 17 | 4607200% | 4607900% | 4608300% | FALSE | Feb-2026 | 10 | 6 | 8 | 2 | LATE | LATE | ON TIME BY ENG |  | C | -10 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4608207% | 100%
PZ4 | 0051735870 | 000010 | 0051735870-000010 | PROJECT OPAL LLE3 | 4611100% | 4609800% | JAM | RCI | WF1819913 | Elec | MAKE | ANSI 49 | 4622700% | 30 | 4607000% | 4607700% | 4609900% | FALSE | Feb-2026 | 10 | 6 | 22 | 16 | LATE | SUPER LATE | ON TIME BY ENG |  | C | -9 | NOT IMPACTED |  |  | Closed | ON TIME | JUAN CARLOS MIRANDA | 18 | 4608007% | 100%
PZ4 | 0051829783 | 000010 | 0051829783-000010 | OP-250808-15689594 | 4609400% | 4608700% | JAM | IJF | WF1821779 | Mech | MAKE | ANSI 49 | 4619900% | 16 | 4607300% | 4608000% | 4609900% | FALSE | Feb-2026 | 10 | 6 | 19 | 13 | LATE | LATE | ON TIME BY ENG |  | C | 4 | IMPACTED |  |  | Closed | LATE | VICTOR HUGO RODRIGEZ TORRALBA | 18 | 4608307% | 100%
PZ4 | 0051829783 | 000010 | 0051829783-000010 | OP-250808-15689594 | 4609400% | 4608700% | JAM | IJF | WF1821837 | Mech | MAKE | ANSI 49 | 4619900% | 16 | 4607300% | 4608000% | 4609100% | FALSE | Feb-2026 | 10 | 6 | 13 | 7 | LATE | LATE | ON TIME BY ENG |  | C | -4 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4608307% | 100%
PZ4 | 0051829783 | 000010 | 0051829783-000010 | OP-250808-15689594 | 4609400% | 4608700% | JAM | IJF | WF1821894 | Mech | BUY | ANSI 49 | 4619900% | 16 | 4607300% | 4608500% | 4608500% | FALSE | Feb-2026 | 10 | 9 | 9 | 0 | ON TIME | ON TIME | ON TIME BY ENG |  | C | -8 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 17 | 4608542% | 100%
PZ4 | 0051733188 | 000490 | 0051733188-000490 | PROJECT ICY HOT CORE AND SHELL | 4609700% | 4609200% | DEV | KGF | WF1821773 | Mech | MAKE | ANSI 49 | 4619600% | 17 | 4607300% | 4608000% | 4609300% | FALSE | Feb-2026 | 10 | 6 | 15 | 9 | LATE | LATE | ON TIME BY ENG |  | C | -3 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4608307% | 100%
PZ4 | 0051829783 | 000010 | 0051829783-000010 | OP-250808-15689594 | 4609400% | 4608700% | JAM | IJF | WF1821845 | Mech | MAKE | ANSI 49 | 4619900% | 16 | 4607300% | 4608000% | 4608700% | FALSE | Feb-2026 | 10 | 6 | 11 | 5 | LATE | LATE | ON TIME BY ENG |  | C | -6 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4608307% | 100%
PZ4 | 0050365418 | 000070 | 0050365418-000070 | BF GOODRICH - FORT WAYNE, IN - OUTDOOR | 4606700% |  | DRV | DP | WF1823455 | Elec | BUY | ANSI 49 | 4624200% | -7 | 4607700% | 4608700% | 4610800% | FALSE | Feb-2026 | 10 | 9 | 24 | 15 | LATE | SUPER LATE | LATE BY ENG |  | C | 30 | IMPACTED |  |  | Closed | LATE | NA | 17 | 4608742% | 100%
PZ4 | 0051829783 | 000010 | 0051829783-000010 | OP-250808-15689594 | 4609400% | 4608700% | JAM | IJF | WF1822810 | Mech | MAKE | ANSI 49 | 4619900% | 15 | 4607600% | 4608500% | 4608400% | FALSE | Feb-2026 | 10 | 8 | 7 | -1 | ON TIME | ON TIME | ON TIME BY ENG |  | C | -9 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4608807% | 100%
PZ4 | 0051735870 | 000010&20 | 0051735870-000010&20 | PROJECT OPAL LLE3 | 4611100% | 4609800% | JAM | RCI | WF1823506 | Elec | MAKE | ANSI 49 | 4622700% | 25 | 4607700% | 4608500% | 4607800% | FALSE | Feb-2026 | 10 | 7 | 2 | -5 | ON TIME | ON TIME | ON TIME BY ENG |  | X | -24 | NOT IMPACTED |  |  | Cancelled | ON TIME | NA | 0 | 4608807% | 0%
PZ4 | 0051829783 | 000010 | 0051829783-000010 | OP-250808-15689594 | 4609400% | 4608700% | JAM | IJF | WF1821913 | Mech | MAKE | ANSI 49 | 4619900% | 16 | 4607300% | 4608300% | 4608700% | FALSE | Feb-2026 | 10 | 7 | 11 | 4 | LATE | LATE | ON TIME BY ENG |  | C | -6 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4608607% | 100%
PZ4 | 0051275480 | 000950 | 0051275480-000950 | TAYLOR DAIRY ROAD WTP | 4602000% | 4600900% | OAC | RCI | WF1823416 | Mech | CNG-BOM | ANSI 49 | 4609400% | -42 | 4607700% | 4608000% | 4608000% | FALSE | Feb-2026 | 10 | 4 | 4 | 0 | ON TIME | ON TIME | LATE BY ENG |  | C | 44 | IMPACTED |  |  | Closed | LATE | NA | 11 | 4608042% | 100%
PZ4 | 0051035589 | 000220 | 0051035589-000220 | CPS EMC UPGRADE - SAN ANTONIO - ALTERMAN | 4608700% | 4607800% | ALT | VL | WF1832012 | Mech | MAKE | ANSI 49 | 4619700% | -5 | 4609300% | 4610400% |  | TRUE | Mar-2026 | 10 | 8 | 6 | -2 | ON TIME | ON TIME | LATE BY ENG |  | I | 10 | IMPACTED |  |  | 10 | LATE | JUAN ANTONIO CABELLO | 11 | 4610707% | 61.11%
PZ4 | 0051829783 | 000010 | 0051829783-000010 | OP-250808-15689594 | 4609400% | 4608700% | JAM | IJF | WF1824795 | Mech | MAKE | ANSI 49 | 4620900% | 12 | 4607900% | 4608600% | 4608400% | FALSE | Feb-2026 | 10 | 6 | 4 | -2 | ON TIME | ON TIME | ON TIME BY ENG |  | C | -9 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4608907% | 100%
PZ4 | 0051829783 | 000010 | 0051829783-000010 | OP-250808-15689594 | 4609400% | 4608700% | JAM | IJF | WF1822717 | Mech | MAKE | ANSI 49 | 4619900% | 15 | 4607600% | 4608400% |  | TRUE | Feb-2026 | 10 | 7 | 19 | 12 | LATE | LATE | ON TIME BY ENG |  | I | 5 | IMPACTED |  |  | 5 | LATE | JUAN CARLOS MIRANDA | 17 | 4608707% | 94.44%
PZ4 | 0051829783 | 000010 | 0051829783-000010 | OP-250808-15689594 | 4609400% | 4608700% | JAM | IJF | WF1823513 | Elec | BUY | ANSI 49 | 4619900% | 14 | 4607700% | 4609100% | 4608600% | FALSE | Feb-2026 | 10 | 11 | 8 | -3 | ON TIME | ON TIME | ON TIME BY ENG |  | C | -7 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 17 | 4609142% | 100%
PZ4 | 0050384250 | 001230 | 0050384250-001230 | NEW PARNASSUS HEIGHTS HOSPITAL - UCSF - | 4609400% | 4605900% | ASP | VHL | WF1824197 | Mech | MAKE | ANSI 49 | 4623300% | 13 | 4607800% | 4608600% |  | TRUE | Feb-2026 | 10 | 7 | 17 | 10 | LATE | LATE | ON TIME BY ENG |  | I | 5 | IMPACTED |  |  | 5 | LATE | VICTOR HUGO RODRIGEZ TORRALBA | 12 | 4608907% | 66.67%
PZ4 | 0051829783 | 000010 | 0051829783-000010 | OP-250808-15689594 | 4609400% | 4608700% | JAM | IJF | WF1822807 | Mech | MAKE | ANSI 49 | 4619900% | 15 | 4607600% | 4608500% | 4609000% | FALSE | Feb-2026 | 10 | 8 | 11 | 3 | LATE | LATE | ON TIME BY ENG |  | C | -5 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4608807% | 100%
PZ4 | 0051733188 | 000490 | 0051733188-000490 | PROJECT ICY HOT CORE AND SHELL | 4609800% | 4609100% | DEV | KGF | WF1821726 | Mech | MAKE | ANSI 49 | 4619600% | 18 | 4607300% | 4608000% | 4608400% | FALSE | Feb-2026 | 10 | 6 | 8 | 2 | LATE | LATE | ON TIME BY ENG |  | C | -11 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4608307% | 100%
PZ4 | 0051733188 | 000490 | 0051733188-000490 | PROJECT ICY HOT CORE AND SHELL | 4609800% | 4609100% | DEV | KGF | WF1821729 | Mech | MAKE | ANSI 49 | 4619600% | 18 | 4607300% | 4608000% | 4608500% | FALSE | Feb-2026 | 10 | 6 | 9 | 3 | LATE | LATE | ON TIME BY ENG |  | C | -10 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4608307% | 100%
PZ4 | 0051674363 | 000010 | 0051674363-000010 | W912EF25QA023-ARMY US | 4610100% | 4609400% | HMA | ISQ | WF1824062 | Mech | BUY | ANSI 49 | 4602900% | 18 | 4607800% | 4609000% | 4609400% | FALSE | Feb-2026 | 10 | 9 | 13 | 4 | LATE | LATE | ON TIME BY ENG |  | C | -6 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 16 | 4609042% | 94.12%
PZ4 | 0051733188 | 000490 | 0051733188-000490 | PROJECT ICY HOT CORE AND SHELL | 4609800% | 4609100% | DEV | KFG | WF1821822 | Mech | MAKE | ANSI 49 | 4619600% | 18 | 4607300% | 4608000% | 4608300% | FALSE | Feb-2026 | 10 | 6 | 7 | 1 | LATE | LATE | ON TIME BY ENG |  | C | -12 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4608307% | 100%
PZ4 | 0051536680 | 000120 | 0051536680-000120 | UNITEDHEALTH GROUP CUL PROJECT, CHASKA, | 4609400% |  | OAC | CML | WF1826241 | Mech | MAKE | ANSI 49 | 4618800% | 10 | 4608300% | 4609000% | 4608600% | FALSE | Mar-2026 | 10 | 6 | 4 | -2 | ON TIME | ON TIME | ON TIME BY ENG |  | C | -7 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4609307% | 100%
PZ4 | 0051434217 | 000320 | 0051434217-000320 | SMUD FAOB | 4611200% | 4610500% | JAM | AL | WF1824056 | Elec | BUY | ANSI 49 | 4622500% | 25 | 4607800% | 4609000% | 4609400% | FALSE | Feb-2026 | 10 | 9 | 13 | 4 | LATE | LATE | ON TIME BY ENG |  | C | -13 | NOT IMPACTED |  |  | Closed | ON TIME | JOSE PABLO AGUILAR | 17 | 4609042% | 100%
PZ4 | 0051674363 | 000010 | 0051674363-000010 | W912EF25QA023-ARMY US | 4610100% | 4609400% | HMA | ISQ | WF1824946 | Mech | MAKE | ANSI 49 | 4622300% | 17 | 4607900% | 4609000% | 4608000% | FALSE | Feb-2026 | 10 | 8 | 2 | -6 | ON TIME | ON TIME | ON TIME BY ENG |  | X | -16 | NOT IMPACTED |  |  | Cancelled | ON TIME | NA | 1 | 4609307% | 5.556%
PZ4 | 0051829783 | 000010 | 0051829783-000010 | OP-250808-15689594 | 4609400% | 4608700% | JAM | IJF | WF1824061 | Mech | MAKE | ANSI 49 | 4619900% | 13 | 4607800% | 4608500% |  | TRUE | Feb-2026 | 10 | 6 | 17 | 11 | LATE | LATE | ON TIME BY ENG |  | I | 5 | IMPACTED |  |  | 5 | LATE | VICTOR HUGO RODRIGEZ TORRALBA | 12 | 4608807% | 66.67%
PZ4 | 0050384250 | 001230 | 0050384250-001230 | NEW PARNASSUS HEIGHTS HOSPITAL - UCSF - | 4609400% | 4608700% | ASP | VHL | WF1826955 | Mech | MAKE | ANSI 49 | 4624000% | 9 | 4608400% | 4609100% |  | TRUE | Mar-2026 | 10 | 6 | 13 | 7 | LATE | LATE | LATE BY ENG |  | I | 5 | IMPACTED |  |  | 5 | LATE | JUAN CARLOS MIRANDA | 16 | 4609407% | 88.89%
PZ4 | 0051733188 | 000410 | 0051733188-000410 | PROJECT ICY HOT CORE AND SHELL | 4609800% | 4609100% | DEV | KGF | WF1824039 | Elec | BUY | ANSI 49 | 4619500% | 15 | 4607800% | 4609000% | 4608700% | FALSE | Feb-2026 | 10 | 9 | 8 | -1 | ON TIME | ON TIME | ON TIME BY ENG |  | C | -8 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 17 | 4609042% | 100%
PZ4 | 0051829783 | 000010 | 0051829783-000010 | OP-250808-15689594 | 4609400% | 4608700% | JAM | IJF | WF1828531 | Elec | BUY | ANSI 49 | 4620900% | 7 | 4608600% | 4610000% |  | TRUE | Mar-2026 | 10 | 11 | 11 | 0 | ON TIME | ON TIME | LATE BY ENG |  | I | 5 | IMPACTED |  |  | 5 | LATE | AILIA TERESA CHUCUAN | 12 | 4610042% | 70.59%
PZ4 | 0051829783 | 000010 | 0051829783-000010 | OP-250808-15689594 | 4609400% | 4608700% | JAM | IJF | WF1829894 | Mech | BUY | ANSI 49 | 4622700% | 5 | 4609000% | 4610400% |  | TRUE | Mar-2026 | 10 | 11 | 9 | -2 | ON TIME | ON TIME | LATE BY ENG |  | I | 5 | IMPACTED |  |  | 5 | LATE | REBECA CISNEROS | 9 | 4610442% | 52.94%
PZ4 | 0051536680 | 000120 | 0051536680-000120 | UNITEDHEALTH GROUP CUL PROJECT, CHASKA, | 4609400% |  | OAC | CML | WF1825519 | Mech | MAKE | ANSI 49 | 4617800% | 11 | 4608000% | 4609000% | 4609100% | FALSE | Feb-2026 | 10 | 7 | 8 | 1 | LATE | LATE | ON TIME BY ENG |  | C | -4 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4609307% | 100%
PZ4 | 0051733188 | 000430 | 0051733188-000430 | PROJECT ICY HOT CORE AND SHELL | 4609700% | 4609700% | DEV | HUP | WF1822560 | Mech | MAKE | ANSI 49 | 4621100% | 16 | 4607600% | 4608300% | 4609000% | FALSE | Feb-2026 | 10 | 6 | 11 | 5 | LATE | LATE | ON TIME BY ENG |  | C | -6 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4608607% | 100%
PZ4 | 0051733188 | 000450 | 0051733188-000450 | PROJECT ICY HOT CORE AND SHELL | 4610100% | 4609700% | DVA | KGF | WF1825447 | Mech | MAKE | ANSI 49 | 4620900% | -6 | 4610800% | 4608700% | 4608600% | FALSE | Mar-2026 | 10 | -16 | -17 | -1 | ON TIME | ON TIME | LATE BY ENG |  | C | -12 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4609007% | 100%
PZ4 | 0051733188 | 000410 | 0051733188-000410 | PROJECT ICY HOT CORE AND SHELL | 4609700% | 4609000% | DEV | HUP | WF1825521 | Mech | BUY | ANSI 49 | 4619500% | 12 | 4608000% | 4609200% | 4609400% | FALSE | Feb-2026 | 10 | 9 | 11 | 2 | LATE | LATE | ON TIME BY ENG |  | C | -2 | NOT IMPACTED |  |  | Closed | ON TIME | VICTOR HUGO RODRIGEZ TORRALBA | 17 | 4609242% | 100% | FLAGGED
PZ4 | 0051733188 | 000410 | 0051733188-000410 | PROJECT ICY HOT CORE AND SHELL | 4609700% | 4609000% | DEV | HUP | WF1825523 | Mech | MAKE | ANSI 49 | 4619500% | 12 | 4608000% | 4609200% |  | TRUE | Feb-2026 | 10 | 9 | 15 | 6 | LATE | LATE | ON TIME BY ENG |  | I | 4 | IMPACTED |  |  | 4 | LATE | FERNANDO CASAS | 15 | 4609507% | 83.33%
PZ4 | 0051035589 | 000210 | 0051035589-000210 | CPS EMC UPGRADE - SAN ANTONIO - ALTERMAN | 4608700% | 4607800% | ALT | VHL | WF1826494 | Elec | MAKE | ANSI 49 | 4619700% | 5 | 4608300% | 4609200% | 4609300% | FALSE | Mar-2026 | 10 | 8 | 9 | 1 | LATE | LATE | LATE BY ENG |  | C | 5 | IMPACTED |  |  | Closed | LATE | NA | 18 | 4609507% | 100%
PZ4 | 0051425171 | 000660 | 0051425171-000660 | BONNEVILLE LOCK AND DAM BRADFORD ISLAND | 4609800% | 4608700% | JAM | ISQ | WF1833724 | Mech | MAKE | ANSI 49 | 4626700% | -2 | 2026-03-18 | 2026-03-25 |  | TRUE | Mar-2026 | 10 | 6 | 2 | -4 | ON TIME | ON TIME | LATE BY ENG |  | I | 3 | IMPACTED |  |  | 3 | LATE | JUAN CARLOS MIRANDA | 7 | 4610907% | 38.89%
PZ4 | 0051829783 | 000010 | 0051829783-000010 | OP-250808-15689594 | 4609400% | 4608700% | JAM | IJF | WF1827035 | Elec | MAKE | ANSI 49 | 4620900% | 9 | 4608400% | 4609400% | 4609400% | FALSE | Mar-2026 | 10 | 9 | 9 | 0 | ON TIME | ON TIME | LATE BY ENG |  | C | 1 | IMPACTED |  |  | Closed | LATE | JOSE PABLO AGUILAR | 18 | 4609707% | 100%
PZ4 | 0051271091 | 000890 | 0051271091-000890 | POLK REGIONAL WC SE WELLFIELD AND WATER | 4610100% | 4609400% | ATA | OAL | WF1827053 | Mech | MAKE | ANSI 49 | 4625200% | 14 | 4608400% | 4609100% |  | TRUE | Mar-2026 | 10 | 6 | 13 | 7 | LATE | LATE | ON TIME BY ENG |  | I | -2 | NOT IMPACTED |  |  | -2 | ON TIME | VICTOR HUGO RODRIGEZ TORRALBA | 12 | 4609407% | 66.67%
PZ4 | 0051271091 | 000890 | 0051271091-000890 | POLK REGIONAL WC SE WELLFIELD AND WATER | 4610100% | 4609400% | ATA | OAL | WF1827055 | Mech | MAKE | ANSI 49 | 4625200% | 14 | 4608400% | 4609100% |  | TRUE | Mar-2026 | 10 | 6 | 13 | 7 | LATE | LATE | ON TIME BY ENG |  | I | -2 | NOT IMPACTED |  |  | -2 | ON TIME | FERNANDO CASAS | 15 | 4609407% | 83.33%
PZ4 | 0051271091 | 000890 | 0051271091-000890 | POLK REGIONAL WC SE WELLFIELD AND WATER | 4610100% | 4609400% | ATA | OAL | WF1827056 | Mech | BUY | ANSI 49 | 4625200% | 14 | 4608400% | 4609100% |  | TRUE | Mar-2026 | 10 | 6 | 13 | 7 | LATE | LATE | ON TIME BY ENG |  | I | -2 | NOT IMPACTED |  |  | -2 | ON TIME | FERNANDO CASAS | 11 | 4609142% | 64.71%
PZ4 | 0051271091 | 000890 | 0051271091-000890 | POLK REGIONAL WC SE WELLFIELD AND WATER | 4610100% | 4609400% | ATA | OAL | WF1827367 | Elec | MAKE | ANSI 49 | 4609900% | 14 | 4608400% | 4609300% | 4609200% | FALSE | Mar-2026 | 10 | 8 | 7 | -1 | ON TIME | ON TIME | ON TIME BY ENG |  | C | -8 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4609607% | 100%
PZ4 | 0051732952 | 000010 | 0051732952-000010 | NOVO NORDISK - BLDG QC CHEM-RM LAB - CLA | 4610100% |  | DEV | ISQ | WF1829949 | Mech | MAKE | ANSI 49 | 4623300% | 10 | 4609000% | 4610000% |  | TRUE | Mar-2026 | 10 | 9 | 9 | 0 | ON TIME | ON TIME | ON TIME BY ENG |  | I | -2 | NOT IMPACTED |  |  | -2 | ON TIME | VICTOR HUGO RODRIGEZ TORRALBA | 12 | 4610307% | 66.67%
PZ4 | 0051735870 | 000010&20 | 0051735870-000010&20 | PROJECT OPAL LLE3 | 4611100% | 4609800% | JAM | RCI | WF1823503 | Elec | BUY | ANSI 49 | 4622700% | 25 | 4607700% | 4609000% | 4608600% | FALSE | Feb-2026 | 10 | 10 | 8 | -2 | ON TIME | ON TIME | ON TIME BY ENG |  | C | -18 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 17 | 4609042% | 100%
PZ4 | 0051735870 | 000010 | 0051735870-000010 | PROJECT OPAL LLE3 | 4611100% | 4609800% | JAM | RCI | WF1823970 | Elec | MAKE | ANSI 49 | 4622500% | 24 | 4607800% | 4608500% | 4608600% | FALSE | Feb-2026 | 10 | 6 | 7 | 1 | LATE | LATE | ON TIME BY ENG |  | C | -18 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4608807% | 100%
PZ4 | 0051519925 | 000010 | 0051519925-000010 | DUNEDIN WWTP ELECTRICAL SYSTEM UPGRADES | 4610800% | 4610100% | DMA | ODE | WF1826982 | Mech | MAKE | ANSI 49 | 4624800% | 19 | 4608400% | 4609100% |  | TRUE | Mar-2026 | 10 | 6 | 13 | 7 | LATE | LATE | ON TIME BY ENG |  | I | -7 | NOT IMPACTED |  |  | -7 | ON TIME | JUAN CARLOS MIRANDA | 16 | 4609407% | 88.89%
PZ4 | 0051519925 | 000010 | 0051519925-000010 | DUNEDIN WWTP ELECTRICAL SYSTEM UPGRADES | 4610800% | 4610100% | DMA | ODE | WF1827051 | Mech | MAKE | ANSI 49 | 4624800% | 19 | 4608400% | 4609100% |  | TRUE | Mar-2026 | 10 | 6 | 13 | 7 | LATE | LATE | ON TIME BY ENG |  | I | -7 | NOT IMPACTED |  |  | -7 | ON TIME | VICTOR HUGO RODRIGEZ TORRALBA | 12 | 4609407% | 66.67%
PZ4 | 0051460807 | 010720 | 0051460807-010720 | UT RED MCCOMBS UNDERGRADUATE SCHOOL OF B | 4610800% | 4610100% | SPH |  | WF1827137 | Elec | MAKE | ANSI 49 | 4610000% | 19 | 4608400% | 4609100% | 4609200% | FALSE | Mar-2026 | 10 | 6 | 7 | 1 | LATE | LATE | ON TIME BY ENG |  | C | -13 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4609407% | 100%
PZ4 | 0051519925 | 000010 | 0051519925-000010 | DUNEDIN WWTP ELECTRICAL SYSTEM UPGRADES | 4610800% | 4610100% | DMA | ODE | WF1827086 | Mech | MAKE | ANSI 49 | 4624800% | 19 | 4608400% | 4609100% |  | TRUE | Mar-2026 | 10 | 6 | 13 | 7 | LATE | LATE | ON TIME BY ENG |  | I | -7 | NOT IMPACTED |  |  | -7 | ON TIME | JUAN CARLOS MIRANDA | 16 | 4609407% | 88.89%
PZ4 | 0051442285 | 000110 | 0051442285-000110 | GIGABAY 15KV SUBSTATIONS REV3 STARBASE T | 4608700% |  | DMA | VHL | WF1827802 | Elec | BUY | ANSI 49 | 4614200% | 3 | 4608500% | 4609900% | 4609300% | FALSE | Mar-2026 | 10 | 11 | 7 | -4 | ON TIME | ON TIME | LATE BY ENG |  | C | 5 | IMPACTED |  |  | Closed | LATE | NA | 16 | 4609942% | 94.12%
PZ4 | 0051442285 | 000110 | 0051442285-000110 | GIGABAY 15KV SUBSTATIONS REV3 STARBASE T | 4608700% |  | DMA | VL | WF1827869 | Mech | MAKE | ANSI 49 | 4613500% | 3 | 4608500% | 4609300% | 4609100% | FALSE | Mar-2026 | 10 | 7 | 5 | -2 | ON TIME | ON TIME | LATE BY ENG |  | C | 3 | IMPACTED |  |  | Closed | LATE | NA | 18 | 4609607% | 100%
PZ4 | 0051460807 | 010720 | 0051460807-010720 | UT RED MCCOMBS UNDERGRADUATE SCHOOL OF B | 4610800% | 4610100% | SPH |  | WF1827155 | Elec | BUY | ANSI 49 | 4610000% | 19 | 4608400% | 4609100% |  | TRUE | Mar-2026 | 10 | 6 | 13 | 7 | LATE | LATE | ON TIME BY ENG |  | I | -7 | NOT IMPACTED |  |  | -7 | ON TIME | JUAN CARLOS MIRANDA | 4 | 4609142% | 23.53%
PZ4 | 0051519925 | 000010 | 0051519925-000010 | DUNEDIN WWTP ELECTRICAL SYSTEM UPGRADES | 4610800% | 4610100% | DMA | ODE | WF1827854 | Mech | MAKE | ANSI 49 | 4624100% | 18 | 4608500% | 4609300% | 4609200% | FALSE | Mar-2026 | 10 | 7 | 6 | -1 | ON TIME | ON TIME | ON TIME BY ENG |  | C | -13 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4609607% | 100%
PZ4 | 0050384250 | 001230 | 0050384250-001230 | NEW PARNASSUS HEIGHTS HOSPITAL - UCSF - | 4609400% | 4608700% | ASP | VHL | WF1828546 | Mech | MAKE | ANSI 49 | 4608900% | 7 | 4608600% | 4609400% | 4609200% | FALSE | Mar-2026 | 10 | 7 | 5 | -2 | ON TIME | ON TIME | LATE BY ENG |  | C | -3 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4609707% | 100%
PZ4 | 0051519925 | 000010 | 0051519925-000010 | DUNEDIN WWTP ELECTRICAL SYSTEM UPGRADES | 4610800% | 4610100% | DMA | ODE | WF1827690 | Elec | MAKE | ANSI 49 | 4624100% | 18 | 4608500% | 4609200% |  | TRUE | Mar-2026 | 10 | 6 | 12 | 6 | LATE | LATE | ON TIME BY ENG |  | I | -7 | NOT IMPACTED |  |  | -7 | ON TIME | VICTOR HUGO RODRIGEZ TORRALBA | 12 | 4609507% | 66.67%
PZ4 | 0051733188 | 000390 | 0051733188-000390 | PROJECT ICY HOT CORE AND SHELL | 4609700% | 4609400% | DEV | LDT | WF1828484 | Mech | MAKE | ANSI 49 | 4622400% | 8 | 4608600% | 4609300% | 4609300% | FALSE | Mar-2026 | 10 | 6 | 6 | 0 | ON TIME | ON TIME | LATE BY ENG |  | C | -3 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4609607% | 100%
PZ4 | 0051872300 | 000010 | 0051872300-000010 | WHOLESTONE FOODS FREEZER/COOLER EXPANSIO | 4610800% | 4610100% | JRC | CL | WF1828567 | Mech | MAKE | ANSI 49 | 4625400% | 17 | 4608600% | 4609400% | 4609200% | FALSE | Mar-2026 | 10 | 7 | 5 | -2 | ON TIME | ON TIME | ON TIME BY ENG |  | C | -13 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4609707% | 100%
PZ4 | 0051733188 | 000530 | 0051733188-000530 | PROJECT ICY HOT CORE AND SHELL | 4609700% | 4609400% | DEV | KGF | WF1829111 | Mech | MAKE | ANSI 49 | 4619500% | 7 | 4608700% | 4609400% | 4609900% | FALSE | Mar-2026 | 10 | 6 | 9 | 3 | LATE | LATE | LATE BY ENG |  | C | 3 | IMPACTED |  |  | Closed | LATE | NA | 18 | 4609707% | 100%
PZ4 | 0051679732 | 000170 | 0051679732-000170 | AT&T 105 AUD – 9TH FLOOR SOUTH AON CLOUD | 4612900% | 4613600% | HMA |  | WF1828953 | Elec | MAKE | ANSI 49 | 4624300% | 31 | 4608700% | 4609400% |  | TRUE | Mar-2026 | 10 | 6 | 10 | 4 | LATE | LATE | ON TIME BY ENG |  | I | -22 | NOT IMPACTED |  |  | -22 | ON TIME | FERNANDO CASAS | 15 | 4609707% | 83.33%
PZ4 | 0051679732 | 000170 | 0051679732-000170 | AT&T 105 AUD – 9TH FLOOR SOUTH AON CLOUD | 4612900% | 4613600% | HMA |  | WF1828955 | Elec | BUY | ANSI 49 | 4624300% | 31 | 4608700% | 4610100% |  | TRUE | Mar-2026 | 10 | 11 | 10 | -1 | ON TIME | ON TIME | ON TIME BY ENG |  | I | -22 | NOT IMPACTED |  |  | -22 | ON TIME | JUAN CARLOS MIRANDA | 4 | 4610142% | 23.53%
PZ4 | 0051519925 | 000010 | 0051519925-000010 | DUNEDIN WWTP ELECTRICAL SYSTEM UPGRADES | 4610800% | 4610100% | DMA | ODE | WF1830767 | Elec | BUY | ANSI 49 | 4624800% | 14 | 4609100% | 4610600% |  | TRUE | Mar-2026 | 10 | 12 | 8 | -4 | ON TIME | ON TIME | ON TIME BY ENG |  | I | -7 | NOT IMPACTED |  |  | -7 | ON TIME | REGINA LOPEZ | 2 | 4610642% | 11.76%
PZ4 | 0051878856 | 000010 | 0051878856-000010 | DCH EAST KITCHEN MACHINE ROOM SWITCHBOAR | 4610800% | 4610100% | ATA | ODE | WF1833232 | Elec | MAKE | ANSI 49 | 4626100% | 9 | 2026-03-17 | 2026-03-26 |  | TRUE | Mar-2026 | 10 | 8 | 3 | -5 | ON TIME | ON TIME | LATE BY ENG |  | I | -7 | NOT IMPACTED |  |  | -7 | ON TIME | JUAN CARLOS MIRANDA | 7 | 4611007% | 38.89%
PZ4 | 0051878856 | 000010 | 0051878856-000010 | DCH EAST KITCHEN MACHINE ROOM SWITCHBOAR | 4610800% | 4610100% | ATA | ODE | WF1833299 | Elec | MAKE | ANSI 49 | 4626100% | 8 | 4609900% | 4610600% |  | TRUE | Mar-2026 | 10 | 6 | 2 | -4 | ON TIME | ON TIME | LATE BY ENG |  | I | -7 | NOT IMPACTED |  |  | -7 | ON TIME | JUAN CARLOS MIRANDA | 1 | 4610907% | 5.556%
PZ4 | 0050798656 | 002730 | 0050798656-002730 | TI LFAB2 - LEHI - TI | 4612700% | 4612000% | LEC |  | WF1829991 | Elec | MAKE | ANSI 49 | 4632400% | 28 | 4609000% | 4610000% |  | TRUE | Mar-2026 | 10 | 9 | 9 | 0 | ON TIME | ON TIME | ON TIME BY ENG |  | I | -20 | NOT IMPACTED |  |  | -20 | ON TIME | REBECA CISNEROS | 11 | 4610307% | 61.11%
PZ4 | 0050798656 | 002730 | 0050798656-002730 | TI LFAB2 - LEHI - TI | 4612700% | 4612000% | LEC |  | WF1830011 | Elec | BUY | ANSI 49 | 4632400% | 28 | 4609000% | 4610400% |  | TRUE | Mar-2026 | 10 | 11 | 9 | -2 | ON TIME | ON TIME | ON TIME BY ENG |  | I | -20 | NOT IMPACTED |  |  | -20 | ON TIME | REGINA LOPEZ | 2 | 4610442% | 11.76%
PZ4 | 0050753978 | 003780 | 0050753978-003780 | KAISER SAN JOSE MEDICAL CENTER HOSPITAL | 4605200% |  | RAS | CML | WF1830426 | Mech | CNG-BOM | ANSI 49 | 4632400% | -28 | 4609100% | 4609400% | 4609300% | FALSE | Mar-2026 | 10 | 4 | 3 | -1 | ON TIME | ON TIME | LATE BY ENG |  | C | 30 | IMPACTED |  |  | Closed | LATE | NA | 11 | 4609442% | 100%
PZ4 | 0051436677 | 000010 | 0051436677-000010 | HAINES WWTP EXPANSION | 4611600% | 4611100% | KYC | GHT | WF1830735 | Mech | MAKE | ANSI 49 | 4623000% | 19 | 4609100% | 4610100% |  | TRUE | Mar-2026 | 10 | 9 | 8 | -1 | ON TIME | ON TIME | ON TIME BY ENG |  | I | -12 | NOT IMPACTED |  |  | -12 | ON TIME | REBECA CISNEROS | 12 | 4610407% | 66.67%
PZ4 | 0051735870 | 000010 | 0051735870-000010 | PROJECT OPAL LLE3 | 4611100% | 4609800% | JAM | RCI | WF1819916 | Elec | MAKE | ANSI 49 | 4622700% | 30 | 4607000% | 4607700% |  | TRUE | Feb-2026 | 10 | 6 | 23 | 17 | LATE | SUPER LATE | ON TIME BY ENG |  | I | -8 | NOT IMPACTED |  |  | -8 | ON TIME | VICTOR HUGO RODRIGEZ TORRALBA | 12 | 4608007% | 66.67%
PZ4 | 0051434217 | 000330 | 0051434217-000330 | SMUD FAOB | 4610700% | 4611200% | JAM | AL | WF1830775 | Mech | MAKE | ANSI 49 | 4623200% | 13 | 4609100% | 4610400% | 4609900% | FALSE | Mar-2026 | 10 | 10 | 7 | -3 | ON TIME | ON TIME | ON TIME BY ENG |  | C | -7 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4610707% | 100%
PZ4 | 0051735870 | 000010 | 0051735870-000010 | PROJECT OPAL LLE3 | 4611100% | 4609800% | JAM | RCI | WF1829706 | Elec | BUY | ANSI 49 | 4622500% | 16 | 4609000% | 4610400% |  | TRUE | Mar-2026 | 10 | 11 | 9 | -2 | ON TIME | ON TIME | ON TIME BY ENG |  | I | -8 | NOT IMPACTED |  |  | -8 | ON TIME | JUAN CARLOS MIRANDA | 4 | 4610442% | 23.53%
PZ4 | 0050384250 | 001230 | 0050384250-001230 | NEW PARNASSUS HEIGHTS HOSPITAL - UCSF - | 4610600% |  | ASP | VHL | WF1831159 | Mech | MAKE | ANSI 49 | 4624000% | 11 | 4609200% | 4610100% | 4609800% | FALSE | Mar-2026 | 10 | 8 | 5 | -3 | ON TIME | ON TIME | ON TIME BY ENG |  | C | -7 | NOT IMPACTED |  |  | Closed | ON TIME | NA | 18 | 4610407% | 100%
PZ4 | 0051434217 | 000320 | 0051434217-000320 | SMUD FAOB | 4611200% | 4610500% | JAM | AL | WF1824069 | Elec | MAKE | ANSI 49 | 4622500% | 25 | 4607800% | 4608500% |  | TRUE | Feb-2026 | 10 | 6 | 17 | 11 | LATE | LATE | ON TIME BY ENG |  | I | -9 | NOT IMPACTED |  |  | -9 | ON TIME | VICTOR HUGO RODRIGEZ TORRALBA | 12 | 4608807% | 66.67%
PZ4 | 0051434217 | 000320 | 0051434217-000320 | SMUD FAOB | 4611200% | 4610500% | JAM | AL | WF1824080 | Elec | MAKE | ANSI 49 | 4622500% | 25 | 4607800% | 4608500% |  | TRUE | Feb-2026 | 10 | 6 | 17 | 11 | LATE | LATE | ON TIME BY ENG |  | I | -9 | NOT IMPACTED |  |  | -9 | ON TIME | VICTOR HUGO RODRIGEZ TORRALBA | 12 | 4608807% | 66.67%
PZ4 | 0051420926 | 000090 | 0051420926-000090 | SQD EXPANSION DE SISITEMAS DE ENERGIA | 4612900% | 4612200% | ASP |  | WF1832207 | Elec | BUY | ANSI 49 | 4625500% | 27 | 4609300% | 4611100% |  | TRUE | Mar-2026 | 10 | 13 | 6 | -7 | ON TIME | ON TIME | ON TIME BY ENG |  | I | -22 | NOT IMPACTED |  |  | -22 | ON TIME | DANIELA PAOLA GONZALEZ | 2 | 4611142% | 11.76%
PZ4 | 0051700206 | 000010 | 0051700206-000010 | EOEM-CUMMINS- HCA ST DAVID'S S AUSTIN | 4612200% | 4611500% | ALT | OAL | WF1832094 | Mech | BUY | ANSI 49 | 4625200% | 22 | 4609300% | 4610700% |  | TRUE | Mar-2026 | 10 | 11 | 6 | -5 | ON TIME | ON TIME | ON TIME BY ENG |  | I | -17 | NOT IMPACTED |  |  | -17 | ON TIME | REGINA LOPEZ | 2 | 4610742% | 11.76%
PZ4 | 0051420926 | 000090 | 0051420926-000090 | SQD EXPANSION DE SISITEMAS DE ENERGIA | 4612900% | 4612200% | ASP |  | WF1832497 | Elec | BUY | ANSI 49 | 4625500% | 26 | 4609400% | 4610800% |  | TRUE | Mar-2026 | 10 | 11 | 5 | -6 | ON TIME | ON TIME | ON TIME BY ENG |  | I | -22 | NOT IMPACTED |  |  | -22 | ON TIME | JUAN CARLOS MIRANDA | 2 | 4610842% | 11.76%
PZ4 | 0051420926 | 000090 | 0051420926-000090 | SQD EXPANSION DE SISITEMAS DE ENERGIA | 4612900% | 4612200% | ASP |  | WF1832514 | Elec | MAKE | ANSI 49 | 4625500% | 26 | 4609400% | 4610500% | 4609400% | FALSE | Mar-2026 | 10 | 8 | 1 | -7 | ON TIME | ON TIME | ON TIME BY ENG |  | X | -26 | NOT IMPACTED |  |  | Cancelled | ON TIME | NA | 0 | 4610807% | 0%
PZ4 | 0051700206 | 000010 | 0051700206-000010 | EOEM-CUMMINS- HCA ST DAVID'S S AUSTIN | 4612200% | 4611500% | ALT | OAL | WF1832093 | Mech | MAKE | ANSI 49 | 4625200% | 22 | 4609300% | 4610500% |  | TRUE | Mar-2026 | 10 | 9 | 6 | -3 | ON TIME | ON TIME | ON TIME BY ENG |  | X | -17 | NOT IMPACTED |  |  | Cancelled | ON TIME | NA | 6 | 4610807% | 33.33%
PZ4 | 0051420926 | 000090 | 0051420926-000090 | SQD EXPANSION DE SISITEMAS DE ENERGIA | 4612900% | 4612200% | ASP |  | WF1832507 | Elec | MAKE | ANSI 49 | 4625500% | 26 | 4609400% | 4610500% |  | TRUE | Mar-2026 | 10 | 8 | 5 | -3 | ON TIME | ON TIME | ON TIME BY ENG |  | I | -22 | NOT IMPACTED |  |  | -22 | ON TIME | JUAN CARLOS MIRANDA | 7 | 4610807% | 38.89%
PZ4 | 0051420926 | 000090 | 0051420926-000090 | SQD EXPANSION DE SISITEMAS DE ENERGIA | 4612900% | 4612200% | ASP |  | WF1832582 | Elec | MAKE | ANSI 49 | 4625500% | 26 | 4609400% | 4610500% |  | TRUE | Mar-2026 | 10 | 8 | 5 | -3 | ON TIME | ON TIME | ON TIME BY ENG |  | I | -22 | NOT IMPACTED |  |  | -22 | ON TIME | JUAN CARLOS MIRANDA | 1 | 4610807% | 5.556%
PZ4 | 0051897029 | 000010&000020 | 0051897029-000010&000020 | PCA RIVERVILLE, VA MILL PZ4 | 4613600% | 2026-04-17 | KRS |  | WF1832612 | Elec | BUY | ANSI 49 | 4623100% | 31 | 2026-03-13 | 2026-03-27 |  | TRUE | Mar-2026 | 10 | 11 | 5 | -6 | ON TIME | ON TIME | ON TIME BY ENG |  | I | -27 | NOT IMPACTED |  |  | -27 | ON TIME | JUAN ANTONIO CABELLO |  | 4610842% | 0%
PZ4 | 0051436677 | 000010 | 0051436677-000010 | HAINES WWTP EXPANSION | 4611600% | 2026-03-30 | KYC | GHT | WF1832617 | Mech | MAKE | ANSI 49 | 4622300% | 16 | 2026-03-13 | 2026-03-24 |  | TRUE | Mar-2026 | 10 | 8 | 5 | -3 | ON TIME | ON TIME | ON TIME BY ENG |  | I | -12 | NOT IMPACTED |  |  | -12 | ON TIME | JUAN ANTONIO CABELLO |  | 4610807% | 0%
PZ4 | 0051700206 | 000010 | 0051700206-000010 | EOEM-CUMMINS- HCA ST DAVID'S S AUSTIN | 4612200% | 4611500% | ALT | OAL | WF1832636 | Mech | MAKE | ANSI 49 | 4625200% | 21 | 2026-03-13 | 2026-03-24 |  | TRUE | Mar-2026 | 10 | 8 | 5 | -3 | ON TIME | ON TIME | ON TIME BY ENG |  | I | -17 | NOT IMPACTED |  |  | -17 | ON TIME | JUAN ANTONIO CABELLO | 6 | 4610807% | 33.33%
QED6 | 0051674363 | 000010 | 0051434217-000320 | SMUD FAOB | 4611200% | 4610500% | JAM | AL | WF1824081 | Mech | MAKE | ANSI 49 | 4622500% | 25 | 4607800% | 4608500% |  | TRUE | Feb-2026 | 10 | 6 | 17 | 11 | LATE | LATE | ON TIME BY ENG |  | I | -9 | NOT IMPACTED |  |  | -9 | ON TIME | VICTOR HUGO RODRIGEZ TORRALBA | 12 | 4608807% | 66.67%
PZ4 | 0051434217 | 000320 | 0051434217-000320 | SMUD FAOB | 4611200% | 4610500% | JAM | AL | WF1824092 | Elec | MAKE | ANSI 49 | 4622500% | 25 | 4607800% | 4608500% |  | TRUE | Feb-2026 | 10 | 6 | 17 | 11 | LATE | LATE | ON TIME BY ENG |  | I | -9 | NOT IMPACTED |  |  | -9 | ON TIME | VICTOR HUGO RODRIGEZ TORRALBA | 12 | 4608807% | 66.67%
PZ4 | 0051434217 | 000330 | 0051434217-000330 | SMUD FAOB | 4611200% | 4610700% | JAM | AL | WF1830776 | Mech | MAKE | ANSI 49 | 4621600% | 16 | 4609100% | 4610400% |  | TRUE | Mar-2026 | 10 | 10 | 8 | -2 | ON TIME | ON TIME | ON TIME BY ENG |  | I | -9 | NOT IMPACTED |  |  | -9 | ON TIME | JUAN CARLOS MIRANDA | 4 | 4610707% | 22.22%
PZ4 | 0051434217 | 000320 | 0051434217-000320 | SMUD FAOB | 4611200% | 4610700% | JAM | AL | WF1831181 | Mech | MAKE | ANSI 49 | 4611100% | 15 | 4609200% | 4610100% |  | TRUE | Mar-2026 | 10 | 8 | 7 | -1 | ON TIME | ON TIME | ON TIME BY ENG |  | I | -9 | NOT IMPACTED |  |  | -9 | ON TIME | FERNANDO CASAS | 15 | 4610407% | 83.33%
PZ4 | 0051425171 | 000660 | 0051425171-000660 | BONNEVILLE LOCK AND DAM BRADFORD ISLAND | 4612900% | 4611800% | JAM | ISQ | WF1833904 | Mech | MAKE | ANSI 49 | 4625100% | 23 | 2026-03-18 | 2026-03-25 |  | TRUE | Mar-2026 | 10 | 6 | 2 | -4 | ON TIME | ON TIME | ON TIME BY ENG |  | I | -22 | NOT IMPACTED |  |  | -22 | ON TIME | JUAN CARLOS MIRANDA | 0 | 4610907% | 0%
PZ4 | 0051897029 | 000010 | 0051897029-000010 | PCA RIVERVILLE, VA MILL PZ4 | 4613600% | 4612900% |  | ODE | WF1834048 | Mech | Make | ANSI 49 | 4623100% | 28 | 2026-03-18 | 2026-03-26 |  | TRUE | Mar-2026 | 10 | 7 | 2 | -5 | ON TIME | ON TIME | ON TIME BY ENG |  | I | -27 | NOT IMPACTED |  |  | -27 | ON TIME | JUAN CARLOS MIRANDA | 0 | 4611007% | 0%
Formulas:
Pre RM Opening Time = NETWORKDAYS.INTL(WFTracker[[#This Row],[Start date]],WFTracker[[#This Row],[RM]],1,Holidays!D619:D634)
Pre RM Opening Time = NETWORKDAYS.INTL(WFTracker[[#This Row],[Start date]],WFTracker[[#This Row],[RM]],1,Holidays!D797:[Sales Number, row above])
Completion Days Template = NETWORKDAYS.INTL(WFTracker[[#This Row],[Start date]],WFTracker[[#This Row],[Due date]],1,Holidays!D619:D634)
Completion Days Template = NETWORKDAYS.INTL(WFTracker[[#This Row],[Start date]],WFTracker[[#This Row],[Due date]],1,Holidays!D797:[Sales Number, row above])
Note on B1: Field Order Number
Note on C1: Line number
Note on D1: Sales Number
Note on E1: Job number
Note on F1: Deadline for releasing to manufacturing (BOM and DRAWINGS) by Eng
Note on H1: Application Engineer
Note on I1: Mechanical designer
Note on J1: Workflow ID on Oneshuttle
Note on K1: Team owner of the Workflow (Electrical or Mechanical)
Note on L1: Template (URGENT MAKE/ URGENT BUY)
Note on M1: Paint selected for the lineup
Note on O1: Working days in advance between RM and when the workflow was created (Start date - RM)
Note on P1: Date when the workflow was created.
Note on Q1: End date that Oneshuttle gives as a target (depends on the template).
Note on R1: Real end date that Oneshuttle registered.
Note on V1: Working days between Start date y Due date; ideally should match the template (Start date - Due date).
Note on W1: The real-life cycle of the workflow in working days.
Note on X1: Delay in working days according to the template (Start date - Due date)
Note on Z1: Classification ["SUPER LATE" (+15 days), "LATE", "ON TIME"] based on the template WF life cycle (if Active Time surpasses Template Completion Days then it is "LATE").
Note on AA1: Classification if the Eng submitted the WF on time based on the Lead Time template (It changed from an AVG of 5 days to an AVG of 10 days)
Note on AB1: Some reasons could be: -Substitution request -Change Orders -Engineering mistakes
Note on AC1: Current status of the workflow -I = Initiated -C = Completed -X = Cancelled
Note on AD1: Delay in working days that the life cycle of the WF has impacted the project based on RM date (Completion Date - RM)
Note on AF1: Working days that a PN has been worked through different WF in case of cancellations.
Note on AG1: Cause that made the Engineer to cancel the Workflow
Note on AH1: Criteria to escalate WF on "Urgent WF Closure teams group" < 5 working days before RM
Note on AL1: Still in development
Run Home
Run Weekly WF Report
Run Weekly WF Report
Run Quick Update View
Run Escalation
Update

## Workflow Dashboard
WF ALL TIME REPORT PZ4/QED6/QED2 | [7 empty] | WF MONTLY TIME REPORT PZ4/QED6/QED2 [FEB]
ACTIVE WF STATS |  |  | ACTIVE QUEUE
ACTIVE WORKFLOWS | 48 |  | Product | (All)
ACTIVE ELECTRIC | 21 |  | Status | I
ACTIVE MECHANIC | 27
|  |  | Job Name | RM | Average of Pre RM Opening Time | Average of % Of completion | Count of WF
HISTORIC WF STATS |  |  | AT&T 105 AUD – 9TH FLOOR SOUTH AON CLOUD | 4612900% | 31 | 53.43% | 2
|  |  | NEW PARNASSUS HEIGHTS HOSPITAL - UCSF - | 4610600% | 11 | 83.33% | 1
| MAKE | BUY | NEW PARNASSUS HEIGHTS HOSPITAL - UCSF - | 4609400% | 11 | 77.78% | 2
TEMPLATE LIFE CYCLE | 6.7875 | 8.9765 | SPACEX STARBASE GIGABAY UNIT SUBSTATIONS | 2025-12-26 | -58 | 0% | 1
REAL LIFE CYCLE | 9.86 | 9.3922 | NOVO NORDISK - BLDG QC CHEM-RM LAB - CLA | 4610100% | 10 | 66.67% | 1
|  |  | OP-250808-15689594 | 4609400% | 10 | 62.34% | 4
IMPACT STATS |  |  | PROJECT OPAL LLE3 | 4611100% | 23 | 42.16% | 2
|  |  | PROJECT ICY HOT CORE AND SHELL | 4609700% | 9.5 | 88.89% | 2
TOTAL WF LATE BY ENG | 174 OUT OF 856 |  | SMUD FAOB | 4611200% | 21.8333 | 56.48% | 6
AVG LIFE CYCLE FOR A WF LATE BY ENG | 7.7529 |  | SMUD FAOB | 4610700% | 13 | 83.33% | 1
AVG IMPACT OF LATE WF FOR RM CAUSED BY ENG | 16.2701 |  | CPS EMC UPGRADE - SAN ANTONIO - ALTERMAN | 4608700% | -5 | 61.11% | 1
REJECTION BY INCORRECT WF BY ENG | 5.14% |  | DUNEDIN WWTP ELECTRICAL SYSTEM UPGRADES | 4610800% | 17.8 | 59.02% | 5
TOP CANCELATION OFFENDER | ACTIVE IN US23 |  | POLK REGIONAL WC SE WELLFIELD AND WATER | 4610100% | 14 | 71.57% | 3
|  |  | UT RED MCCOMBS UNDERGRADUATE SCHOOL OF B | 4610800% | 19 | 11.76% | 1
CRITICAL WFs |  |  | TI LFAB2 - LEHI - TI | 4612700% | 28 | 36.44% | 2
|  |  | HAINES WWTP EXPANSION | 4611600% | 17.5 | 33.33% | 2
|  |  | SQD EXPANSION DE SISITEMAS DE ENERGIA | 4612900% | 26.25 | 16.99% | 4
Product | (All) |  | EOEM-CUMMINS- HCA ST DAVID'S S AUSTIN | 4612200% | 21.5 | 22.55% | 2
Status | I |  | PCA RIVERVILLE, VA MILL PZ4 | 4613600% | 29.5 | 0% | 2
Classification [Completion-RM] | LATE |  | DCH EAST KITCHEN MACHINE ROOM SWITCHBOAR | 4610800% | 8.5 | 0% | 2
|  |  | BONNEVILLE LOCK AND DAM BRADFORD ISLAND | 4612900% | 23 | 0% | 1
WF | RM | Job Name | BONNEVILLE LOCK AND DAM BRADFORD ISLAND | 4609800% | -2 | 0% | 1
WF1822717 | 4609400% | OP-250808-15689594 | Grand Total |  | 16.1875 | 45.45% | 48
WF1824061 | 4609400% | OP-250808-15689594
WF1824197 | 4609400% | NEW PARNASSUS HEIGHTS HOSPITAL - UCSF - | [5 empty] | ACTIVE QUEUE |  |  |  |  | CRITICAL WORKFLOWS
WF1825523 | 4609700% | PROJECT ICY HOT CORE AND SHELL
WF1826955 | 4609400% | NEW PARNASSUS HEIGHTS HOSPITAL - UCSF -
WF1828531 | 4609400% | OP-250808-15689594
WF1829111 | 4609700% | PROJECT ICY HOT CORE AND SHELL
WF1829894 | 4609400% | OP-250808-15689594
WF1832012 | 4608700% | CPS EMC UPGRADE - SAN ANTONIO - ALTERMAN | [5 empty] | Product | (All)
WF1832921 | 4601700% | SPACEX STARBASE GIGABAY UNIT SUBSTATIONS | [5 empty] | Status | I
WF1833724 | 4609800% | BONNEVILLE LOCK AND DAM BRADFORD ISLAND
[8 empty] | Job Name | RM | Average of Pre RM Opening Time | Average of % Of completion | Count of WF | Product | (All)
[8 empty] | AT&T 105 AUD – 9TH FLOOR SOUTH AON CLOUD | 4612900% | 31 | 53.43% | 2 | Status | I
[8 empty] | NEW PARNASSUS HEIGHTS HOSPITAL - UCSF - | 4609400% | 11 | 77.78% | 2 | Classification [Completion-RM] | LATE
[8 empty] | NEW PARNASSUS HEIGHTS HOSPITAL - UCSF - | 4610600% | 11 | 83.33% | 1
[8 empty] | SPACEX STARBASE GIGABAY UNIT SUBSTATIONS | 2025-12-26 | -58 | 0% | 1 | Job Name | RM | Average of Pre RM Opening Time | Average of % Of completion | Count of WF
[8 empty] | NOVO NORDISK - BLDG QC CHEM-RM LAB - CLA | 4610100% | 10 | 66.67% | 1 | NEW PARNASSUS HEIGHTS HOSPITAL - UCSF - | 4609400% | 11 | 77.78% | 2
[8 empty] | OP-250808-15689594 | 4609400% | 10 | 62.34% | 4 | SPACEX STARBASE GIGABAY UNIT SUBSTATIONS | 2025-12-26 | -58 | 0% | 1
[8 empty] | PROJECT OPAL LLE3 | 4611100% | 23 | 42.16% | 2 | OP-250808-15689594 | 4609400% | 10 | 62.34% | 4
[8 empty] | PROJECT ICY HOT CORE AND SHELL | 4609700% | 9.5 | 88.89% | 2 | PROJECT ICY HOT CORE AND SHELL | 4609700% | 9.5 | 88.89% | 2
[8 empty] | SMUD FAOB | 4610700% | 13 | 83.33% | 1 | CPS EMC UPGRADE - SAN ANTONIO - ALTERMAN | 4608700% | -5 | 61.11% | 1
[8 empty] | SMUD FAOB | 4611200% | 21.8333 | 56.48% | 6 | BONNEVILLE LOCK AND DAM BRADFORD ISLAND | 4609800% | -2 | 0% | 1
[8 empty] | CPS EMC UPGRADE - SAN ANTONIO - ALTERMAN | 4608700% | -5 | 61.11% | 1 | Grand Total |  | 1.4545 | 58.53% | 11
[8 empty] | DUNEDIN WWTP ELECTRICAL SYSTEM UPGRADES | 4610800% | 17.8 | 59.02% | 5
[8 empty] | POLK REGIONAL WC SE WELLFIELD AND WATER | 4610100% | 14 | 71.57% | 3
[8 empty] | UT RED MCCOMBS UNDERGRADUATE SCHOOL OF B | 4610800% | 19 | 11.76% | 1
[8 empty] | TI LFAB2 - LEHI - TI | 4612700% | 28 | 36.44% | 2
[8 empty] | HAINES WWTP EXPANSION | 4611600% | 17.5 | 33.33% | 2
[8 empty] | SQD EXPANSION DE SISITEMAS DE ENERGIA | 4612900% | 26.25 | 16.99% | 4
[8 empty] | EOEM-CUMMINS- HCA ST DAVID'S S AUSTIN | 4612200% | 21.5 | 22.55% | 2
[8 empty] | PCA RIVERVILLE, VA MILL PZ4 | 4613600% | 29.5 | 0% | 2
[8 empty] | DCH EAST KITCHEN MACHINE ROOM SWITCHBOAR | 4610800% | 8.5 | 0% | 2
[8 empty] | BONNEVILLE LOCK AND DAM BRADFORD ISLAND | 4609800% | -2 | 0% | 1
[8 empty] | BONNEVILLE LOCK AND DAM BRADFORD ISLAND | 4612900% | 23 | 0% | 1
[8 empty] | Grand Total |  | 16.1875 | 45.45% | 48